## Summary (hidden)
| Priority |  |  | Response Needed from Nan
Building |  | 03055-001.0 | Adhesive-bonded Reinforcing Bars and All threads In Concrete | Submittal # | Name
|  | 03071-001.0 | Sika Epoxies | 01292-001.0 | Detailed Breakdown of Project Cost
|  | 03111-001.0 | Geofoam | 01321-002.0 | Pre-liminary Schedule
|  | 03111-002.0 | Geofoam: Adhesive | 03931-001.0 | Epoxy
|  | 03150-001.0 | Expansion Joint | 11555-001.0 | Tekleen
| HIGH PRIORITY | 03150-002.0 | PVC Waterstop Sika | 15241-001.0 | HDPE
| HIGH PRIORITY | 03200-002.0 | CMC Rebar: Shop Drawings | 01450-001.0 | Independent Lab Concrete Testing
|  | 04055-001.0 | Product Data Hilti HY-270 Adhesive Anchor Sysstem | 15832-001.0 | Odor Control Fans
|  | 07210-001.0 | Building Insulation | 01756-001.0 | TSC Requalifications
|  | 07410-001.0 | Preformed Metal | 02312-001.0 | CLSM Mix Design
|  | 09310-001.0 | Ceramic Tiling | 03200-001.0 | CMC Rebar Concrete reinforcing Accessories
|  | 09650-001.0 | Resilient Flooring
|  | 09652-001.0 | Resilient Base and Accessories: Base and Adhesive
|  | 13120-001.0 | Pre-Engineered Structures
Civil | HIGH PRIORITY | 02256-002.0 | Probe and Grout Plan
| HIGH PRIORITY | 02260-001.0 | Vibration Monitoring Program
|  | 02260-002.0 | Vibration Monitoring: Baseline Data
|  | 02312-001.0 | CLSM Mix Design
|  | 02370-001.1 | Riprap Resubmittal – Puna Rock
|  | 02762-001.1 | Traffic Signs
| HIGH PRIORITY | 02820-001.3 | Islandwide – Fences and Gate
|  | 15052-001.0 | Concrete Encasement
|  | 16133-001.0 | Duct Banks: Shop Drawings
EQUIPMENT |  | 11294B-001.0 | HD Fabricated SS Slide Gates
|  | 11313F-001.0 | Optimal Water
|  | 11395D-001.0 | Daniel Company - BTF
|  | 12330-001.0 | Camlock Submittal
|  | 12330-002.0 | Bins
MECHANICAL | HIGH PRIORITY | 02553-001.0 | Temporary Bypass - Bar Screen
|  | 02667-001.1 | Hot Tapping and Line Stopping
|  | 15110-001.0 | Product Submittal: Sliding Valve Boxes
|  | 15211-001.0 | Ductile Iron Pipe: AWWA C151
|  | 15230-001.0 | PVC C900
|  | 15230-002.0 | SCH80 PVC
|  | 15230-003.0 | Solvent Cement and Primer
|  | 15814-001.0 | FIBERGLASS REINFORCED PLASTIC DUCTS
|  | 15830-001.0 | Fans
ELEC |  | 02581-001.0 | Precast Electrical Structure Mix Design
SCHEDULE
QUALITY CONTROL |  | 01450-001.1 | **Resubmittal for Trueform LLC Qualifcations
|  | 01460-002.0 | CQCM Replacement Qualifications
Note: ** to be discussed with Enginner

## Scheduler
note: submittal status code: AN - Approved no comments, AC - Approved no comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 01140 | WORK RESTRICTIONS |  | JO/JT | 1.02-A | Baseline Schedule with MOP tasks. |  |  |  |  | This is space is intentionnaly left blank for scrolling
|  |  |  | JO/JT | 1.02-B | Method of Procedure (MOP) Form.
|  |  |  | JO/JT | 1.02-C | Method of Procedure (MOP) Log.
|  |  |  | JO/JT | 1.02-D | Progress Schedule with MOP tasks.
01321-001.1 | 01321 | Scheduler and Reports | Beeman's Qualification | JO | N/A | Scheduler Qualification | 2025-04-15 | 2025-04-23 |  | REV
01321-001.2 | 01321 | Scheduler and Reports | Jude Qualification | JO | N/A | Scheduler Qualification | 2025-05-13 | 2025-08-12 |  | AN
01321-002.0 | 01322 | Scheduler and Reports |  | JO | 1.02-A | Submit preliminary and baseline schedule. | 2025-05-07 | 2025-05-23 |  | REV
01321-003.0 | 01322 | Scheduler and Reports |  | JO | 1.02-A | Submit preliminary and baseline schedule. | 2025-09-15 |  |  | Submitted
| 01323 | Scheduler and Reports |  | JO | 1.02-B | Submit preliminary and baseline Detailed Breakdown of Project Costs.
| 01324 | Scheduler and Reports |  | QC | 1.02-C | Submit preliminary and baseline schedule of submittals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 01325 | Scheduler and Reports |  | JO | 1.02-D | Submit, on a monthly basis, updated schedules as specified.
| 01326 | Scheduler and Reports |  | JO | 1.02-E | Submit final schedule update as specified.
| 01327 | Scheduler and Reports |  | JO | 1.02-F | Submit revised schedules and time impact analyses as specified.
| 01328 | Scheduler and Reports |  | JO | 1.02-G-2 | 3 sets of the CPM network and/or bar chart (as specified by the Owner) on D-size sheets. a. Color-coding to be specified by the Owner.
| 01329 | Scheduler and Reports |  | JO | 1.02-G-3 | 3 sets of tabular reports listing all activities sorted numerically identifying duration, early start, late start, early finish, late finish, total float, and all predecessor/successor information.
| 01330 | Scheduler and Reports |  | JO | 1.02-G-4 | 2 sets of CPM Schedule data electronic files in a native backed-up file (.xer).

## Precon
note: submittal status code: AN - Approved no Exceptions, AC - Approved see comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submital Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
00436-001.0 | 00436 | LIST OF EQUIPMENT MANUFACTURERS | List of Equipment Manufacturers | Table 1 | 1.01 | List of Selected Equipment Manufacturers with circling the manufacturer or supplier that will furnish the respective item of equipment for the Work. | 2025-04-07 | 2025-04-24 |  |  | This is space is intentionnaly left blank for scrolling
| 01140 | WORK RESTRICTIONS |  |  | 1.02-A | Baseline Schedule with MOP tasks.
[5 empty] | 1.02-B | Method of Procedure (MOP) Form.
[5 empty] | 1.02-C | Method of Procedure (MOP) Log.
[5 empty] | 1.02-D | Progress Schedule with MOP tasks.
01150-003.0 | 1150 | MITIGATION AND MONITORING REQUIREMENTS | Dust Control Management Plan | MN | 1.02-B | Dust control management plan. | 2025-05-28 | 2025-06-02
01150-003.1 | 01150 | MITIGATION AND MONITORING REQUIREMENTS | Dust Control Management Plan | MN | 1.02-B | Dust control management plan. | 2025-06-27 | 2025-07-31 |  | AN
01150-001.0 | 01150 | MITIGATION AND MONITORING REQUIREMENTS | Wildlife Biologist Qualifications | KN | 1.02-C | Qualifications of wildlife biologist performing Hawaiian geese surveys. | 2025-04-25 | 2025-04-30 |  | AN
01150-002.0 | 01150 | MITIGATION AND MONITORING REQUIREMENTS | Bird Survey *For Information Only* | CQC Team | N/A | Intial Bird Survey | 2025-05-19 | 2025-05-19 |  | RA | This is space is intentionnaly left blank for scrolling
01292-001.0 | 01292 | DETAILED BREAKDOWN OF PROJECT COSTS | Preliminary Detailed Breakdown of Project Costs | MR | 1.03-A | Submit Detailed Breakdown of Project Costs for the Preliminary Schedule as specified in, Section 01321 - Schedules and Reports. | 2025-05-23 | 2025-05-28 |  | NCR
| 01294 | APPLICATIONS FOR PAYMENT |  |  | 1.04-A | Submit Application for Payment and Substantiating Data with cover letter.
1330-001.0 | 01330 | SUBMITTAL PROCEDURES | Site Safety and Health Plan | RI | N/A | Site Specific Safety and Health Plan for entire Project | 2025-05-27 | 2025-07-31 |  | RA
| 01354 | HAZARDOUS MATERIAL PROCEDURES |  | QC | 1.03-A | Submit laboratory reports, hazardous material removal plans, and certifications.
[5 empty] | 1.03-B-1 | Removal and Legal Disposal of Asbestos Cement Pipe Plan.
| 01357 | DELEGATED DESIGN PROCEDURES |  |  | 1.04-A-1 | Contractor’s Professional Engineer’s qualifications.
[5 empty] | 1.04-A-2 | Contractor’s Professional Engineer Professional Liability Insurance certificate.
[5 empty] | 1.04-B-1 | Product data.
[5 empty] | 1.04-B-2 | Design documents with signature and seal from the Contractor’s Professional Engineer.
[5 empty] | 1.04-B-3 | Lists and schedules.
[5 empty] | 1.04-C-1 | Contractor’s Professional Engineer’s comments on submittals.
[5 empty] | 1.04-C-2 | Other construction documents, as required.
01500-001.0 | 01500 | TEMPORARY FACILITIES AND CONTROLS | TEMPORARY FACILITIES & CONTROLS FIELD OFFICE | Civil | 1.12 | Owner’s and Engineer’s/Construction Manager’s Field Office. | 2025-04-15 | 2025-04-16 |  | REV
01500-001.1 | 01500 | TEMPORARY FACILITIES AND CONTROLS | Resubmittal -TEMPORARY FACILITIES & CONTROLS FIELD OFFICE | Civil | 1.12 | Owner’s and Engineer’s/Construction Manager’s Field Office. | 2025-05-07 | 2025-05-13 |  | REV
01500-002.0 | 01500 |  | Project Sign | Civil | 1.10-G | For all signs, submit Designs, scaled layouts, and mockups of the signs in color and with line, lettering styles, and scales for approval. | 2025-06-13 | 2025-06-24 |  | RA
01573-001.0 | 01573 | EROSION AND SEDIMENT CONTROL | Filter Fence | QC | 1.03-D | Manufacturer’s catalog sheets and other product data on geotextile fabric, erosion control blankets, straw bales, silt fencing, etc. | 2025-05-06 | 2025-05-06 |  | REV
01573-001.1 | 01573 | EROSION AND SEDIMENT CONTROL | Resubmittal: DOUBLE NET MULCH SOCK | QC | 1.03-D | Manufacturer’s catalog sheets and other product data on geotextile fabric, erosion control blankets, straw bales, silt fencing, etc. | 2025-05-07 | 2025-05-09 |  | RA
01573-002.0 | 01573 | EROSION AND SEDIMENT CONTROL | Erosion Control Socks | QC | 1.03-A-2 | Provide samples of previously prepared, submitted, and accepted SWPPPs for similar type projects. | 2025-05-09 | 2025-05-09 |  | RA
| 01573 | EROSION AND SEDIMENT CONTROL | FIO - NGPC NPDES | QC | N/A | FIO (For information Only) Approved NPDES Permits, No gov't approval required nor desired. | 2025-06-09
| 01573 | EROSION AND SEDIMENT CONTROL | FIO - NGPC NPDES |  | 1.03-C | Copies of environmental permits and all correspondence received from governmental agencies regarding environmental compliance. | 2025-06-09
| 01573 | EROSION AND SEDIMENT CONTROL | FIO - NGPC NPDES |  |  | Provide samples of previously prepared, submitted, and accepted SWPPPs for similar type projects. | 2025-06-09
10401-001.0 | 10401 | First Aid Kits | QC | QC | 1.03-A | Shop drawings. | 2025-05-05 | 2025-05-13
10401-002.0 | 10401 | First Aid Kits | QC | QC | 1.03-B-1 | Product data: Submit manufacturer's product literature information for products specified. | 2025-05-05 | 2025-05-13
| 10520 |  |  | QC | 1.03-A-1 | Product data: Extinguishers: Materials description for fire extinguishers; include ratings and classifications.
|  |  |  | QC | 1.03-A-2 | Product data: Installation instructions for each product specified.
|  |  |  | QC | 1.03-B | Shop drawings.

## Mech
note: submittal status code: AN - Approved no comments, AC - Approved with comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 01751 | DIGESTER PRESSURE TESTING |  | QC/Mech | 1.03-A | Submit testing plan with detailed steps and procedures to be followed, in accordance with requirements in Section 01756 - Commissioning. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 01783 | WARRANTIES AND BONDS |  |  | 1.02-A-1 | Submit manufacturer's warranty prior to fabrication and shipment of the item from the manufacturer's facility.
[5 empty] | 1.02-A-2 | Submit manufacturer's special warranty when specified.
[5 empty] | 1.02-B | Provide consolidated warranties and bonds within 15 calendar days of Substantial Completion.
02553-001.0 | 02553 | TEMPORARY BYPASS PUMPING | Temporary Bar screen | Mech | 1.04-A | Prepare and submit a project-specific wastewater bypass pumping plan with completed wastewater bypass pumping checklist. | 2025-08-04 |  |  | Submitted | This is space is intentionnaly left blank for scrolling
02667-001.0 | 02667 | HOT TAPPING AND LINE STOPPING | HOT TAPPING AND LINE STOPPING | NN | 1.02-B | Experience summary and references for specialty contractor to perform the work. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-C | Step-by-step description of procedures to be used for hot tapping and line stopping. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-D | Shop drawings for all materials used in the hot tapping and line stopping of the pipeline. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-E | Installation procedures including tapping sleeves and pressure plate, tapping nozzle and appurtenances, and line stop. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-F | Installation and removal procedures for the line stop. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-G | List of equipment to be used in the installation with demonstration of backup equipment available to be on site prior to commencement of work. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-H | Calculations for design of tapping sleeves, draw structure, pressure plate, and line stop. | 2025-04-21 | 2025-04-21
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-I | Letter verifying that all equipment and specialized appurtenances are provided by one supplier. | 2025-04-21 | 2025-04-21
02667-001.1 | 02667 | HOT TAPPING AND LINE STOPPING | HOT TAPPING AND LINE STOPPING | NN | 1.02-B | Experience summary and references for specialty contractor to perform the work. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-C | Step-by-step description of procedures to be used for hot tapping and line stopping. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-D | Shop drawings for all materials used in the hot tapping and line stopping of the pipeline. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-E | Installation procedures including tapping sleeves and pressure plate, tapping nozzle and appurtenances, and line stop. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-F | Installation and removal procedures for the line stop. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-G | List of equipment to be used in the installation with demonstration of backup equipment available to be on site prior to commencement of work. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-H | Calculations for design of tapping sleeves, draw structure, pressure plate, and line stop. | 2025-06-13 | 2025-09-03 |  | Rev
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-I | Letter verifying that all equipment and specialized appurtenances are provided by one supplier. | 2025-06-13 | 2025-09-03 |  | Rev
02667-001.2 | 02667 | HOT TAPPING AND LINE STOPPING | HOT TAPPING AND LINE STOPPING | NN | 1.02-B | Experience summary and references for specialty contractor to perform the work. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-C | Step-by-step description of procedures to be used for hot tapping and line stopping. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-D | Shop drawings for all materials used in the hot tapping and line stopping of the pipeline. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-E | Installation procedures including tapping sleeves and pressure plate, tapping nozzle and appurtenances, and line stop. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-F | Installation and removal procedures for the line stop. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-G | List of equipment to be used in the installation with demonstration of backup equipment available to be on site prior to commencement of work. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-H | Calculations for design of tapping sleeves, draw structure, pressure plate, and line stop. | 2025-09-10 |  |  | submitted
|  |  | HOT TAPPING AND LINE STOPPING | NN | 1.02-I | Letter verifying that all equipment and specialized appurtenances are provided by one supplier. | 2025-09-10 |  |  | submitted
12330-001.0 | 12330 | BINS | Camlock Submittal | Jyun | 1.02-B | Product data. | 2025-06-05 | 2025-09-03 | 2025-10-03 | NCR
12330-002.0 | 12330 | BINS | Bins | Jyun | 1.02-C | Shop drawings. | 2025-06-16 |  |  | Submitted
| 12330 | BINS |  |  | 1.02-D | Warranty conforming to Section 01783 - Warranties and Bonds.
| 12330 | BINS |  |  | 1.02-E | Operation and Maintenance Manual.
| 12330 | BINS |  |  | 1.02-F | Manufacturer's installation instructions: Indicate special installation requirements.
| 13206A | FIBERGLASS REINFORCED PLASTIC ABOVEGROUND STORAGE TANKS |  |  | 1.03-B | Shop Drawings.
[5 empty] | 1.03-C-1 | Calculations for anchoring equipment to structures.
13206F-001.0 | 13206F | HYDROPNEUMATIC BLADDER TANK | Wessels, Co. (Product Data & Shop Dwg) | Equip | 1.04-B | Product data. | 2025-08-29 | 2025-09-08 | 2025-10-08 | NCR
13206F-001.0 | 13206F | HYDROPNEUMATIC BLADDER TANK | Wessels, Co. (Product Data & Shop Dwg) | Equip | 1.04-C | Shop Drawings. | 2025-08-29 | 2025-09-08 | 2025-10-08 | NCR | This is space is intentionnaly left blank for scrolling
| 13206F | HYDROPNEUMATIC BLADDER TANK |  |  | 1.04-D-1 | Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
| 13206F | HYDROPNEUMATIC BLADDER TANK |  |  | 1.04-E-1 | Manufacturer's installation instructions.
| 13206F | HYDROPNEUMATIC BLADDER TANK |  |  | 1.04-E-2 | Equipment anchor setting template.
| 13206F | HYDROPNEUMATIC BLADDER TANK |  |  | 1.04-E-3 | Complete details for installation of the equipment including rigging, moving, and setting into place.
| 13206F | HYDROPNEUMATIC BLADDER TANK |  |  | 1.04-F-1 | Certification of compliance with ASME BPVC, and data reports in accordance with the ASME BPVC and other local codes as required.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-B | Submit statement that fabrication will be in accordance with API 650, revision number and date, and appendix applicable for the tank, signed by an authorized representative from the tank manufacturer.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-C | Product data sheets for tank accessories including manufacturer-provided piping.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-D | Shop drawings. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-E | Calculations.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-F | Welder qualifications.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-G | Instructions for handling, storage, and installation of tanks.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-H | Submit certification that tank and its appurtenances have been cleaned and passivated per Section 05500 - Metal Fabrications.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-I | API 650 Certifications.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-J | Inspection records and certified mill tests for stainless steel plate and structural members.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-K | Warranty.
| 13206N | WELDED STAINLESS STEEL ABOVEGROUND STORAGE TANKS |  |  | 1.03-L | Manufacturer’s field-testing requirements.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  | M. Nakai | 1.03-A | Submit as specified in Section 01330 - Submittal Procedures and Section 15050 - Common Work Results for Mechanical Equipment.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  |  | 1.03-B | Shop drawings.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  |  | 1.03-C | Calculations.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | QC |  | 1.03-D-1 | Quality control submittals: Certificate of suitability with diesel and methanol.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | QC |  | 1.03-D-2 | Quality control submittals: Certificate of compliance with the specified regulations.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | QC |  | 1.03-D-3 | Quality control submittals: Obtain Engineer's acceptance of certificates before tank is brought on-site.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | QC |  | 1.03-D-4 | Quality control submittals: Contractor's plan for coordination with tank manufacturer on the size, number, and location of the fittings required in the tank for the insertion of mechanical and electrical equipment.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  |  | 1.03-E | Operation and maintenance manuals.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | TSC |  | 1.03-F-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK | TSC |  | 1.03-F-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  |  | 1.03-G | Manufacturer's installation instructions.
| 13212C(ADD8) | ABOVEGROUND FUEL-STORAGE TANK AND APPURTENANCES – STEEL VAULTED TANK |  |  | 1.03-H | Submit a recommended list of spare parts including quantities and maintenance supplies.
| 13214(ADD6) | FUEL SYSTEM ACCESSORIES |  | M. Nakai | 1.03-A | Submit as specified in Section 01330 - Submittal Procedures and Section 15050 - Common Work Results for Mechanical Equipment.
[5 empty] | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
| 13215 | DIGESTER CLEANING |  |  | 1.06-A | Anaerobic Digester Cleaning Work Plan.
[5 empty] | 1.06-B | Disposal records on a daily basis.
| 13233 | FIXED STEEL DOME DIGESTER COVERS |  |  | 1.03-A | Complete fabrication, assembly and installation drawings, and operation, maintenance and storage instructions, together with detailed specifications and data covering materials used, parts, devices and other accessories forming a part of the equipment furnished.
[5 empty] | 1.03-B | Technical Manual: Complete operation and maintenance instruction, lubrication schedules and troubleshooting guides.
| 13446 | VALVE AND GATE ACTUATORS |  |  | 1.03-A | Shop drawings.
| 13447 | ELECTRIC ACTUATORS |  |  | 1.04-B | Provide a complete list/schedule of all actuators being provided with their associated tag names as indicated on the design drawings and/or specifications, service process area and the size of the valve they are actuating.
[5 empty] | 1.04-C | Product data.
[5 empty] | 1.04-D | Shop drawings.
[5 empty] | 1.04-E | Calculations.
[5 empty] | 1.04-F | Provide letters from both the electric actuator manufacturer and the valve (or gate) manufacturer confirming that they have coordinated the electric actuator selection with the specified valve design requirements, including operating speed.
[5 empty] | 1.04-G | Provide draft vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.04-H-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-H-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-I-1 | Project closeout documents: Provide final vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
| 13930 | WET PIPE FIRE EXTINGUISHING SYSTEMS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C-1 | Delegated Design Submittals: Shop Drawings.
[5 empty] | 1.04-C-2 | Delegated Design Submittals: Calculation worksheet.
[5 empty] | 1.04-D | Local fire authority approval for the entire system design.
[5 empty] | 1.04-E-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-E-1-b | Commissioning Submittals: Certificates.
[5 empty] | 1.04-E-1-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-E-1-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.04-E-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-E-1-f | Commissioning Submittals: Owner Training.
[5 empty] | 1.04-F-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operating and Maintenance Manuals.
| 14555 | SHAFTLESS SCREW CONVEYOR SYSTEM |  |  | 1.04-B | Installation List.
[5 empty] | 1.04-C | Product Data.
[5 empty] | 1.04-D | Shop Drawings.
[5 empty] | 1.04-E | Detailed electrical and instrumentation drawings and information.
[5 empty] | 1.04-F | Separate certification from the spiral manufacturer.
[5 empty] | 1.04-G | Complete Bill of Materials with part numbers.
[5 empty] | 1.04-H | Calculations: Detailed calculations and design data verifying conformance with the Drawings and Specifications.
[5 empty] | 1.04-I | Manufacturer's Installation Instructions.
[5 empty] | 1.04-J | Motor data per Section 16222 - Low Voltage Motors up to 500 Horsepower.
|  |  | QC |  | 1.04-K-1 | Quality Control Submittals: Detailed performance test procedures: Source quality control and field testing.
|  |  | QC |  | 1.04-K-2 | Quality Control Submittals: Performance test data including measured leakage rates of conveyor gates.
|  |  | QC |  | 1.04-K-3 | Quality Control Submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning and this Section.
|  |  | QC |  | 1.04-K-4 | Quality Control Submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-L | Operation and Maintenance Manual per Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.04-M | Wiring Schematics.
[5 empty] | 1.04-N | Fabrication drawings for the Vendor Control Panel.
[5 empty] | 1.04-O | Technician Qualifications Resume: Submit resume of technician(s) to perform manufacturer’s field services.
| 14556 | SHAFTED SCREW CONVEYORS |  |  | 1.04-B | Submit motor information as specified in Section 16222 - Low Voltage Motors up to 500 Horsepower and in this Section.
[5 empty] | 1.04-C | Installation List.
[5 empty] | 1.04-D | Shop Drawings.
[5 empty] | 1.04-E | Detailed electrical and instrumentation drawings and information.
[5 empty] | 1.04-F | Details of storage and off-loading requirements.
[5 empty] | 1.04-G | Sample warranty.
[5 empty] | 1.04-H | Calculations: Detailed calculations and design data verifying conformance with the Drawings and Specifications. |  |  |  |  | This is space is intentionnaly left blank for scrolling
|  |  | QC |  | 1.04-I | Quality Control Submittals: Submit manufacturer's certified performance, material and equipment records, and qualifications as specified.
[5 empty] | 1.04-J | Manufacturer's installation instructions.
[5 empty] | 1.04-K | Operation and Maintenance: Submit four copies of O&M Manual for each screw conveyor system.
| 14592 | SLUDGE STORAGE BIN |  |  | 1.04-B | Calculations: Submit structural and seismic calculations signed by a Professional Engineer licensed in the State of Hawaii.
| 14612 | DAVIT CRANES |  |  | 1.02-B | Product data.
[5 empty] | 1.02-C | Shop drawings and calculations.
[5 empty] | 1.02-D-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.02-E-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 14624 | MONORAIL SYSTEM |  |  | 1.05-B | Product data.
[5 empty] | 1.05-C | Shop drawings.
[5 empty] | 1.05-D | Calculations.
[5 empty] | 1.05-E-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-F-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.05-G | Certificates.
| 14633 | TOP RUNNING DOUBLE GIRDER BRIDGE CRANES |  |  | 1.05-B | Product data.
[5 empty] | 1.05-C | Calculations.
[5 empty] | 1.05-D | Shop drawings.
[5 empty] | 1.05-E-1 | Commissioning submittals: Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-E-2 | Commissioning submittals: Manufacturer's Certificate of Compliance with Federal Regulations.
[5 empty] | 1.05-E-3 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-F | Design data: Structural and seismic calculations for rails and bridge beams.
[5 empty] | 1.05-G | Certificates.
[5 empty] | 1.05-H-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals
| 14650 | JIB CRANES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings and calculations.
[5 empty] | 1.03-D-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-E-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
| 14670 | WINCHES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Warranty.
[5 empty] | 1.03-D | Complete bill of materials.
[5 empty] | 1.03-E | Manufacturer's installation instructions.
[5 empty] | 1.03-F | Operation and Maintenance Manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.03-G | Shop drawings.
[5 empty] | 1.03-H | Product data.
[5 empty] | 1.03-J | Operations and maintenance data.
| 15050 | COMMON WORK RESULTS FOR MECHANICAL EQUIPMENT |  |  | 1.06-C | Product data.
[5 empty] | 1.06-D | Shop drawings.
[5 empty] | 1.06-E | Calculations.
[5 empty] | 1.06-F | Operation and maintenance manuals.
[5 empty] | 1.06-G | Commissioning submittals: As specified in Section 01756 - Commissioning.
[5 empty] | 1.06-H | Project closeout documents: As specified in Section 01770 - Closeout Procedures.
| 15052 | COMMON WORK RESULTS FOR GENERAL PIPING |  |  | 1.04-B | Product data.
15052-001.0 | 15052 | COMMON WORK RESULTS FOR GENERAL PIPING | Concrete Encasement |  | 1.04 B - 1(G) | Layouts - Shop drawings | 2025-08-19 | 2025-09-10 |  | REV
15052-001.1 | 15052 | COMMON WORK RESULTS FOR GENERAL PIPING | Concrete Encasement |  | 1.04 B - 1(G) | Layouts - Shop drawings | 2025-09-11 |  |  | submitted
| 15052 | COMMON WORK RESULTS FOR GENERAL PIPING |  |  | 1.04-C | Calculations.
| 15057 | FUSION BONDED EPOXY LINING |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Test reports: Include manufacturer's certification that lining passed tests.
[5 empty] | 1.03-C | Manufacturer's application instructions.
| 15061 | PIPE SUPPORTS |  |  | 1.03-B | Product data.
| 15062 | PREFORMED CHANNEL PIPE SUPPORT SYSTEM |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Calculations.
| 15063 | NON-METALLIC PIPE SUPPORT SYSTEM |  |  | 1.03-B | Shop drawings.
[5 empty] | 1.03-C | Calculations.
15076-001.0 | 15076 | PIPE IDENTIFICATION | Detectable warning tape | Uriah/QC | 1.03-B-1 | Product data. | 2025-09-25 |  |  | Submitted
| 15076 | PIPE IDENTIFICATION |  |  | 1.03-B-2 | Samples.
| 15076 | PIPE IDENTIFICATION |  |  | 1.03-B-3 | Manufacturer's installation instructions.
| 15076 | PIPE IDENTIFICATION |  |  | 1.03-B-4-a | Operation and Maintenance Data.
| 15076 | PIPE IDENTIFICATION |  |  | 1.03-B-4-b | Warranty.
| 15082 | PIPING INSULATION |  | RL Ohana | 1.04-B | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
| 15084 | DUCTWORK INSULATION |  |  | 1.03-B | Product data: As specified in Specifications Section 15052: Common Work Results for General Piping.
15110-001.0 | 15110 | COMMON WORK RESULTS FOR VALVES | ValveBox |  | 1.03-B | Product data. | 2025-06-05 | 2025-09-04 |  | AN
| 15110 | COMMON WORK RESULTS FOR VALVES |  |  | 1.03-C | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
| 15110 | COMMON WORK RESULTS FOR VALVES |  |  | 1.03-D | Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 15110 | COMMON WORK RESULTS FOR VALVES |  |  | 1.03-E | Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15111 | BALL VALVES |  |  | 1.03-B | Product data: As specified in Section 15110 - Common Work Results for Valves.
[5 empty] | 1.03-C | For valves specified to have electric actuators, provide letters from both the valve manufacturer and the electric actuator manufacturer confirming that they have coordinated the electric actuator selection with the specified valve design requirements
[5 empty] | 1.03-D-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15112 | BUTTERFLY VALVES |  |  | 1.03-B | Product data: 15110 - Common Work Results for Valves.
[5 empty] | 1.03-C-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15114 | CHECK VALVES |  |  | 1.03-B | Product data: As specified in Section 01600 - Product Requirements.
[5 empty] | 1.03-C-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation Compliance as specified in Section 01756 - Commissioning.
15115-001.0 | 15115 | GATE, GLOBE, AND ANGLE VALVES | KNIFE GATE VALVE | Mechanical | 1.0-B | Product data: As specified in Section 15110 - Common Work Results for Valves. | 2025-08-25 | 2025-09-17 | 2025-09-08 | NR
15115-002.0 | 15115 | GATE, GLOBE, AND ANGLE VALVES | GATE VALVE GV00 | Uriah/Civil | 2.0-B | Product data: As specified in Section 15110 - Common Work Results for Valves. | 2025-09-17 |  |  | submitted
| 15115 | GATE, GLOBE, AND ANGLE VALVES |  |  | 1.03-C | For valves specified to have electric actuators, provide letters from both the valve manufacturer and the electric actuator manufacturer confirming that they have coordinated the electric actuator selection with the specified valve design requirements.
| 15115 | GATE, GLOBE, AND ANGLE VALVES |  |  | 1.03-D-1 | Commissioning submittals: For valves larger than 16 inches: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15116 | PLUG VALVES |  | Mechanical | 1.03-B | For valves specified to have electric actuators, provide letters from both the valve manufacturer and the electric actuator manufacturer confirming that they have coordinated the electric actuator selection with the specified valve design requirements, including operating speed.
15116-001.0 | 15116 | PLUG VALVES | Dezurick Product Data |  | 1.03-C | Product data as defined in 01600 - Product Requirements. | 2025-09-02 | 2025-09-22 | 2025-10-22 | NCR
| 15116 | PLUG VALVES |  |  | 1.03-D | Shop drawings showing installation arrangement of major component assemblies.
| 15116 | PLUG VALVES |  |  | 1.03-E | Calculations.
15116-001.0 | 15116 | PLUG VALVES | Dezurick Product Data |  | 1.03-F | Vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. | 2025-09-02 | 2025-09-22 | 2025-10-22 | NCR
| 15116 | PLUG VALVES |  |  | 1.03-G-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 15116 | PLUG VALVES |  |  | 1.03-G-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 15117 | SPECIALTY VALVES |  |  | 1.03-B | Product data: As specified in Section 15110 - Common Work Results for Valves.
[5 empty] | 1.03-C-1 | Commissioning submittals: Backflow preventer certification.
[5 empty] | 1.03-C-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15118 | PRESSURE CONTROL VALVES |  |  | 1.02-B | Product data: As specified in Section 15110 - Common Work Results for Valves.
[5 empty] | 1.02-C-1 | Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15119 | AIR AND VACUUM RELIEF VALVES |  |  | 1.03-B | Product data: As specified in Section 15110 - Common Work Results for Valves.
[5 empty] | 1.03-C-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15120 | PIPING SPECIALTIES |  |  | 1.03-B | Product data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.03-C | Calculations.
[5 empty] | 1.03-D | Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15121 | PIPE COUPLINGS |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C-1 | Calculations: Provide calculations in accordance with NSF 372 for materials in contact with drinking water.
[5 empty] | 1.03-D | Piping layout drawings: Coordinate preparation of required piping layout drawings such that coupling center sleeve sizes are clearly indicated on the Drawings.
| 15122 | FIRE HYDRANTS |  | QC | N/A
| 15125 | STRAINERS |  |  | 1.03-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
15211-001.0 | 15211 | DUCTILE IRON PIPE: AWWA C151 | Ductile Iron Pipe: AWWA C151 | Nishant/QC | 1.03-B | Product data: As specified in Section 15052 - Common Work Results for General Piping. | 2025-08-05 | 2025-09-23 | 2025-10-23 | NCR
[5 empty] | 1.03-C | Manufacturer's qualifications.
[5 empty] | 1.03-D | Manufacturer's Quality Assurance Manual.
[5 empty] | 1.03-E | Shop drawings.
[5 empty] | 1.03-F | Provide manufacturer’s test reports.
15230-001.0 | 15230 | PLASTIC PIPING AND TUBING | Product submittal:C900 PVC | Mechanical | 1.04-B 1.04-C 2.03.A | Product data: As specified in Section 15052 - Common Work Results for General Piping. Shop Drawings | 2025-05-28 | 2025-09-03 | 2025-10-03 | REV
15230-001.1 | 15230 | PLASTIC PIPING AND TUBING | Product submittal:C900 PVC | Mechanical | 1.04-B 1.04-C 2.03.A | Product data: As specified in Section 15052 - Common Work Results for General Piping. Shop Drawings | 2025-09-12 |  |  | Submitted
15230-002.0 | 15230 | PLASTIC PIPING AND TUBING | Product submittal: SCH80 PVC & CPVC | Mechanical | 2.02-A.1 & 2 | Product data:Materials and Fittings Only! | 2025-05-30 | 2025-09-03 | 2025-10-03 | REV
15230-002.1 | 15230 | PLASTIC PIPING AND TUBING | Product submittal: SCH80 PVC & CPVC | Mechanical | 2.02-A.1 & 2 | Product data:Materials and Fittings Only! | 2025-09-11 |  |  | Submitted
| 15230 |  |  |  | 1.04-C | Shop Drawings.
15230-003.0 | 15230 | PLASTIC PIPING AND TUBING | Product Data: Solvent Cement and Primer | Nishant | 2.03 A. 3 | Product Data for Solvent Cement and Primer | 2025-07-30 |  |  | Submitted
15230-004.0 | 15230 | PLASTIC PIPING AND TUBING | Variance: HDPE Product Data | Brandon | 2.03 A. 3 | Variance to use HDPE pipe in lieu of PVC | 2025-08-20 | 2025-08-25 | 2025-09-24 | NCR
| 15234(ADD6) | POLYETHYLENE (PE) PIPE: ASTM D2513 |  |  | 1.04-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D | Calculations.
| 15241 | HIGH DENSITY POLYETHYLENE (HDPE) PIPE: AWWA C906 |  |  | 1.04-B | Shop drawings.
15241-001.0 | 15241 | HIGH DENSITY POLYETHYLENE (HDPE) PIPE: AWWA C906 | Submittals: HDPE Pipe & Fittings, Qualifications of installation crew for HDPE | Mechanical | 1.04-C | Product data: As specified in Section 15052 - Common Work Results for General Piping. | 2025-06-09 | 2025-06-10 |  | REV
15241-001.0 | 15241 | HIGH DENSITY POLYETHYLENE (HDPE) PIPE: AWWA C906 |  |  | 1.04-D | Qualifications of installation crew for high-density polyethylene pipe including qualifications of the fusion machine technician. Furnish proof of training in the use of fusion equipment. | 2025-06-09 | 2025-06-10 |  | REV
15241-001.1 | 15241 | HIGH DENSITY POLYETHYLENE (HDPE) PIPE: AWWA C906 | HDPE for Emergency Bypass Only | Mechanical |  | Resubmital, no shop drawings | 2025-08-22 |  |  | AC
| 15254 | CAST IRON SOIL PIPE: ASTM A74 |  |  | 1.03-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
| 15270 | STEEL PIPE: GALVANIZED AND BLACK, ASTM A53 |  |  | 1.03-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
[5 empty] | 1.03-C | Manufacturer's qualifications.
[5 empty] | 1.03-D | Manufacturer's Quality Assurance Manual.
| 15272 | STEEL PIPE |  |  | 1.04-B | Submit installation schedule, line-lay drawings, method of handling pipe and method of coating and welding repairs.
[5 empty] | 1.04-C | Wall thickness design calculations sealed by a Licensed Professional Engineer.
[5 empty] | 1.04-D | Thrust restraint calculations for all fittings and valves including the restraint length, single, and double weld lengths to be sealed by a Licensed Professional Engineer.
[5 empty] | 1.04-E | Fabrication and Lay drawings showing a schematic location with profile and tabulated layout schedule that is sealed by a Licensed Professional Engineer
[5 empty] | 1.04-F | Certificates of Compliance.
[5 empty] | 1.04-G | Certified Test Reports.
| 15281 | COPPER WATER TUBE: SEAMLESS, ASTM B88 |  |  | 1.03-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
| 15286 | STAINLESS STEEL PIPE AND TUBING |  |  | 1.04-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Field welding references: Welder and weld operator qualification certificates and welding procedures.
| 15293 | DOUBLE CONTAINMENT PIPING |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Manufacturer’s published installation instructions.
[5 empty] | 1.03-C | Expansion joint design information.
| 15400 | PLUMBING SYSTEMS |  |  | 1.05-B | Product data: As specified in Section 15052 - Common Work Results for General Piping.
| 15430 | EMERGENCY EYE/FACE WASH AND SHOWER EQUIPMENT |  |  | 1.04-A | Submit as specified in Section 01330 - Submittal Procedures and Section 01600 - Product Requirements.
| 15500 | COMMON WORK RESULTS FOR HVAC |  |  | 1.04-A | Where items in this Section are components of equipment or systems specified in other sections, include data for this Section’s components with the equipment or system submittal.
[5 empty] | 1.04-B-2 | When products are specified in this Section but are not referenced in other Technical Sections: Product data.
[5 empty] | 1.04-B-3 | When products are specified in this Section but are not referenced in other Technical Sections: Description of coating system and instructions for field touch up and re-coating.
| 15521 | HOT WATER SYSTEM COMPONENTS |  |  | 1.03-A | Shop drawings.
[5 empty] | 1.03-B-1 | Quality control submittals: Factory functional test report.
[5 empty] | 1.03-B-2 | Quality control submittals: Field performance test report.
[5 empty] | 1.03-B-3 | Quality control submittals: Certificate of Compliance with ASME Code Section VIII, Division 1, as applicable.
[5 empty] | 1.03-B-4 | Quality control submittals: Certificates of Installation as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-C | Certificates as specified in Sections 01756 - Commissioning, 15050 - Common Work Results for Mechanical Equipment, and 15958 - Mechanical Equipment Testing.
[5 empty] | 1.03-D | Warranties.
| 15552 | HOT WATER BOILER |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Provide detailed drawings of the fuel train and individual components.
[5 empty] | 1.03-E | Provide detailed product data and dimensioned drawings of the burner and associated components.
[5 empty] | 1.03-F | Provide manufacturer published data or cutsheets with product descriptions for all accessories including fuel train components, valves, burner, controller, sensors, switches, transmitters, gauges, and other equipment provided as part of the complete boiler package.
[5 empty] | 1.03-G | Provide technical data sheets for coatings system, including coating type for primer and topcoat, paint manufacturer’s recommended thickness, application process, and other information to confirm coatings are appropriate for the conditions specified in paragraph 2.08.
[5 empty] | 1.03-H | Include diagrams for power, signal, and control wiring including a schematic wiring diagram of boiler control system showing all components, interlocks, and clearly identify factory wiring and field wiring by others.
[5 empty] | 1.03-I | Provide manufacturer’s test reports, including combustion test report, and other reports as required by the manufacturer.
[5 empty] | 1.03-J | Calculations: As specified in Section 15050 - Common Work Results for Mechanical Equipment
[5 empty] | 1.03-K | Field emissions testing report.
[5 empty] | 1.03-L | Quality control submittals.
[5 empty] | 1.03-M | Maintenance Service Agreement (MSA): Provide MSA including maintenance service requirements per paragraph 3.02-F.
[5 empty] | 1.03-N-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-N-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-O-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.03-O-2 | Project closeout documents: ASME stamp Certification and Report. Submit a copy of the inspection report and documentation of hydrostatic testing.
[5 empty] | 1.03-O-3 | Project closeout documents: Manufacturer’s data reports.
[5 empty] | 1.03-O-4 | Project closeout documents: Startup reports proving satisfactory performance.
| 15732 | AIR CONDITIONING UNITS |  |  | 1.07-B | Catalog cuts, bulletins, and brochures.
[5 empty] | 1.07-C | Drawings.
[5 empty] | 1.07-D | Delegated Design submittals: Anchoring and bracing: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria
[5 empty] | 1.07-E-1 | Engineering data: Manufacturer's published data for compressor, evaporator coil, condenser, evaporator fan, refrigerant, filter, etc. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.07-E-2 | Engineering data: Maximum equipment vibration levels and field-testing method.
[5 empty] | 1.07-E-3 | Engineering data: Sound power level in each of 8 octave bands and overall Sones.
[5 empty] | 1.07-E-4 | Engineering data: Fan performance curves showing specified operating condition.
[5 empty] | 1.07-E-5 | Engineering data: Bearing life.
[5 empty] | 1.07-F | Manufacturer's recommendations for handling, storage, and installation.
[5 empty] | 1.07-G | Nameplate data.
[5 empty] | 1.07-H | Vendor operation and maintenance manuals: Manufacturer's standard instruction manual for operation and maintenance.
| 15740 | HEAT PUMPS |  |  | 1.04-B | Product data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D | Calculations.
[5 empty] | 1.04-E | Quality control submittals.
[5 empty] | 1.04-F-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-F-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-G-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.04-H | Warranties.
| 15812 | METAL DUCTS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Design data: Seismic design calculations.
15814-001.0 | 15814 | FIBERGLASS REINFORCED PLASTIC DUCTS | same as spec |  | 1.03-B | Shop drawings. | 2025-08-11 |  |  | AS
15814-001.0 | 15814 | FIBERGLASS REINFORCED PLASTIC DUCTS | same as spec |  | 1.03-C | Calculations. | 2025-08-11 |  |  | AS
x | 15814 | FIBERGLASS REINFORCED PLASTIC DUCTS |  |  | 1.03-D | Direct burial procedure and details.
15814-001.0 | 15814 | FIBERGLASS REINFORCED PLASTIC DUCTS | same as spec |  | 1.03-E | Manufacturer's installation instructions. | 2025-08-11 |  |  | AS
15814-001.0 | 15814 | FIBERGLASS REINFORCED PLASTIC DUCTS | same as spec |  | 1.03-F | Submit test results as specified in Section 06608 - Fiberglass Reinforced Plastic verifying that ductwork meets standards specified. | 2025-08-11 |  |  | AS
15830-001.0 | 15830 | FANS | same as spec | Jyun | 1.05-A | Submit as specified in the General Requirements and Section 15050 - Common Work Results for Mechanical Equipment. | 2025-06-19 | 2025-08-25 | 2025-09-24 | NCR
15830-001.0 | 15830 | FANS | same as spec | Jyun | 1.05-B | Product data. | 2025-06-19 | 2025-08-25 | 2025-09-24 | NCR
15830-001.0 | 15830 | FANS | same as spec | Jyun | 1.05-C | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. | 2025-06-19 | 2025-08-25 | 2025-09-24 | NCR
| 15830 | FANS |  |  | 1.05-D | Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
15832-001.0 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-A | Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment and specified herein. | 2025-06-19 | 2025-08-18 | 2025-09-02 | REV
15832-001.0 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-B | Product data. | 2025-06-19 | 2025-08-18 | 2025-09-02 | REV
15832-001.0 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-C | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. | 2025-06-19 | 2025-08-18 | 2025-09-02 | REV
15832-001.0 | 15832 | ODOR CONTROL FANS | same as spec | Marshall | 1.04-D | Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning. | 2025-06-19 | 2025-08-18 | 2025-09-02 | REV
15832-001.1 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-A | Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment and specified herein. | 2025-08-25 |  |  | Submitted
15832-001.1 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-B | Product data. | 2025-08-25 |  |  | Submitted
15832-001.1 | 15832 | ODOR CONTROL FANS | same as spec | Jyun | 1.04-C | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. | 2025-08-25 |  |  | Submitted
15832-001.1 | 15832 | ODOR CONTROL FANS | same as spec | Marshall | 1.04-D | Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning. | 2025-08-25 |  |  | Submitted
| 15838 | GRAVITY VENTILATORS |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Drawings.
[5 empty] | 1.03-D | Manufacturer's recommendations for handling, storage, and installation.
[5 empty] | 1.03-E | Vendor operation and maintenance manuals: Manufacturer's standard instruction manual for operation and maintenance.
[5 empty] | 1.03-F | Provide manufacturers reports on factory testing.
[5 empty] | 1.03-G | High wind certification.
| 15852 | LOUVERS |  |  | 1.04-A | Shop drawings: Include dimensions, anchorage details, and relationships to adjacent materials.
[5 empty] | 1.04-B | Product data.
| 15936 | INSTRUMENTATION AND CONTROL DEVICES FOR HVAC |  |  | 1.03-B | Product data: As specified in Section 15500 - Common Work Results for HVAC.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.03-E | Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 15954 | TESTING, ADJUSTING, AND BALANCING FOR HVAC |  |  | 1.03-A | Resumes of proposed supervisor and personnel showing training and qualifications.
[5 empty] | 1.03-B | Testing plan.
[5 empty] | 1.03-C | Report.
| 15956 | PIPING SYSTEMS TESTING |  |  | 1.04-B | Schedule and notification of tests.
| 15958 | MECHANICAL EQUIPMENT TESTING |  |  | 1.03-A | Provide Source Test Plans as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-B | Provide Installation and Functional Testing Plans as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-C | Schedule of source (factory) tests, Owner staff training, installation testing, pretest checks, clean water facility testing, functional testing, performance testing, start-up testing, and closeout documentation, as specified in this Section and in Section 01756 - Commissioning.
[5 empty] | 1.03-D | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.03-E | Test instrumentation calibration data.
[5 empty] | 1.03-F | Test reports as specified in this Section and in Section 01756 - Commissioning and equipment sections.
15958-002.0 | 15958 | MECHANICAL EQUIPMENT TESTING | PDM Specialist Qualifications | MC | 3.07 | Qualifcations and Equipment Variance Request | 2025-09-12 | 2025-09-25 |  | REV
15958-002.1 | 15958 | MECHANICAL EQUIPMENT TESTING | PDM Specialist Qualifications | MC | 3.07 | Qualifcations and Equipment Variance Request | 2025-09-25 |  |  | in progress
Formulas:
NLT Date (14 days) = [Return Date]+30
NLT Date (14 days) = 30+[Return Date]

## Equipment
note: submittal status code: AN - Approved no comments, AC - Approved with comments resumittal not required, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 11215 | HIGH-PRESSURE WASHERS |  |  | 1.03-B | Shop drawings and product data.
[5 empty] | 1.03-C | Manufacturer’s installation instructions.
[5 empty] | 1.03-D | Operations and Maintenance Manual.
11245-001.0 | 11245 | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS | Blue - White | QC/Marshall | 1.03-B-1 | Product data: Current NSF 61 Certification for components to be in contact with associated chemical or potable water. | 2025-09-02 |  |  | Submitted
11245-001.0 | 11245 | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS | Blue - White | QC/Marshall | 1.03-B-2 | Product data: Provide data showing chemical compatibility and history of service with the associated chemical for materials in the system. | 2025-09-02 |  |  | Submitted
11245-001.0 | 11245 | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS | Blue - White | QC/Marshall | 1.03-C | Shop Drawings. | 2025-09-02 |  |  | Submitted
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  |  | 1.03-D-1 | Calculations: For each pump type, submit calibration charts and tables relating flow rate to speed.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  |  | 1.03-D-2 | Calculations: Submit calculations for each metering pump showing the suitability of each pump for the suction and discharge conditions of each application point.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  |  | 1.03-D-3 | Calculations: Calibration curves for each pump relating speed to flow rate.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  |  | 1.03-E | Vendor operation and maintenance manuals: As specified in Section 01782 -Operation and Maintenance Manuals.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-b | Commissioning Submittals: Certificates.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-c | Commissioning Submittals: Test Plans.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-d | Commissioning Submittals: Test Reports.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
|  | LIQUID CHEMICAL PERISTALTIC TUBE METERING PUMPS |  | QC/Mech | 1.03-F-1-f | Commissioning Submittals: Owner training.
| 11246 | POLYMER BLENDING AND FEED EQUIPMENT: LIQUID |  |  | 1.03-B-1 | Product data: Detailed specifications and shop drawings with both isometric and orthogonal views of the proposed installation.
[5 empty] | 1.03-B-2 | Product data: Hydraulic characteristics of the mixer.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Calculations: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
[5 empty] | 1.03-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
|  |  |  | QC/Mech | 1.03-F-1 | Commissioning submittals: Provide Manufacturer's Certificate of Source Testing as specified in Section 01756 - Commissioning.
|  |  |  | QC/Mech | 1.03-F-1 | Commissioning submittals: Provide Manufacturer's Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-B | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment. | 2025-06-19 |  |  | Submitted
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-C | Shop drawings. | 2025-06-19 |  |  | Submitted
| 11294B |  |  |  | 1.06-D | Installation List.
| 11294B |  |  |  | 1.06-E-1 | Gate operators: Provide certification from both the operator manufacturer and the gate manufacturer confirming that the proposed gate stem configuration has been coordinated with motorized operator selection.
| 11294B |  |  |  | 1.06-E-2 | Gate operators: For coordination purposes, gate manufacturer shall submit calculations verifying the suitability of the selected operator for the application.
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-F | Design Calculations: As specified in Section 15050 - Common Work Results for Mechanical Equipment: | 2025-06-19 |  |  | Submitted
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-G | Complete bill of materials. | 2025-06-19 |  |  | Submitted
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-H | Wall thimbles design. | 2025-06-19 |  |  | Submitted
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-I | Manufacturer's installation instructions. | 2025-06-19 |  |  | Submitted
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-J | Vendor operation and maintenance manuals as specified in Section 01782 - Operation and Maintenance Manuals. | 2025-06-19 |  |  | Submitted
| 11294B |  |  | TC | 1.06-K-1 | Commissioning submittals: Provide Manufacturer's Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 11294B |  |  | TC | 1.06-K-2 | Commissioning submittals: Detailed Performance Test Procedures: Factory and field testing.
11294B-001.0 | 11294B | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.06-L | Detailed performance test procedures for factory and field-testing. | 2025-06-19 |  |  | Submitted
| 11294B |  |  |  | 1.06-M | Certificate of Installation and Functionality Compliance.
| 11294B |  |  |  | 1.06-N | Testing results reports and certifications.
11312C-001.0 | 11312C | HORIZONTAL RECESS IMPELLER CENTRIFUGAL PUMPS |  | QCMarshall | 1.05-B | Torsional analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled. | 2025-09-02 |  |  | Submitted
11312C-001.0 |  |  |  | QCMarshall | 1.05-C | Furnish motor submittals as specified in Section 16222 - Low Voltage Motors up to 500 Horsepower. | 2025-09-02 |  |  | Submitted
11312C-001.0 |  |  |  | QCMarshall | 1.05-D | Manufacturer’s Representatives qualifications as specified in Section 01756 - Commissioning. | 2025-09-02 |  |  | Submitted
11312C-001.0 |  |  |  | QCMarshall | 1.05-E | Manufacturer’s installation instructions. | 2025-09-02 |  |  | Submitted
[5 empty] | 1.05-F | Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.05-G | Test results. Verify conformance with noise requirements.
11312C-001.0 |  |  |  | QCMarshall | 1.05-H | Detailed dimensional drawings of pump skid and equipment pad, and any proposed modifications to reduce the footprint for improved clearances in the grit pump room. | 2025-09-02 |  |  | Submitted
| 11312D(ADD4) | VERTICAL TURBINE SHORT SETTING CENTRIFUGAL PUMPS |  |  | 1.05-B-1 | Product Submittals: As specified in Section 01600 - Product Requirements.
[5 empty] | 1.05-B-2 | Product Submittals: Product data.
[5 empty] | 1.05-B-3 | Product Submittals: Shop Drawings.
[5 empty] | 1.05-B-4 | Product Submittals: Calculations.
[5 empty] | 1.05-C-1 | Delegated Design: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.05-D-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.05-D-1-b | Commissioning Submittals: Certificates.
[5 empty] | 1.05-D-1-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.05-D-1-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.05-D-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.05-D-1-f | Commissioning Submittals: Owner Training.
[5 empty] | 1.05-E | Operation and maintenance manuals.
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-B | Vibration analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
11312E-001.0 | 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  | MC | 1.04-C | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment. |  |  |  | in progress
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-D | Shop drawings.
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-E-1 | Calculations: Torsional analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-F | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-G-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 11312E | HORIZONTAL SCREW CENTRIFUGAL PUMPS |  |  | 1.04-G-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 11312I | PROGRESSING CAVITY PUMPS |  |  | 1.04-B | Vibration analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
11312I-001.0 | 11312I | PROGRESSING CAVITY PUMPS | Product Data: Netzsch Sludge Pumps | MC | 1.04-C-1 | Product data: Submit seal water pressure and flow requirements.
11312I-001.0 | 11312I | PROGRESSING CAVITY PUMPS | Product Data: Netzsch Sludge Pumps | MC | 1.04-D | Shop drawings.
| 11312I | PROGRESSING CAVITY PUMPS |  |  | 1.04-E-1 | Calculations: Torsional analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
| 11312I | PROGRESSING CAVITY PUMPS |  |  | 1.04-F | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
| 11312I | PROGRESSING CAVITY PUMPS |  |  | 1.04-G-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 11312I | PROGRESSING CAVITY PUMPS |  |  | 1.04-G-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
11312J-001.0 | 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  | Marshall | 1.04-B | Vibration analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled. | 2025-08-25 |  |  | Submitted
| 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  |  | 1.04-C | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
| 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  |  | 1.04-D | Shop drawings.
| 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  |  | 1.04-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
| 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  |  | 1.04-F-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 11312J | SUBMERSIBLE PROCESS LIQUID SUMP PUMPS |  |  | 1.04-F-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
11312K-001.0 | 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  | QC/Marshall | 1.04-B | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment. | 2025-09-02 |  |  | Submitted
11312K-001.0 | 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  | QC/Marshall | 1.04-C | Shop drawings. | 2025-09-02 |  |  | Submitted
| 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  |  | 1.04-D | Calculations: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
| 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  |  | 1.04-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
| 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  |  | 1.04-F-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 11312K | SUBMERSIBLE MEDIUM CAPACITY CENTRIFUGAL PUMPS |  |  | 1.04-F-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 11312O | HORIZONTAL ANSI CENTRIFUGAL PUMPS |  |  | 1.04-B | Vibration analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
[5 empty] | 1.04-C-1 | Product data: Pump certification as specified in Section 01600 - Product Requirements.
[5 empty] | 1.04-C-2 | Product data: Weighted average lead calculations Section 01600 - Product Requirements.
[5 empty] | 1.04-D | Shop drawings.
[5 empty] | 1.04-E-1 | Calculations: Torsional analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled.
[5 empty] | 1.04-F | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.04-G-1 | Commissioning submittals: Provide Manufacturer's Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-G-2 | Commissioning submittals: Provide Manufacturer's Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-B | Vibration analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-C | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-D | Shop drawings. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-E-1 | Calculations: Torsional analysis: Submit as specified in Section 15050 - Common Work Results for Mechanical Equipment when scheduled. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-F | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-G-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning. | 2025-09-04 |  |  | Submitted
11312R-001.0 | 11312R | SINGLE-LOBE ROTARY PUMPS | HES |  | 1.04-G-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning. | 2025-09-04 |  |  | Submitted
| 11313F | SUBMERSIBLE CHOPPER CENTRIFUGAL PUMPS |  |  | 1.05-B-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.05-C-1-a | Manufacturer’s representative qualifications.
[5 empty] | 1.05-C-1-b | Certificates.
11313F-001.0 |  | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.05-C-1-c | Test Plans. | 2025-06-16 |  |  | Submitted
[5 empty] | 1.05-C-1-d | Test Reports.
[5 empty] | 1.05-C-1-e | Manufacturer’s representatives field notes and data.
[5 empty] | 1.05-C-1-f | Owner training.
11313F-001.0 |  | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.05-D-1-a-1 | Product data: Certification of Rockwell C Hardness for cutter bars and impeller. | 2025-06-16 |  |  | Submitted
11313F-001.0 |  | HEAVY-DUTY FABRICATED STAINLESS STEEL SLIDE GATES |  | Jyun | 1.05-D-2 | Shop drawings. | 2025-06-16 |  |  | Submitted
[5 empty] | 1.05-D-3-a | Calculations: Torsional analysis.
[5 empty] | 1.05-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
11320-001.0 | 11320 | PACKAGED SEWER LIFT STATION |  | QC/Marshall | 1.04-B | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment. | 2025-08-28 |  |  | Submitted
11320-001.0 | 11320 | PACKAGED SEWER LIFT STATION |  | QC/Marshall | 1.04-C | Shop drawings. | 2025-08-28 |  |  | Submitted
| 11320 | PACKAGED SEWER LIFT STATION |  |  | 1.04-D | Calculations: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
11320-001.0 | 11320 | PACKAGED SEWER LIFT STATION |  | QC/Marshall | 1.04-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals. | 2025-08-28 |  |  | Submitted
| 11320 | PACKAGED SEWER LIFT STATION |  | QC | 1.04-F-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 11320 | PACKAGED SEWER LIFT STATION |  | QC | 1.04-F-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 01783/11320 | WARRANTIES AND BONDS |  |  | 1.02-A-1 | Submit manufacturer's warranty prior to fabrication and shipment of the item from the manufacturer's facility.
[5 empty] | 1.02-A-2 | Submit manufacturer's special warranty when specified.
[5 empty] | 1.02-B | Provide consolidated warranties and bonds within 15 calendar days of Substantial Completion.
11322D-001.0 | 11322D | VORTEX GRIT BASIN EQUIPMENT |  | Marshall | 1.04-C-1 | Product Data: Motor characteristics and performance. | 2025-08-25 |  | 2025-09-08 | Submitted
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-C-2 | Product Data: Accessories.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-D | Shop Drawings.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-E | Operation and Maintenance Manuals as specified in Section 01782 - Operation and Maintenance Manuals: Include shop manuals.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-F | Manufacturer’s performance guarantee.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-G | Manufacturer's installation instructions.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-H | Equipment Manufacturer certification of bearing life.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-I | Motor shop test results.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-J | Recommendations for short and long-term storage.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-K | Certified Data and Capability.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-L | Shop and field testing procedures and equipment.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-M | Removal efficiency testing procedures.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-N | Removal efficiency testing data and results.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-O | Training lesson plan.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-P | Nomenclature labels for equipment.
| 11322D | VORTEX GRIT BASIN EQUIPMENT |  |  | 1.04-Q | Warranties.
| 11324 | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-B-1 | Installation lists.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-B-2 | Test reports by independent party for a minimum of 5 installations must be provided proving that the organic content of the washed grit product at these tested installations has been below 5 percent.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-C | Shop drawings.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-D | Manufacturer’s performance guarantee. |  |  |  |  | This is space is intentionnaly left blank for scrolling
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-E | Manufacturer’s installation instructions.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-F-1 | Calculations: Structural calculations and details prepared by a Professional Engineer registered in the state where the Project is located
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-F-2 | Calculations: Non-proprietary mechanical calculations and details prepared by a registered Professional Engineer.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-G | Test reports.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-H | Certificates.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-I | Manufacturer’s field reports, including performance test results and analysis.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-J | Operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-K | Warranties. |  |  |  |  | This is space is intentionnaly left blank for scrolling
|  | GRIT WASHING AND DEWATERING EQUIPMENT |  |  | 1.04-L | Technician Qualifications Resume: Resume of technician to perform adjustments, inspections, start-up, observations of test operations, and training.
| 11332A | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-B | Installation List.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-C | Shop drawings.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-D | Calculations: Detailed calculations and design data verifying conformance with the Drawings and Specifications.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-E | Complete Bill of Materials.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-F-1 | Quality Control Submittals: Detailed performance test procedures: Factory and field testing.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-F-2 | Quality Control Submittals: Factory Testing:
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-F-3 | Quality Control Submittals: Certificate of proper installation.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-G | Technician Qualifications Resume: Submit resume of technician to perform manufacturer’s field services.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-H | Submit location of the nearest permanent service headquarters of the screen and motor manufacturer for the screen and motor submitted.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-I | Submit operating instructions with descriptive literature.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-J | A copy of documents proving certification of the Manufacturer’s Quality Management System according to ISO 9001.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-1 | Instrumentation and control: P&IDs for the Screens.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-2-a | Instrumentation and control: Hardware submittal: Bill of Materials.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-2-b | Instrumentation and control: Hardware submittal: ISA data sheets for instruments provided.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-2-c | Instrumentation and control: Hardware submittal: Catalog cut sheets for process control and instrumentation equipment.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-2-d | Instrumentation and control: Hardware submittal: Instrument installation, mounting, and anchoring details.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-3 | Instrumentation and control: Network Architecture Diagram.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-5 | Instrumentation and control: List of spare parts to be provided by Vendor.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-6 | Instrumentation and control: Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-7 | Instrumentation and control: Detailed loop drawings in accordance with ISA S5.4.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-8 | Instrumentation and control: Point-to-point interconnection wiring diagrams.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-9 | Instrumentation and control: Panel wiring, conduit diagrams, and I/O module layout.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-10 | Instrumentation and control: English-language loop descriptions.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-11 | Instrumentation and control: Instrument index with ranges and setpoints.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-12 | Instrumentation and control: Electronic copy on a CD-ROM of the LOI program.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-13 | Instrumentation and control: Electronic copy on a CD-ROM of the VCP PLC system program.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-K-14 | Instrumentation and control: Detailed factory testing procedure.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-1 | Proposed layout of mounted devices and terminals with dimensions within VCP.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-2 | Proposed VCP PLC programming printout with input/output (I/O) listing if available using ladder logic format.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-3 | Complete I/O list.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-4 | Proposed VCP LOI graphic display printouts.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-5 | Operating description for VCP.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-6-a | PLC cabinet: Panel exterior and internal elevations with detailed bill of materials.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-6-b | PLC cabinet: PLC power schematic and I/O shop drawings.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-6-c | PLC cabinet: Product data for panel and all components.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-6-d | PLC cabinet: PLC memory and spare I/O calculations.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-6-e | PLC cabinet: Thermal management calculations.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-7 | Visual print out of all LOI screens.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-8 | I/O listing and network mapping of tagged I/O.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-L-9 | VCP schematic drawings including interface with local control panel provided by others.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-M | Operation and Maintenance Manuals.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-N | List of Spare Parts and Special Tools.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-O | List of recommended Spare Parts.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-P | Manufacturer's Installation Instructions.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-Q | Warranties.
|  | CHAIN DRIVEN MULTI-RAKE BAR SCREENS |  |  | 1.04-R | Training course outlines.
| 11333A | SCREENINGS WASHER COMPACTOR |  |  | 1.04-B | Installation Reference List.
[5 empty] | 1.04-E | Shop Drawings.
[5 empty] | 1.04-F-1 | Control and instrumentation: P&IDs for the screenings compactor Units.
[5 empty] | 1.04-F-2-a | Control and instrumentation: Hardware submittal: Bill of Materials.
[5 empty] | 1.04-F-2-b | Control and instrumentation: Hardware submittal: ISA data sheets for instruments provided.
[5 empty] | 1.04-F-2-c | Control and instrumentation: Hardware submittal: Catalog cuts for process control and instrumentation equipment.
[5 empty] | 1.04-F-2-d | Control and instrumentation: Hardware submittal: Instrument installation, mounting, and anchoring details.
[5 empty] | 1.04-F-3 | Control and instrumentation: Network Architecture Diagram.
[5 empty] | 1.04-F-5 | Control and instrumentation: List of spare parts to be provided by Vendor.
[5 empty] | 1.04-F-6 | Control and instrumentation: Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-F-7 | Control and instrumentation: Detailed loop drawings in accordance with ISA S5.4.
[5 empty] | 1.04-F-8 | Control and instrumentation: Point-to-point interconnection wiring diagrams indicating field instrumentation and control panel connections.
[5 empty] | 1.04-F-9 | Control and instrumentation: Panel wiring, conduit diagrams, and I/O module layout.
[5 empty] | 1.04-F-10 | Control and instrumentation: English-language loop descriptions.
[5 empty] | 1.04-F-11 | Control and instrumentation: Instrument index with ranges and setpoints.
[5 empty] | 1.04-F-12 | Control and instrumentation: Electronic copy on a CD-ROM of the LOI program.
[5 empty] | 1.04-F-13 | Control and instrumentation: Electronic copy on a CD-ROM of the VCP PLC system program.
[5 empty] | 1.04-F-14 | Control and instrumentation: Detailed factory testing procedure.
[5 empty] | 1.04-G-1 | Vendor Control Panels (VCPs): Proposed layout of mounted devices and terminals with dimensions within VCP.
[5 empty] | 1.04-G-2 | Vendor Control Panels (VCPs): Proposed VCP PLC programming printout with input/output (I/O) listing if available using ladder logic format.
[5 empty] | 1.04-G-3 | Vendor Control Panels (VCPs): Complete I/O list.
[5 empty] | 1.04-G-4 | Vendor Control Panels (VCPs): Proposed VCP LOI graphic display printouts.
[5 empty] | 1.04-G-5 | Vendor Control Panels (VCPs): Operating description for VCP.
[5 empty] | 1.04-G-6-a | Vendor Control Panels (VCPs): PLC cabinet: Panel exterior and internal elevations with detailed bill of materials.
[5 empty] | 1.04-G-6-b | Vendor Control Panels (VCPs): PLC cabinet: PLC power schematic and I/O shop drawings. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-G-6-c | Vendor Control Panels (VCPs): PLC cabinet: Product data for panel and all components.
[5 empty] | 1.04-G-6-d | Vendor Control Panels (VCPs): PLC cabinet: PLC memory and spare I/O calculations.
[5 empty] | 1.04-G-6-e | Vendor Control Panels (VCPs): PLC cabinet: Thermal management calculations.
[5 empty] | 1.04-G-7 | Vendor Control Panels (VCPs): Visual print out of all LOI screens.
[5 empty] | 1.04-G-8 | Vendor Control Panels (VCPs): I/O listing and network mapping of tagged I/O.
[5 empty] | 1.04-G-9 | Vendor Control Panels (VCPs): VCP schematic drawings including interface with local control panel provided by others.
[5 empty] | 1.04-I | Calculations: Detailed calculations and design data verifying conformance with the Drawings and Specifications
[5 empty] | 1.04-J-1 | Quality Control Submittals: Detailed Performance Test Procedures: Factory and Field testing. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-J-2 | Quality Control Submittals: Performance Test Data.
[5 empty] | 1.04-J-3-a | Quality Control Submittals: Manufacturer's certification that the equipment was installed in accordance with the manufacturer's instructions, inspected by the manufacturer, serviced with the proper lubricants, and equipped with applicable safety equipment and controls.
[5 empty] | 1.04-J-3-b | Quality Control Submittals: Manufacturer's certification that all welding was performed in accordance with American Welding Society (AWS) D1.1 Structural Welding Code, or equivalent.
[5 empty] | 1.04-J-3-c | Quality Control Submittals: Manufacturer's certification that the stainless steel materials of the equipment were passivated after fabrication by submersion in an acid bath or an acid spray to reestablish the oxidation film and to remove embedded iron, surface rust, and weld burn.
[5 empty] | 1.04-J-3-d | Quality Control Submittals: A copy of documents proving certification of the Manufacturer's Quality Management System and Environmental Program.
[5 empty] | 1.04-K | List of Spare Parts and Special Tools.
[5 empty] | 1.04-L | List of recommended Spare Parts.
[5 empty] | 1.04-M | Manufacturer's Installation Instructions.
[5 empty] | 1.04-N | Submit operating instructions with descriptive literature.
[5 empty] | 1.04-O | Documentation of required maintenance for all equipment including an approved list of lubricants and the required quantities.
[5 empty] | 1.04-P | Operation and Maintenance Manuals.
[5 empty] | 1.04-Q | Technician Qualifications Resume: Submit resume of technician to perform Manufacturer's Field Services.
[5 empty] | 1.04-R | Submit location of the nearest permanent service headquarters of the screen and motor manufacturer for the screen and motor submitted.
[5 empty] | 1.04-S | Warranties.
[5 empty] | 1.04-T | Training course outlines.
11334-001.0 | 11334 | INLINE GRINDER | Franklin Miller | QC/Marshall | 1.03-B | Product data. | 2025-09-02 | 2025-09-23 | 2025-10-23 | NR
11334-001.0 | 11334 | INLINE GRINDER | Franklin Miller | QC/Marshall | 1.03-C | Shop drawings. | 2025-09-02 | 2025-09-23 | 2025-10-23 | NR
[5 empty] | 1.03-D | Calculations.
[5 empty] | 1.03-E-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-E-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-F-1 | Project closeout documents: Final vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
| 11342 | HELICAL SCUM SKIMMING EQUIPMENT |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop Drawings.
[5 empty] | 1.03-D-1 | Calculations: Submit structural and mechanical calculations showing that parts and equipment comply with specified requirements.
[5 empty] | 1.03-E | Manufacturer's Drawings.
[5 empty] | 1.03-F | Provide draft vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.03-G-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.03-G-1-b | Commissioning Submittals: Certificates.
[5 empty] | 1.03-G-1-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.03-G-1-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.03-G-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.03-G-1-f | Commissioning Submittals: Owner training.
[5 empty] | 1.03-H-1 | Project closeout documents: Provide final vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
| 11348(ADD4) | CHEMICAL MIXERS |  |  | 1.05-B | Product data: As specified in Section 15050 - Common Work Results for Mechanical Equipment.
[5 empty] | 1.05-C | Shop drawings.
[5 empty] | 1.05-D | Calculations.
[5 empty] | 1.05-E | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.05-F-1 | Commissioning submittals: Provide Manufacturer's Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-F-2 | Commissioning submittals: Provide Manufacturer's Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 11351 | SLUDGE COLLECTOR FOR RECTANGULAR BASIN: CONVENTIONAL STYLE |  |  | 1.04-B-1 | Delegated Design Submittals: rovide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-C-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-C-1-b | Commissioning Submittals: Certificates.
[5 empty] | 1.04-C-1-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-C-1-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.04-C-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-C-2 | Commissioning Submittals: Owner training.
[5 empty] | 1.04-D | Vendor operation and maintenance manuals: As specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.04-E-1 | Calculations: Flight deflection.
[5 empty] | 1.04-E-2-a | Product data: Flights, sprockets, and chains.
[5 empty] | 1.04-E-3 | Manufacturer's instructions.
[5 empty] | 1.04-E-4 | Shop Drawings.
[5 empty] | 1.04-E-5 | Schedules.
| 11353A | HYDRAULIC SUCTION HEADER CIRCULAR SECONDARY CLARIFIER EQUIPMENT |  |  | 1.05-B-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.05-C-1-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.05-C-1-b | Commissioning Submittals: Certificates.
[5 empty] | 1.05-C-1-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.05-C-1-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.05-C-1-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.05-C-2 | Commissioning Submittals: Owner training.
[5 empty] | 1.05-D-1-a | Calculations: Mechanical Equipment.
[5 empty] | 1.05-D-2 | Product data.
[5 empty] | 1.05-D-3 | Shop Drawings.
[5 empty] | 1.05-E | Submit Manufacturer's or designated contract fabrication facility’s structural steel fabrication qualifications and information.
[5 empty] | 1.05-F | Submit the reference information as a minimum for at least 5 projects of equal or greater size where suction header clarifier mechanisms were provided for secondary municipal wastewater service over the last 5 years.
[5 empty] | 1.05-G | Field test: Submit method of conducting cutout torque test and verification that method of testing will not impose stresses in any member which exceeds maximum allowable stresses specified in this Section.
[5 empty] | 1.05-H | Provide draft vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.05-I-1 | Project closeout documents: Provide final vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 11354 | THICKENERS |  |  | 1.05-B | Shop Drawings.
[5 empty] | 1.05-C-1 | Quality control submittals: Factory functional test report.
[5 empty] | 1.05-C-2 | Quality control submittals: Field performance test report.
[5 empty] | 1.05-C-3 | Quality control submittals: Certified test results for sludge conditioning system.
[5 empty] | 1.05-C-4 | Quality control submittals: Certificate of Installation Compliance.
[5 empty] | 1.05-C-5 | Quality control submittals: Certificate of Functionality Compliance.
[5 empty] | 1.05-C-6 | Quality control submittals: Supplier's installation manuals.
[5 empty] | 1.05-D-2-a | Operation and maintenance manual: Lubrication instructions. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.05-D-2-b | Operation and maintenance manual: Maintenance instructions.
[5 empty] | 1.05-D-2-c | Operation and maintenance manual: Operation instructions.
[5 empty] | 1.05-D-2-d | Operation and maintenance manual: Start-up instructions.
[5 empty] | 1.05-D-2-e | Operation and maintenance manual: Trouble-shooting instructions.
[5 empty] | 1.05-D-2-f | Operation and maintenance manual: Unloading and handling methods.
[5 empty] | 1.05-D-2-g | Operation and maintenance manual: Storage requirements for equipment and all supplied consumables.
[5 empty] | 1.05-E | Supplier's qualifications: Submit all information proving conformance with quality assurance requirements.
[5 empty] | 1.05-F | Warranties.
[5 empty] | 1.05-G-1 | Commissioning submittals: Provide Supplier's Certificate of Source Testing.
[5 empty] | 1.05-G-2 | Commissioning submittals: Provide Supplier's Certificate of Installation and Functionality Compliance.
[5 empty] | 1.05-H | echnician qualifications resume: Submit resume of technician to perform thickener adjustments, inspections, performance testing, and training.
[5 empty] | 1.05-I | Training course outline.
| 11358 | CENTRIFUGE DEWATERING EQUIPMENT |  |  | 1.05-D | Centrifuge Manufacturer Qualifications.
[5 empty] | 1.05-E | Product Data.(ADD7)
[5 empty] | 1.05-F | Shop Drawings.(ADD7)
[5 empty] | 1.05-G | Design Calculations.
[5 empty] | 1.05-H | Test Procedures.
[5 empty] | 1.05-I | Test results.
[5 empty] | 1.05-J-1 | Software: Final electronic PDF reports for PLCs and LOI software shall be submitted after successful installation and testing.
[5 empty] | 1.05-J-2 | Software: Provide electronic data tables or register mapping information to integrate centrifuge system with PCS. This submittal must be finalized 60 days prior to commencement of Field Testing.
[5 empty] | 1.05-J-3 | Software: As specified in Division 17 to be compatible with Rockwell Automation CompactLogix controller.(ADD7)
[5 empty] | 1.05-K | Certificates.
[5 empty] | 1.05-L | Manufacturer's Installation Instructions: Installation and check-out instructions including lubrication and initial start-up procedures.
[5 empty] | 1.05-M | Operation and Maintenance Manuals.
[5 empty] | 1.05-N | Location of nearest Service Center and Service Representative and procedure for responding to warranty and non-warranty requests.
[5 empty] | 1.05-O | Operator Training Lesson Plan.
[5 empty] | 1.05-P | Maintenance Service Agreement (MSA): Provide MSA including maintenance service requirements per paragraph 1.09-E.
11381-001.0 | 11381 | DIGESTER APPURTENANCES |  | QC/Marshall | 1.03-A | Product data. | 2025-09-04 |  |  | submitted
11395D-001.0 | 11395D | HEADWORKS ODOR CONTROL SYSTEM |  |  | 1.04-A | Shop Drawings | 2025-06-17 | 2025-09-03 | 2025-09-18 | AS
| 11395D |  |  |  | 1.04-C-1 | Detailed structural and mechanical layout drawings.
11395D-001.0 | 11395D | HEADWORKS ODOR CONTROL SYSTEM |  |  | 1.04-C-2 | Complete basis of design calculations for the FRP vessels, ladders, and media supports. | 2025-06-17 | 2025-09-03 | 2025-09-18 | AS
| 11395D |  |  |  | 1.04-C-3 | Description of the laminate and the type of reinforcing to be used and a letter from the manufacturer stating the laminate reinforcing material used will provide chemical resistance at least equal to the published chemical resistance for the resin for the intended application, and the resin will meet the performance requirements stated and is suitable for the service conditions specified herein and the fabrication technique proposed.
| 11395D |  |  |  | 1.04-C-4 | Furnish a list of recommended spare parts for each piece of equipment in the scope of supply.
| 11395D |  |  |  | 1.04-C-5 | Process control narrative.
| 11395D |  |  |  | 1.04-C-6 | Description of control system operation to demonstrate compliance with the Specifications.
| 11395D |  |  |  | 1.04-C-7 | Equipment offloading and installation instructions with enough detail to allow the Contractor to complete the mechanical and electrical installation of all System components.
| 11395D |  |  |  | 1.04-C-8 | Annual utility and nutrient usage calculations.
| 11395D |  |  |  | 1.04-C-9 | Information on hazards associated with the System and appropriate safety precautions, including applicable Material Safety Data Sheets (MSDS).
| 11395D |  |  |  | 1.04-C-10 | Installation guidelines for the Contractor.
| 11395D |  |  |  | 1.04-C-11 | Manufacturer’s catalog information, descriptive literature, specifications, and identification of materials of construction. Provide a detailed bill of materials.
| 11395D |  |  |  | 1.04-C-12 | Manufacturer’s Information on the Bioscrubber media.
| 11395D |  |  |  | 1.04-C-13 | Manufacturer’s information on the recirculation pump, spray nozzle, mist eliminator and all other mechanical components as applicable.
| 11395D |  |  |  | 1.04-C-14 | External utility requirements.
| 11395D |  |  |  | 1.04-C-15 | Complete instrumentation, control, logic, and power wiring diagrams, electrical schematics in sufficient details to allow installation of the instrumentation, controls, and electrical components.
| 11395D |  |  |  | 1.04-C-16 | VWCP, VLCPs and VMCP external layouts, internal layouts, bill of materials, logic diagrams, HMIs, power and control wirings, PLC I/O, network connections, calculations, thermal management including air conditioners and heaters.
| 11395D |  |  |  | 1.04-C-17 | Coating systems - Including manufacturer's descriptive technical catalog literature and specifications per Section 09960 - High-Performance Coatings.
| 11395D |  |  |  | 1.04-C-18 | Field-testing plan for meeting system performance requirements.
| 11395D |  |  |  | 1.04-D-1 | Quality control submittals: Manufacturer’s Certification of Compliance that the factory finish system is identical to the requirements specified herein.
| 11395D |  |  |  | 1.04-D-2 | Quality control submittals: Manufacturer’s Certificate of Installation and Functionality Compliance.
| 11395D |  |  |  | 1.04-D-3 | Quality control submittals: Manufacturer’s training program.
| 11395D |  |  |  | 1.04-D-4 | Quality control submittals: Equipment Testing and Field Start-Up Report.
| 11395D |  |  |  | 1.04-E | Submit certification indicating the quality control, testing, and inspection has been completed and standards specified herein have been met prior to shipment to the jobsite.
| 11395D |  |  |  | 1.04-F | Furnish 3 bound copies and two (2) electronic copies of the Operation and Maintenance instructions for each odor control unit.
11395D-001.0 | 11395D | HEADWORKS ODOR CONTROL SYSTEM |  |  | 1.04-G | Submit the performance guarantee and warranty for the system. | 2025-06-17 |  |  | Submitted
| 11395D |  |  |  | 1.04-H | Submit results of all performance testing procedures and results.
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-1 | Detailed structural and mechanical layout drawings showing system fabrication, dimensions, size, and locations of connections to other work. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-2 | Complete basis of design calculations for the FRP vessels, ladders, and media supports. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-3 | Description of the laminate and the type of reinforcing to be used and a letter from the manufacturer stating the laminate reinforcing material used will provide chemical resistance at least equal to the published chemical resistance for the resin for the intended application, and the resin will meet the performance requirements stated and is suitable for the service conditions specified herein and the fabrication technique proposed. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-4 | Furnish a list of recommended spare parts for each piece of equipment in the scope of supply. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-5 | Process control narrative. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-6 | Description of control system operation to demonstrate compliance with the Specifications. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-7 | Equipment offloading and installation instructions with enough detail to allow the Contractor to complete the mechanical and electrical installation of all System components. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-8 | Annual utility and nutrient usage calculations. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-9 | Information on hazards associated with the System and appropriate safety precautions, including applicable Material Safety Data Sheets (MSDS). | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-10 | Installation guidelines for the Contractor. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-11 | Manufacturer’s catalog information, descriptive literature, specifications, and identification of materials of construction. Provide a detailed bill of materials. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-12 | Manufacturer’s Information on the biological and activated carbon media. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-13 | Manufacturer’s information on spray nozzle, mist eliminator and all other mechanical components as applicable. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-14 | External utility requirements. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-15 | Complete instrumentation, control, logic, and power wiring diagrams in sufficient details to allow installation of the instrumentation, controls, and electrical components. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-16 | VWCP and VMCP external layouts, internal layouts, bill of materials, logic diagrams, HMIs, power and control wirings, PLC I/O, network connections, calculations, thermal management including air conditioners and heaters. | 2025-09-02 | 2025-09-12 |  | AN
11395E-001.0 | 11395E | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-17 | Coating systems: Including manufacturer's descriptive technical catalog literature and Specifications per Section 09960 - High-Performance Coatings. | 2025-09-02 | 2025-09-12 |  | AN | This is space is intentionnaly left blank for scrolling
11395E-001.0 |  | BLEND TANKS ODOR CONTROL SYSTEM | Product Data | QC/Marshall | 1.04-C-18 | Field-testing plan for meeting system performance requirements. | 2025-09-02 | 2025-09-12 |  | AN
[5 empty] | 1.04-D-1 | Quality control submittals: Manufacturer’s Certification of Compliance that the factory finish system is identical to the requirements specified herein.
[5 empty] | 1.04-D-2 | Quality control submittals: Manufacturer’s Certificate of Installation and Functionality Compliance.
[5 empty] | 1.04-D-3 | Quality control submittals: Manufacturer’s training program.
[5 empty] | 1.04-D-4 | Quality control submittals: Equipment Testing and Field Start-Up Report.
[5 empty] | 1.04-E | Submit certification indicating the quality control, testing, and inspection has been completed and standards specified herein have been met prior to shipment to the jobsite.
[5 empty] | 1.04-F | Furnish three (3) bound copies and two (2) electronic copies of the Operation and Maintenance instructions for each odor control unit.
[5 empty] | 1.04-G | Submit the performance guarantee and warranty for the system. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-H | Submit results of all performance testing procedures and results.
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-1 | Detailed structural and mechanical layout drawings showing system fabrication, dimensions, size, and locations of connections to other work. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-2 | Complete basis of design calculations for the FRP vessels, ladders, and media supports. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-3 | Description of the laminate and the type of reinforcing to be used and a letter from the manufacturer stating the laminate reinforcing material used will provide chemical resistance at least equal to the published chemical resistance for the resin for the intended application, and the resin will meet the performance requirements stated and is suitable for the service conditions specified herein and the fabrication technique proposed. Manufacturer shall also submit certification of applicable wind load design in accordance with current edition of the Hawaii Building Code and applicable specifications. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-4 | Furnish a list of recommended spare parts for each piece of equipment in the scope of supply. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-5 | Process control narrative. Include irrigation system summary of the operation mode of irrigation. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-6 | Description of control system operation to demonstrate compliance with the Specifications. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-7 | Equipment offloading and installation instructions with enough detail to allow the Contractor to complete the mechanical and electrical installation of all System components. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-8 | Annual utility and nutrient usage calculations. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-9 | Information on hazards associated with the System and appropriate safety precautions, including applicable Material Safety Data Sheets (MSDS). | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-10 | Installation guidelines for the Contractor. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-11 | Manufacturer’s catalog information, descriptive literature, specifications, and identification of materials of construction. Provide a detailed bill of materials. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-12 | Manufacturer’s Information on the biological and activated carbon media. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-13 | Manufacturer’s information on spray nozzle, mist eliminator and all other mechanical components as applicable. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-14 | External utility requirements. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-15 | Complete instrumentation, control, logic, and power wiring diagrams in sufficient details to allow installation of the instrumentation, controls, and electrical components. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-16 | VWCP and VMCP external layouts, internal layouts, bill of materials, logic diagrams, HMIs, power and control wirings, PLC I/O, network connections, calculations, thermal management including air conditioners and heaters. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.0 | 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-C-17 | Coating systems: Including manufacturer's descriptive technical catalog literature and Specifications per Section 09960 - High-Performance Coatings. | 2025-09-02 | 2025-09-10 | 2025-09-24 | REV
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-1 | Detailed structural and mechanical layout drawings showing system fabrication, dimensions, size, and locations of connections to other work. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-2 | Complete basis of design calculations for the FRP vessels, ladders, and media supports. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-3 | Description of the laminate and the type of reinforcing to be used and a letter from the manufacturer stating the laminate reinforcing material used will provide chemical resistance at least equal to the published chemical resistance for the resin for the intended application, and the resin will meet the performance requirements stated and is suitable for the service conditions specified herein and the fabrication technique proposed. Manufacturer shall also submit certification of applicable wind load design in accordance with current edition of the Hawaii Building Code and applicable specifications. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-4 | Furnish a list of recommended spare parts for each piece of equipment in the scope of supply. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-5 | Process control narrative. Include irrigation system summary of the operation mode of irrigation. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-6 | Description of control system operation to demonstrate compliance with the Specifications. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-7 | Equipment offloading and installation instructions with enough detail to allow the Contractor to complete the mechanical and electrical installation of all System components. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-8 | Annual utility and nutrient usage calculations. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-9 | Information on hazards associated with the System and appropriate safety precautions, including applicable Material Safety Data Sheets (MSDS). | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-10 | Installation guidelines for the Contractor. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-11 | Manufacturer’s catalog information, descriptive literature, specifications, and identification of materials of construction. Provide a detailed bill of materials. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-12 | Manufacturer’s Information on the biological and activated carbon media. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-13 | Manufacturer’s information on spray nozzle, mist eliminator and all other mechanical components as applicable. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-14 | External utility requirements. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-15 | Complete instrumentation, control, logic, and power wiring diagrams in sufficient details to allow installation of the instrumentation, controls, and electrical components. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-16 | VWCP and VMCP external layouts, internal layouts, bill of materials, logic diagrams, HMIs, power and control wirings, PLC I/O, network connections, calculations, thermal management including air conditioners and heaters. | 2025-09-24 |  |  | Submitted
11395F-001.1 | 11395F | SOLIDS ODOR CONTROL SYSTEM | Resubmittal |  | 1.04-C-17 | Coating systems: Including manufacturer's descriptive technical catalog literature and Specifications per Section 09960 - High-Performance Coatings. | 2025-09-24 |  |  | Submitted
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  | Commising | 1.04-C-18 | Field-testing plan for meeting system performance requirements.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  | QC | 1.04-D-1 | Quality control submittals: Manufacturer’s Certification of Compliance that the factory finish system is identical to the requirements specified herein.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  | QC | 1.04-D-2 | Quality control submittals: Manufacturer’s Certificate of Installation and Functionality Compliance.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  | QC | 1.04-D-3 | Quality control submittals: Manufacturer’s training program.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  | QC | 1.04-D-4 | Quality control submittals: Equipment Testing and Field Start-Up Report.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-E | Submit certification indicating the quality control, testing, and inspection has been completed and standards specified herein have been met prior to shipment to the jobsite.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-F | Furnish three (3) bound copies and two (2) electronic copies of the Operation and Maintenance instructions for each odor control unit.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-G | Submit the performance guarantee and warranty for the system.
| 11395F | SOLIDS ODOR CONTROL SYSTEM |  |  | 1.04-H | Submit results of all performance testing procedures and results.
11403-001.0 | 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker | Marshall/QC | 1.03-B | Product data including materials of construction. | 2025-09-02 |  | 2025-09-16 | Submitted
11403-001.0 | 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker | Marshall/QC | 1.03-C | Shop drawings. | 2025-09-02 |  | 2025-09-16 | Submitted
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-D | Calculations.
11403-001.0 | 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker | Marshall/QC | 1.03-E | Product data of other equipment provided with the heat exchanger package. | 2025-09-02 |  | 2025-09-16 | Submitted
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-F | ASME certification.
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-G | Quality control submittals.
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-H | Operation and maintenance manuals.
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-I-1 | Commissioning submittals: Provide Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-I-2 | Commissioning submittals: Provide Manufacturer’s Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
| 11403 | TUBE-IN-TUBE HEAT EXCHANGER | Walker |  | 1.03-J-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
11406-001.0 | 11406A | WASTE GAS BURNER | L&J Technologies | QC/Marshall | 1.03-B-1 | The make and model and catalog cut sheets for all waste gas burner system components showing materials of construction, layout plans and section drawings for all components, anchor bolt sizing calculations and drawings (if anchor bolts used), a process and instrumentation diagram meeting ISA standards, and identification of all materials and metallurgy used in the system. | 2025-09-04 |  | 2025-09-18 | submitted
[5 empty] | 1.03-B-2 | Wiring and control diagrams of the system.
[5 empty] | 1.03-B-3 | Complete piping layout drawings for the pilot gas train.
[5 empty] | 1.03-B-4 | Complete control descriptions including sequence of operations, safety features, and alarms.
[5 empty] | 1.03-B-5 | Local control panel arrangement, elevations, control system logic and control system wiring diagrams, and control schematics.
[5 empty] | 1.03-B-6 | Calculations demonstrating resistance of the equipment to loadings/forces from snow, wind, and seismic conditions specified herein. Calculations to be signed by an engineer registered in the state of Hawaii.
[5 empty] | 1.03-B-7 | Installation procedures.
[5 empty] | 1.03-B-8 | Requirements for storage and protection prior to installation.
[5 empty] | 1.03-B-9 | Complete drawings on control panel mounting frame.
[5 empty] | 1.03-C-1 | Operations and Maintenance Manual: As-built control system logic and wiring diagrams.
[5 empty] | 1.03-C-2 | Operations and Maintenance Manual: Maintenance schedule.
| 11406B | TEMPORARY FLARE |  |  | 1.05-D | The temporary flare plan.
| 11501 | DIGESTER GAS CONDITIONING SYSTEM |  |  | 1.05-A | Supplier shall submit equipment and appurtenances specified in this Section in a complete initial submittal as specified in Section 01330 - Submittal Procedures and Section 15050 - Common Work Results for Mechanical Equipment.
[5 empty] | 1.05-B-1 | Engineering drawings.
[5 empty] | 1.05-B-2 | Complete shop drawings.
[5 empty] | 1.05-B-3 | Structural calculations and anchor bolt sizing for structures.
[5 empty] | 1.05-B-4 | Data sheets and product information for the H2S adsorption media, including material safety data sheets.
[5 empty] | 1.05-B-5 | Certified treatment performance and pressure drop calculations for all system components considering the full range of specified digester gas conditions and ambient conditions.
[5 empty] | 1.05-B-6 | Material ASTM designations.
[5 empty] | 1.05-B-7 | Complete Operation and Maintenance Support and Service Plan that documents periodic gas sampling and service requirements for the mechanical and H2S adsorption equipment.
[5 empty] | 1.05-B-8 | Original manufacturer installation guides, operation and maintenance manuals, bulletins, and spare part lists for each component.
[5 empty] | 1.05-B-9 | Maintenance Service Agreement (MSA) – MSA including maintenance service requirements per Part 3 – Execution, below.
[5 empty] | 1.05-B-10 | Handheld analyzer, including manufacturer’s published product data and certification showing it has been calibrated for the digester gas application.
[5 empty] | 1.05-C-1 | Supplier shall clearly identify: Field wiring and terminations.
[5 empty] | 1.05-C-2 | Supplier shall clearly identify: Instrumentation and equipment supplied by others.
[5 empty] | 1.05-C-3 | Supplier shall clearly identify: Any shipped-loose instrumentation and/or equipment for Contractor to install and their recommended installation locations.
11555-001.0 | 11555(ADD4) | SELF-CLEANING STRAINERS | Tekleen Product Data |  | 1.04-B | Product data: As specified in Section 15050 - Basic Mechanical Materials and Methods. | 2025-05-05 | 2025-05-22 |  | REV
11555-001.0 | 11555(ADD4) | SELF-CLEANING STRAINERS | Tekleen Product Data |  | 1.04-C | Shop drawings. | 2025-05-05 | 2025-05-22 |  | REV
11555-001.1 | 11555(ADD4) | SELF-CLEANING STRAINERS | Tekleen Product Data |  | 1.04-B | Product data: As specified in Section 15050 - Basic Mechanical Materials and Methods. | 2025-09-12 |  |  | Submitted
11555-001.1 | 11555(ADD4) | SELF-CLEANING STRAINERS | Tekleen Product Data |  | 1.04-C | Shop drawings. | 2025-09-12 |  |  | Submitted
|  | SELF-CLEANING STRAINERS |  |  | 1.04-D | Calculations.
|  | SELF-CLEANING STRAINERS |  |  | 1.04-E-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
|  | SELF-CLEANING STRAINERS |  |  | 1.04-F-1 | Commissioning submittals: Provide Manufacturer's Certificate of Source Testing as specified in Section 01756 - Commissioning.
|  | SELF-CLEANING STRAINERS |  |  | 1.04-F-2 | Commissioning submittals: Provide Manufacturer's Certificate of Installation and Functionality Compliance as specified in Section 01756 - Commissioning.
|  | SELF-CLEANING STRAINERS |  |  | 1.04-G-1 | Project closeout documents: Provide vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
11635-001.0 | 11635 | AUTOMATIC SAMPLERS
Formulas:
NLT Date (14 days) = [Return Date]+30
NLT Date (14 days) = 15+[Return Date]

## Civil
note: submittal status code: AN - Approved no Exeception, AC - Approved with comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
01722-001.0 | 01722 | FIELD ENGINEERING |  | Civil | 1.02 B | Qualifications of the professional land surveyor that will be performing the field engineering. | 2025-04-16 | 2025-04-22 | 2025-04-30 | AN | This is space is intentionnaly left blank for scrolling
|  |  |  | Civil | 1.02-C | Pre-Excavation Report. |  |  | N/A
01734-001.0 | 01734 | WORK WITHIN PUBLIC RIGHT-OF-WAY | Traffic Control Plan | Civil | 1.03-A | Traffic control plan: Submit detailed traffic control plan for acceptance by jurisdictional agency. |  |  | N/A | L
| 01738 | SELECTIVE ALTERATIONS AND DEMOLITION |  | Civil | 1.05-B | Shop drawings. |  |  | N/A
n/a |  |  |  |  | 1.05-C-1 | Permits and notices authorizing demolition. |  |  | N/A
|  |  |  | Civil | 1.05-C-2 | Certificates of severance of utility services. |  |  | N/A
01738-001.0 |  |  | Solid Waste Dispersion SOH, Solid Waste Management Plan |  | 1.05-C-3 | Permit for transport and disposal of debris. | 2025-05-19 | 2025-05-23 | 2025-06-02 | RC
|  |  |  | Civil | 1.05-C-4 | Selective Demolition Plan. |  |  | N/A
|  |  |  | Civil | 1.05-C-5 | Pipe Abandonment Plan. |  |  | N/A |  | This is space is intentionnaly left blank for scrolling
| 01757 | DISINFECTION | Disinfection Test Plan | QC/Civil | 1.03-A | Submit disinfection test plan which details procedure to be utilized to disinfect the facilities. |  |  | N/A
| 01757 | DISINFECTION |  | QC/Mech | 1.03-B | Submit disinfection reports. |  |  | N/A
| 01757 | DISINFECTION |  | QC/Mech | 1.03-C | Submit bacteriological reports. |  |  | N/A
| 01757 | DISINFECTION |  |  | 1.03-D | Submit required permits, including but not limited to permit clearance. |  |  | N/A
02050-001.0 | 02050 | SOILS AND AGGREGATES FOR EARTHWORK | PunaRock Aggregate | Civil | 1.03-A& B-1,2 | Product data./Test Reports/ Certificates of Compliances | 2025-04-15 | 2025-04-17 | 2025-04-29 | REV
02050-001.1 | 02050 | SOILS AND AGGREGATES FOR EARTHWORK | PunaRock Aggregate | Civil | 1.03-A& B-1,2 | Product data./Test Reports/ Certificates of Compliances | 2025-05-30 | 2025-06-05 | 2025-06-13 | AC
| 02085 | PRECAST CONCRETE VAULTS |  | Civil | 1.03-B | Shop drawings. |  |  | N/A
|  |  |  | Civil | 1.03-C | Manufacturer’s Certification for Vaults: Written certification that the vault complies with the requirements of this Section. |  |  | N/A
| 02240 | DEWATERING |  | Civil | 1.02-A | Dewatering plan. |  |  | N/A
02256-001.0 | 02256 | FOUNDATION PROBING AND GROUTING | Probe and Grout QC Specialist Qualifications | QC | 1.03-B | Submit the name and qualifications of the Contractor-retained QC Specialist responsible to inspect, observe, and document the following work activities: drilling and cleaning of probe holes; grout preparation; backfilling; and any other related work activities as required throughout construction. | 2025-06-27 | 2025-08-18 | 2025-07-11 | AN
02256-002.0 | 02256 | FOUNDATION PROBING AND GROUTING | Probe and Grout Work PLan | Civil | 1.03-C | Probe and Grout Work Plan. | 2025-07-29 | 2025-08-26 | 2025-08-12 | REV
| 02256 | FOUNDATION PROBING AND GROUTING |  | QC | 1.03-D | Reports and Records. |  |  | N/A
| 02260 | EXCAVATION SUPPORT AND PROTECTION |  | Civil | 1.04-A | Shop drawings and calculations |  |  | N/A
|  | EXCAVATION SUPPORT AND PROTECTION |  | Civil | 1.04-B-1 | Submit location and details of control points and method and schedule of measurements. |  |  | N/A
|  | EXCAVATION SUPPORT AND PROTECTION |  | Civil | 1.04-B-2 | Survey data. |  |  | N/A
|  | EXCAVATION SUPPORT AND PROTECTION |  | Civil | 1.04-C | Detailed sequence of installation and removal of shoring. |  |  | N/A
02260-001.0 |  | EXCAVATION SUPPORT AND PROTECTION | Vibration Monitoring Program | Civil | 1.04-D-1 | Vibration monitoring program as specified in Section 02238 - Rock Removal. | 2025-07-03 | 2025-08-22 | 2025-07-17 | AN
02260-001.0 |  | EXCAVATION SUPPORT AND PROTECTION | Vibration Monitoring Program | Civil | 1.04-D-2 | Manufacturer’s literature on vibration monitoring instrumentation. | 2025-07-03 | 2025-08-22 | 2025-07-17 | AN
02260-002.0 |  | EXCAVATION SUPPORT AND PROTECTION | Baseline Data | QC | 1.04-D-3 | Vibration monitoring data. | 2025-08-04 | 2025-08-25 | 2025-08-18 | AN
|  | EXCAVATION SUPPORT AND PROTECTION |  | Civil | 1.04-F | Dewatering submittals as specified in Section 02240 - Dewatering, with submittals for excavation support and protection. |  |  | N/A
| 02280 | SUBSURFACE UTILITY ENGINEERING |  | Civil | 1.06-A | Shop drawings. |  |  | N/A
02280-001.0 |  |  | Pothole Plan | Civil | 1.06-B-1 | Submit a schedule for all SUE events that shows start, end, and intermediate milestones. | 2025-06-12 | 2025-07-12 | 2025-06-26 | REV
02280-001.0 |  |  | Pothole Plan | Civil | 1.06-B-2 | Provide sketches showing the conditions at various stages in the sequence of SUE. | 2025-06-12 | 2025-07-12 | 2025-06-26 | REV
| 02300 | EARTHWORK |  | PM | 1.04-A | Copy of Property Owner’s Agreement allowing placement of surplus soil material on their property. |  |  | N/A
02300-001.0 | 02300 | EARTHWORK | CEL Earthwork Lab Capabilities | QC | 1.04-B | Testing lab: Submit Contractor's proposed testing laboratory capabilities and equipment. | 2025-06-18 | 2025-07-31 | 2025-07-02 | AN
02300-002.0 | 02300 | EARTHWORK | For Information Only - Test Report Proctor | QC | 1.04-C-1 | Submit certified test reports of tests specified to be performed by the Contractor. |  |  | N/A | RA
| 02300 | EARTHWORK |  | PM | 1.04-D | Qualifications of Offsite Borrow Source: If offsite borrow source is required, Contractor shall submit qualifications package of the borrow source for approval by the Engineer. |  |  | N/A
02312-001.0 | 02312 | CONTROLLED LOW STRENGTH MATERIAL (CLSM) | Mix Design CLSM | Civil | 1.03-A | Product data: Submit data completely describing materials in the mix and demonstrating compliance with the requirements of this Section. | 2025-07-28 | 2025-08-19 | 2025-08-11 | NCR
| 02312 |  |  | QC | 1.03-B-2 | Trial batch test data. |  |  | N/A
| 02314 | LOW DENSITY CELLULAR CONCRETE FILL |  | Civil | 1.03-A | Mix design. |  |  | N/A
|  |  |  | Civil | 1.03-B | Cellular concrete applicator qualifications. |  |  | N/A
|  |  |  | QC | 1.03-C | Test reports. |  |  | N/A
| 02318 | TRENCHING |  | Civil | 1.04-B | Product data on soils and aggregates. |  |  | N/A
|  |  |  | Civil | 1.04-C-1 | Provide 50-pound sample of materials when requested by the Engineer. |  |  | N/A
|  |  |  | QC | 1.04-D-1 | Certification of Contractor's testing laboratory. |  |  | N/A
|  |  |  | QC | 1.04-D-2 | Record copy report for tests performed by Contractor's testing laboratory. |  |  | N/A
02370-001.0 | 02370 | RIPRAP |  | Civil | 1.02-A | Puna Riprap: Product data. | 2025-04-14 | 2025-04-15 | 2025-04-28 | REV
02370-001.1 | 02370 | RIPRAP |  | Civil | 1.02-A | Puna Riprap: Product data. | 2025-07-07 | 2025-08-15 | 2025-07-21 | AN
2600-001.0 | 02600 | CONCRETE MANHOLES | CONCRETE MANHOLES | Civil | 1.03-B | Shop drawings. | 2025-09-24 |  |  | Submitted
|  |  |  | Civil | 1.03-C | Calculations and criteria used in manhole design including material properties, loadings, load combinations, and dimensions assumed. |  |  | N/A
|  |  |  | Civil | 1.03-D | Test methods and results including certification that the manhole riser exceeds the minimum requirements in accordance with ASTM C478. |  |  | N/A
|  |  |  | Civil | 1.0-E | Sealed drawings and design calculations by a licensed Professional Engineer licensed in the State where the project is located. |  |  | N/A
|  |  |  | Civil | 1.03-F-1 | ISO 9001 certificate by a third party confirming that ASTM test reports are valid and up to date at the time of the bid and during construction period. |  |  | N/A
|  |  |  | Civil | 1.03-F-2 | Manufacturer's Certificate of Source Testing. |  |  | N/A
02620-001.0 | 02620 | Filter Fabric | Filter Fabric - Mirafi 140N | QC | 1.04-A | Product data. | 2025-04-15 | 2025-04-25 | 2025-04-29 | AN
[5 empty] | 1.04-B | Samples. | 2025-04-15 | 2025-04-25 | 2025-04-29
[5 empty] | 1.04-C-1 | QC: Certificates of Compliance. | 2025-04-15 | 2025-04-25 | 2025-04-29
[5 empty] | 1.04-C-2 | QC: Manufacturer's Instructions. |  | 2025-04-25 | N/A
02621-001.0 | 02621 | Stabilization Fabric | Stabilization Fabric - Mirafi 600X | QC | 1.04-A | Product data. | 2025-04-15 | 2025-04-25 | 2025-04-29 | AN
[5 empty] | 1.04-B | Samples. | 2025-04-15 | 2025-04-25 | 2025-04-29
[5 empty] | 1.04-C-1 | Certificates of Compliance. | 2025-04-15 | 2025-04-25 | 2025-04-29
[5 empty] | 1.04-C-2 | Manufacturer's Installation Instructions. |  |  | N/A
| 02742 | ASPHALTIC CONCRETE PAVING |  | Yamada | 1.03-A | Proposed mix design and gradation of materials. |  |  | N/A
|  |  |  | Yamada | 1.03-B-1 | Certificate of Compliance. |  |  | N/A
02762-001.0 | 02762 | PAVEMENT MARKINGS | Traffic Sign Submital | Civil / GP | 1.02-A | Product data. | 2025-05-05 | 2025-06-02 | 2025-05-19 | REV
02762-001.1 | 02762 | PAVEMENT MARKINGS | Traffic Sign Submital | Civil / Gp | 1.02-A | Product data. | 2025-06-03 |  | 2025-06-17 | Submitted
| 02762 | PAVEMENT MARKINGS |  | Civil | 1.02-B | Manufacturer's instructions. |  |  | N/A
| 02772 | CONCRETE CURBS, GUTTERS, AND SIDEWALKS |  | Civil | 1.02-A | Product data: Submit data completely describing products. |  |  | N/A
|  |  |  | Civil | 1.02-B | Samples: Submit samples when requested. |  |  | N/A
02820-001.1 | 02820 | FENCES AND GATES (Islandwide Fencing) |  | islandwide | 1.03-A | Product data: Submit data completely describing products. | 2025-05-20 | 2025-06-05 | 2025-06-03 | REV
02820-001.1 |  |  |  | islandwide | 1.03-B | Shop drawings. | 2025-05-20 | 2025-06-05 | 2025-06-03 | REV
02820-001.1 |  |  |  | islandwide | 1.03-C-1 | Certificates of compliance: Provide certification that materials conform to referenced specifications. | 2025-05-20 | 2025-06-05 | 2025-06-03 | REV
02820-001.1 |  |  |  | islandwide | 1.03-C-2 | Qualifications: Provide installer's references and list of local references. | 2025-05-20 | 2025-06-05 | 2025-06-03 | REV
02820-001.3 | 02820 | FENCES AND GATES (Islandwide Fencing) |  | islandwide | 1.03-A | Product data: Submit data completely describing products. | 2025-06-26 | 2025-08-25 | 2025-07-10 | REV
02820-001.3 |  |  |  | islandwide | 1.03-B | Shop drawings. | 2025-06-26 | 2025-08-25 | 2025-07-10 | REV
02820-001.3 |  |  |  | islandwide | 1.03-C-1 | Certificates of compliance: Provide certification that materials conform to referenced specifications. | 2025-06-26 | 2025-08-25 | 2025-07-10 | REV
02820-001.3 |  |  |  | islandwide | 1.03-C-2 | Qualifications: Provide installer's references and list of local references. | 2025-06-26 | 2025-08-25 | 2025-07-10 | REV
02820-001.4 | 02820 | FENCES AND GATES (Islandwide Fencing) | Resubmittal Islandwide | islandwide | 1.03-A | Product data: Submit data completely describing products. | 2025-08-27 | 2025-09-19 | 2025-09-10 | AC
02820-001.4 |  |  |  | islandwide | 1.03-B | Shop drawings. | 2025-08-27 | 2025-09-19 | 2025-09-10 | AC
02820-001.4 |  |  |  | islandwide | 1.03-C-1 | Certificates of compliance: Provide certification that materials conform to referenced specifications. | 2025-08-27 | 2025-09-19 | 2025-09-10 | AC
02820-001.4 |  |  |  | islandwide | 1.03-C-2 | Qualifications: Provide installer's references and list of local references. | 2025-08-27 | 2025-09-19 | 2025-09-10 | AC
| 02952 | PAVEMENT RESTORATION AND REHABILITATION |  | Civil | 1.02-A-1 | Prior to placement of asphalt concrete, submit full details, including design and calculations for the asphalt concrete mix proposed. |  |  | N/A
|  |  |  | Civil | 1.02-A-2 | Submit gradation of aggregate base. |  |  | N/A
|  |  |  | Civil | 1.02-A-3 | Submit proposed mix design of portland cement concrete. |  |  | N/A
Formulas:
NLT Date (14 days) = IF(ISBLANK([Date Submitted]),"N/A",[Date Submitted]+14)
Return Date = 30+[Date Submitted]

## Building
note: submittal status code: AN - Approved no comments, AC - Approved with comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 01759 | WATER LEAKAGE TEST FOR CONCRETE STRUCTURES |  |  | 1.03-A | Shop drawings. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 01759 |  |  | QC | 1.03-B | Tests and evaluation reports.
| 01759 |  |  | QC | 1.03-C-1 | Testing plan for each structure, or portion thereof, required to be tested.
| 01759 |  |  |  | 1.03-C-2 | Proposed procedures and products for repair of leaks.
03055-001.0 | 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE | Product Data: Adhesive Bonded Reinforcing Bars and All Thread Ro... | Struc | 1.04-A | Product data: Technical data for adhesives. | 2025-06-26 | 2025-08-25 |  | AN
| 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE |  | QA | 1.04-B-1 | Special inspection: Detailed step-by-step instructions for the special inspection procedures required by the building code specified in Section 01410 - Regulatory Requirements.
| 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE |  | Struc | 1.04-B-2 | Evaluation Report confirming that the product complies with the requirements of AC308 for both un-cracked and cracked concrete and for use in Seismic Design Categories A through F.
| 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE |  | Struc | 1.04-B-3 | Installer qualifications.
| 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE |  | QC/Struc | 1.04-C | Inspection and testing reports. |  |  |  |  | This is space is intentionnaly left blank for scrolling
03071-001.0 | 03071 | EPOXIES |  | Struc | 1.03-B | Product Data: Submit manufacturer's data completely describing epoxy materials. | 2025-07-30 | 2025-08-19 |  | AN
03071-001.0 |  |  |  | Struc | 1.03-C-1 | Manufacturer's installation instructions. | 2025-07-30 | 2025-08-19 |  | AN
| 03072 | EPOXY RESIN/PORTLAND CEMENT BONDING AGENT |  |  | N/A
| 03102 | CONCRETE FORMWORK |  | Struc | 1.04-A-1 | Submit in such detail as the Engineer may require to assure themselves that intent of the Specifications can be complied with by use of proposed system. |  |  |  | In progress
|  |  |  | Struc | 1.04-A-2 | Alternate combinations of plywood thickness and stud spacing may be submitted. |  |  |  | In Progress
|  |  |  | Struc | 1.04-A-3 | Shop drawings and design calculations stamped and signed by a Structural Engineer licensed in the State of Hawaii. |  |  |  | In progress
03111-001.0 | 03111 | CONCRETE VOID FILL (GEOFOAM) | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu | 1.03-A | Product data. | 2025-06-27 | 2025-08-22 | 2025-09-05 | REV
03111-001.0 |  |  | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu <kdubbudu@nanhawaii.com> | 1.03-B | Manufacturer's installation instructions for application type specified. | 2025-06-27 | 2025-08-22 | 2025-09-05 | REV
03111-001.1 | 03111 | CONCRETE VOID FILL (GEOFOAM) | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu | 1.03-A | Product data. | 2025-09-16 | 2025-09-22 |  | AN
03111-001.1 |  |  | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu <kdubbudu@nanhawaii.com> | 1.03-B | Manufacturer's installation instructions for application type specified. | 2025-09-16 | 2025-09-22 |  | AN
03111-002.0 | 03111 | CONCRETE VOID FILL (GEOFOAM) | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu | 1.03-A | Product data. | 2025-06-27 | 2025-08-25 | 2025-09-24 | REV
03111-002.0 |  |  | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu <kdubbudu@nanhawaii.com> | 1.03-B | Manufacturer's installation instructions for application type specified. | 2025-06-27 | 2025-08-25 | 2025-09-24 | REV
03111-002.1 | 03111 | CONCRETE VOID FILL (GEOFOAM) | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu | 1.03-A | Product data. | 2025-09-16 |  |  | Submitted
03111-002.1 |  |  | CONCRETE VOID FILL (GEOFOAM) | Krishna Dubbudu <kdubbudu@nanhawaii.com> | 1.03-B | Manufacturer's installation instructions for application type specified. | 2025-09-16 |  |  | Submitted
03150-001.0 | 03150 | CONCRETE ACCESSORIES | Joint fillers | Krishna Dubbudu | 1.03-A | Product data. Joint fillers | 2025-06-27 | 2025-08-19 |  | AN
03150-002.0 | 03150 | CONCRETE ACCESSORIES | PVC Waterstop |  | 1.03-A | product data polyvinyl waterstops | 6/31/2025 | 2025-08-25 | 2025-09-09 | AS
| 03150 | CONCRETE ACCESSORIES |  | Struc | 1.03-B-1 | Sample: Polyvinyl chloride waterstop.
03150-002.0 | 03150 | CONCRETE ACCESSORIES | PVC Waterstop | QC/Struc | 1.03-C | Laboratory test reports: Indicating that average properties of polyvinyl chloride waterstops material and finish conform to requirements specified in this Section. | 6/31/2025 | 2025-08-25 | 2025-09-09 | AS
03150-002.0 | 03150 | CONCRETE ACCESSORIES | PVC Waterstop | Struc | 1.03-D-1-a | Written certificates that polyvinyl chloride waterstops supplied on this Project meet or exceed physical property in accordance with USACE CRD-C-572 and the requirements of this Section. | 6/31/2025 | 2025-08-25 | 2025-09-09 | AS
03150-002.0 | 03150 | CONCRETE ACCESSORIES | PVC Waterstop | Struc | 1.03-D-2 | Manufacturer's instructions: For materials specified in this Section that are specified to be installed with such instructions. | 6/31/2025 | 2025-08-25 | 2025-09-09 | AS
| 03150 | CONCRETE ACCESSORIES |  | QC | 1.04 A | Mock-up
03154-001.0 | 03154 | HYDROPHILIC RUBBER WATERSTOP | Sika Hydrotite(Product Data) | Struc | 1.02-A-2-a | Manufacturer’s product data sheets. | 2025-09-10 |  |  | Submitted
| 03154 | HYDROPHILIC RUBBER WATERSTOP |  | QC/Struc | 1.02-A-3-a | Minimum 6-inch long samples of each type of waterstop to be used if requested by the Engineer.
03154-001.0 | 03154 | HYDROPHILIC RUBBER WATERSTOP | Sika Hydrotite(Product Data) | Struc | 1.02-A-4-a | Installation instructions and recommended installation details for the complete waterstop system, and for each component used in that system. | 2025-09-10 |  |  | Submitted
| 03200 | CONCRETE REINFORCING |  | Struc | 1.04-B-1-a-1 | Schedule of support materials to be provided and locations of use.
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-B-1-b-2 | Manufacturer's data indicating compression strength of concrete and confirming dimensions and thickness(es).height(s) to be provided for each location where used. | 2025-07-29 | 2025-08-19 |  | AC |  |  |  |  | Note: ensure to address comments
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-B-2-a | Mechanical reinforcing bar couplers: Evaluation Report documenting compliance with the requirements of ICC-ES AC133. | 2025-07-29 | 2025-08-19 |  | AC
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-B-2-b | Mechanical reinforcing bar couplers: Details, properties, and dimensions of couplers. Include type or size identification, and bar size(s) and grade(s) for which the coupler is suitable. | 2025-07-29 | 2025-08-19 |  | AC
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-B-2-c | Mechanical reinforcing bar couplers: Manufacturer’s installation and testing instructions. | 2025-07-29 | 2025-08-19 |  | AC
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-B-2-d | Mechanical reinforcing bar couplers: Manufacturer's statement that products installed in accordance with manufacturer's recommended procedures will develop strengths and limit slip as specified in this Section. | 2025-07-29 | 2025-08-19 |  | AC
03200-002.0 | 03200 | CONCRETE REINFORCING | CONCRETE REINFORCING SHOP DRAWINGS Grit basins, Head odor Control, and Head works | Struc | 1.04-C | Shop drawings. | 2025-08-13 | 2025-09-04 | 2025-10-04 | NCR
03200-003.0 | 03200 | CONCRETE REINFORCING | CONCRETE REINFORCING SHOP DRAWINGS Screening Walls | Struc | 1.04-C | Shop drawings. | 2025-09-17 |  |  | Submitted
| 03200 | CONCRETE REINFORCING | Note: If Requested By Engineer | QC/Struc | 1.04-D-1 | Bar supports/wire reinforcement supports: Samples of each type of chair and bolster proposed for use. Submit with letter stating where each type will be used.
| 03200 | CONCRETE REINFORCING | Note: If Requested By Engineer | QC/Struc | 1.04-D-2 | Precast concrete bar supports: Samples of each type of precast support proposed for use. Submit with letter stating where each will be used.
| 03200 | CONCRETE REINFORCING | Note: Submittal be provided for each shipping. | Struc | 1.04-E-1 | Certified copy of mill test for each steel used. Show physical properties and chemical analysis.
| 03200 | CONCRETE REINFORCING | Note: Submittal be provided for each shipping. | Struc | 1.04-E-2-a | Mechanical reinforcing bar couplers: Current Evaluation Report confirming that couplers provide specified tension and compression strength and conform to specified limits on total slip within the coupler.
| 03200 | CONCRETE REINFORCING | Note: Submittal be provided for each shipping. | Struc | 1.04-E-2-b | Mechanical reinforcing bar couplers: Certified copy of mill tests for heat(s) of steel incorporated into the reinforcing bar couplers shipped.
| 03200 | CONCRETE REINFORCING | Note: Submittal be provided for each shipping. | Struc | 1.04-E-2-c | Mechanical reinforcing bar couplers: For threaded sleeve type couplers, heat treatment lot numbers for each shipment.
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-F-1-a | Mechanical reinforcing bar couplers: Manufacturer's installation instructions. | 2025-07-29 | 2025-08-19 |  | AC
03200-001.0 | 03200 | CONCRETE REINFORCING | CMC Rebar(Precast concrete Bar Supports) | Struc | 1.04-F-1-b | Mechanical reinforcing bar couplers: Manufacturer's instructions for confirmation testing of couplers after reinforcing bars have been inserted into the couplers. | 2025-07-29 | 2025-08-19 |  | AC
| 03200 | CONCRETE REINFORCING | Subcontractor has no plan to use welding, will include if needed | Struc | 1.04-G-1-a | Welding procedures conforming to AWS D1.4 for reinforcement to be field welded - Procedures qualification record.
| 03200 | CONCRETE REINFORCING | Subcontractor has no plan to use welding, will include if needed | Struc | 1.04-H-1 | Welder qualifications.
| 03200 | CONCRETE REINFORCING |  | QC | 1.04-I-1 | Field quality control and inspection reports.
| 03200 | CONCRETE REINFORCING |  | QC | 1.04-I-2 | Field quality assurance special inspection and testing reports.
03300-001.0 | 03300 | CAST-IN-PLACE-CONCRETE | Product Submittal: Evaporation Retardant | CQC Team | 1.05-B-1 | Product data: data completely describing products and demonstrating compliance with the requirements of this Section. | 2025-05-06 | 2025-05-20 |  | AC
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Product Data, Design Data, Test Report : Cast-in-Place Concrete | STRUC | 1.05-B-2 | Product data: Data for all products in the mix for each class of concrete shall be submitted concurrently with that mix design. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Product Data: Cast-in-Place Concrete | STRUC | 1.05-B-3-a | Product data: For each admixture included in concrete mixes, submit manufacturer's product data demonstrating compliance with standards specified. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Product Data: Cast-in-Place Concrete | Struc | 1.05-B-4 | Product data: Curing compound: Submit complete data on proposed compound. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Design Data: Cast-in-Place Concrete | STRUC | 1.05-C-1 | Concrete mix designs. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE |  | QC/STRUC | 1.05-D-1 | Concrete mixes - Trial batches: Drying shrinkage test results. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE |  | QC/STRUC | 1.05-D-2 | Concrete mixes - Trial batches: Compression strength test results. |  |  |  | In progress
| 03300 | CAST-IN-PLACE-CONCRETE |  | Struc | 1.05-D-3 | If there is any change in suppliers or in quality of concrete mix constituents, submit new test data.
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Test Reports: Cast-in-Place Concrete | STRUC | 1.05-E-2 | Test reports: Aggregate. |  |  |  | In progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Test Reports: Cast-in-Place Concrete | STRUC | 1.05-E-3 | Test reports: Cement. |  |  |  | In Progress
03300-003.0 | 03300 | CAST-IN-PLACE-CONCRETE | Test Reports: Cast-in-Place Concrete | STRUC | 1.05-E-4 | Test reports: Supplemental cementitious material. |  |  |  | In Progress
| 03300 | CAST-IN-PLACE-CONCRETE |  | STRUC | 1.05-F-1 | Current NRMCA certification for all plants and trucks that will be used to supply concrete.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-G-1 | Truck batch tickets for each load of concrete delivered to the site, whether accepted or rejected.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-G-2 | Concrete supplier's quality control plan.
| 03300 | CAST-IN-PLACE-CONCRETE |  |  | 1.05-H-1 | Contractor's notifications of readiness for concrete placement.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-H-2 | Contractor's reports of field quality control testing.
| 03300 | CAST-IN-PLACE-CONCRETE |  | Struc | 1.05-I-1 | Special procedure submittals: Sequence of concrete placing.
03300-002.0 | 03300 | CAST-IN-PLACE-CONCRETE | Special Procedure: Hot Weather Concreting Plan | Struc | 1.05-I-2 | Special procedure submittals: Hot weather concreting plan. | 2025-05-06 | 2025-06-02 |  | REV
| 03300 | CAST-IN-PLACE-CONCRETE |  | Struc | 1.05-I-3 | Special procedure submittals: Repair of defective concrete
03300-004.0 | 3300 | CAST-IN-PLACE-CONCRETE | Cast-in-place Concrete structures shop drawings | Civil | 1.04 | cast in place delegated drawings
| 03366 | TOOLED CONCRETE FINISHING |  |  | N/A
| 03565 | BASIN BOTTOM GROUT |  |  | 1.04-A | Manufacturer's instructions.
| 03600 | GROUTING |  | Struc | 1.03-A-1 | Cement grout: Mix design.
| 03600 | GROUTING |  | Struc | 1.03-A-2 | Cement grout: Material submittals.
| 03600 | GROUTING |  | Struc | 1.03-B-1 | Cement mortar: Mix design.
| 03600 | GROUTING | Non-shrink Epoxy Grout - Five Star | Struc | 1.03-C-1 | Material submittals. Non-shrink epoxy grout: Manufacturer's literature.
| 03600 | GROUTING |  | QC/STRUC | 1.03-C-2 | Material submittals. Non-shrink epoxy grout: Quality control tests results.
| 03600 | GROUTING |  | Struc | 1.03-D-1 | Non-shrink grout: Manufacturer's literature.
| 03600 | GROUTING |  | Qc/Struc | 1.03-D-2 | Non-shrink grout: Quality control tests results.
| 03703 | THERMAL CONTROL OF CONCRETE |  | STRUC | 1.03-A | Product data.
|  |  |  | STRUC | 1.03-B | Thermal Control Plan.
|  |  |  | STRUC | 1.03-C | Temperature Monitoring Program.
|  |  |  | STRUC | 1.03-D | Temperature monitoring data.
|  |  |  | STRUC | 1.03-E | Layout of cooling pipe system, if used, showing pipe sizes and material type, connections, location, spacing, method of support, and system for monitoring temperature of water in cooling pipes.
03926-001.0 | 03926 | STRUCTURAL CONCRETE REPAIR | Concrete Repair | Struc | 1.03-A | Product data: Submit manufacturer's data completely describing structural repair concrete materials. | 2025-05-09 | 2025-05-14 |  | AN
| 03926 | STRUCTURAL CONCRETE REPAIR |  | STRUC | 1.03-B | Certificates of Compliance.
| 03926 | STRUCTURAL CONCRETE REPAIR |  | STRUC | 1.03-C | Manufacturer's Instructions. |  |  |  |  | This is space is intentionnaly left blank for scrolling
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM | Epoxy | Struc | 1.03-B | Product data. | 2025-05-07 | 2025-05-13 | 2025-06-12 | NCR
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | QC | 1.03-C-1 | Quality control submittals: Certificates of Compliance. | 2025-05-07 | 2025-05-13 | 2025-06-12 | NCR
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | QC | 1.03-C-2 | Quality control submittals: Manufacturer's Instructions. | 2025-05-07 | 2025-05-13 | 2025-06-12 | NCR
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | QC/Struc | 1.03-D-1 | Special procedure submittals: Protection plan for surrounding areas and non-cementitious surfaces. | 2025-05-07 | 2025-05-13 | 2025-06-12 | NCR
03933-001.0 | 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | Struc | 1.03-B | Product data: Submit manufacturer's data completely describing polyurethane resin injection system materials. | 2025-09-08 | 2025-09-09 |  | AN
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC | 1.03-C-1 | Quality control submittals: Certificates of Compliance.
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC | 1.03-C-2 | Quality control submittals: Manufacturer's Instructions.
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC/STRUC | 1.03-C-3 | Quality control submittals: Protection plan for surrounding areas and non-cementitious surfaces. |  |  |  |  | This is space is intentionnaly left blank for scrolling
04055-001.0 | 04055 | ADHESIVE BONDING REINFORCING BARS AND ALL THREAD RODS IN MASONRY | Product Data Hilti HY-270 Adhesive Anchor Sysstem | Struc | 1.04-A-1 | Product data: Independent testing laboratory results indicating allowable loads in tension and shear for masonry walls of the types included in the Work, with load modification factors for temperature, spacing, edge distance, and other installation variables. | 2025-06-26 | 2025-08-25 |  | AC
04055-001.0 | 04055 | ADHESIVE BONDING REINFORCING BARS AND ALL THREAD RODS IN MASONRY | Product Data Hilti HY-270 Adhesive Anchor Sysstem | Struc | 1.04-A-2 | Product data: Handling and storage instructions. | 2025-06-26 | 2025-08-25 |  | AC
04055-001.0 | 04055 | ADHESIVE BONDING REINFORCING BARS AND ALL THREAD RODS IN MASONRY | Product Data Hilti HY-270 Adhesive Anchor Sysstem | Struc | 1.04-A-3 | Product data: Installation instructions. | 2025-06-26 | 2025-08-25 |  | AC
| 04055 | ADHESIVE BONDING REINFORCING BARS AND ALL THREAD RODS IN MASONRY |  | QC/Struc | 1.04-B-1 | Quality control submittals: Detailed instructions for special inspection to comply with the building code specified in Section 01410 - Regulatory Requirements.
| 04055 | ADHESIVE BONDING REINFORCING BARS AND ALL THREAD RODS IN MASONRY |  | QC/Struc | 1.04-B-2 | Evaluation Report confirming that the product complies with the requirements of ICC-ES AC58.
| 04090 | MASONRY ACCESSORIES |  | Struc | 1.03-A-1-a | Changes to reinforcing steel contract drawing requirements: Indicate in separate letter submitted with shop drawings any changes of requirements indicated on the Drawings for reinforcing steel.
| 04090 | MASONRY ACCESSORIES |  | Struc | 1.03-A-1-c | Changes to reinforcing steel contract drawing requirements: Reinforcement detail drawings.
| 04090 | MASONRY ACCESSORIES |  | Struc | 1.03-A-1-d | Changes to reinforcing steel contract drawing requirements: Welding procedures.
| 04090 | MASONRY ACCESSORIES |  | Struc | 1.03-B | Product data.
| 04100 | MORTAR AND MASONRY GROUT |  | STRUC | 1.04-A | Product data.
|  |  |  | STRUC | 1.04-B | Shop drawings.
|  |  |  | STRUC | 1.04-C | Mortar color samples.
|  |  |  | STRUC | 1.04-D | Design Mixes for mortar and grout.
|  |  |  | QC | 1.04-E-1 | Test reports: Mortar Strength Test Results.
|  |  |  | QC | 1.04-E-2 | Test reports: Grout Strength Test Results.
| 04220 | CONCRETE UNIT MASONRY |  | Struc | 1.04-B-1 | Product data: manufacturer’s product data for split face block.
|  |  |  | Struc | 1.04-B-2 | Product data: manufacturer’s product data for proposed cleaning agent.
|  |  |  | Struc | 1.04-C | Shop drawings.
|  |  |  | Struc | 1.04-D | Samples: Include samples of stretcher units in sufficient quantity to illustrate color range.
|  |  |  | QC | 1.04-E-1 | Test reports: Compressive strength.
|  |  |  | QC | 1.04-E-2 | Test reports: Linear shrinkage.
|  |  |  | QC | 1.04-E-3 | Test reports: Moisture content as a percentage of total absorption.
|  |  |  | QC | 1.04-E-4 | Test reports: Total absorption.
|  |  |  | QC | 1.04-E-5 | Test reports: Unit weight.
|  |  |  | STRUC | 1.04-F | Manufacturer’s instructions
|  |  |  | QA | 1.04-G-1 | Quality assurance submittals: If requested by the Engineer, submit a record of the Installer’s evidence of qualifications.
|  |  |  | QA | 1.04-G-2 | Quality assurance submittals: If requested by the Engineer, submit a record of the Masonry Cleaner’s evidence of qualifications.
| 05120 | STRUCTURAL STEEL FRAMING |  | STRUC | 1.04-A-1 | Product data: Welding electrodes : Electrode manufacturer's data.
|  |  |  | STRUC | 1.04-A-2 | Product data: Compressible-washer-type direct tension indicators.
|  |  |  | STRUC | 1.04-A-3 | Product data: Stainless steel.
|  |  |  | STRUC | 1.04-B | Shop drawings.
|  |  |  | QC/STRUC | 1.04-C-1 | Quality control submittals: Welding procedure specifications (WPS) in accordance with AWS D1.1 and D1.6.
|  |  |  | QC/STRUC | 1.04-C-2 | Quality control submittals: Welder qualifications.
|  |  |  | QC/STRUC | 1.04-C-3 | Quality control submittals: Steel fabricator's AISC certification.
|  |  |  | QC/STRUC | 1.04-D-1 | Test reports: Certified copies of mill tests and analyses made in accordance with applicable ASTM standards, or reports from a recognized commercial laboratory, including chemical and tensile properties of each shipment of structural steel or part thereof having common properties.
| 05140 | STRUCTURAL ALUMINUM |  | QC/STRUC | 1.03-A-1 | Quality control submittals: Test Reports: Certified copies of mill tests or reports from a recognized commercial laboratory including chemical and tensile properties of each shipment of structural metal or part thereof having common properties. Tests and analyses shall be made in accordance with applicable ASTM Standards.
|  |  |  | QC/STRUC | 1.03-A-2 | Quality control submittals: Welder’s certificates.
| 05190 | MECHANICAL ANCHORING AND FASTENING TO CONCRETE AND MASONRY |  | Struc | 1.05-A-2 | Submit information listed for each type of anchor or fastener to be used.
|  |  |  | Struc | 1.05-B-1 | Product data.
|  |  |  | Struc | 1.05-B-2 | Samples.
|  |  |  | Struc | 1.05-B-3 | Certificates.
|  |  |  | QC/Struc | 1.05-B-4 | Test reports.
|  |  |  | Struc | 1.05-B-5 | Manufacturer’s instructions.
|  |  |  | Struc | 1.05-B-6 | Qualification statements.
|  |  |  | Struc | 1.05-B-7-a | Delegated Design Submittals: When requesting product substitutions for post installed anchors, submit calculations, indicating the diameter, effective embedment depth and spacing of the proposed anchors, and demonstrating that the substituted product will provide load resistance that is equal to or greater than that provided by the anchors listed in this Section.
| 05310 | STEEL DECKING |  | Struc | 1.03-A | Product data.
|  |  |  | Struc | 1.03-B | Shop drawings.
| 05500 | METAL FABRICATIONS |  | Struc | 1.04-A | Product Data.
05500-001.0 | 05500 | METAL FABRICATIONS | Metal Fabrications | Struc/QC/Jyun | 1.04-B | Shop drawings. | 2025-09-08 | 2025-09-10 | 2025-10-10 | NCR
| 05500 | METAL FABRICATIONS |  | Struc | 1.04-C-1 | Samples: Guardrails with specified finishes.
| 05500 | METAL FABRICATIONS |  | Struc | 1.04-D-1 | Design data.
| 05500 | METAL FABRICATIONS |  | QC | 1.04-D-2-a | Test reports: Guardrails.
| 05500 | METAL FABRICATIONS |  | QC | 1.04-D-2-b | Test reports: Gratings.
| 05500 | METAL FABRICATIONS |  | QC | 1.04-D-2-c | Test reports: Planks.
| 06070(ADD3) | WOOD TREATMENT |  | Struc | 1.04-A | Product Data: Provide data on all treatment products, including field application instructions if applicable.
|  |  |  | Struc | 1.04-B | Preserver Certifications.
|  |  |  | Struc | 1.04-C | Contractor’s Certification: Provide a certification letter stating that all wood used on this job including cuts and penetration were treated and coated with preservatives in compliance with requirements of this contract.
|  |  |  | Struc | 1.04-D | Guarantee: Guarantee form for written guarantee.
|  |  |  | Struc | 1.04-E | Act 045, Session Laws of Hawaii 2018, Contractor Temporary Permit.
| 06200 | FINISH CARPENTRY |  | Struc | 1.03-A | Submit shop drawings, product data, and samples.
|  |  |  | Struc | 1.03-B | Installation instructions.
|  |  |  | Struc | 1.03-C | Submit minimum 6-inch long trim and molding samples, and minimum 2-inch square plastic laminate samples showing colors and patterns.
| 06400 | ARCHITECTURAL WOODWORK |  | Struc | 1.03-A-1 | Shop Drawings.
|  |  |  | Struc | 1.03-A-2 | Product data.
|  |  |  | Struc | 1.03-A-3-a | Samples: Wood species to receive transparent finish.
|  |  |  | Struc | 1.03-A-3-b | Samples: Factory applied finish.
|  |  |  | Struc | 1.03-A-3-c | Samples: Type and color of plastic laminate.
|  |  |  | Struc | 1.03-A-4 | Manufacturer's Installation Instructions.
|  |  |  | Struc | 1.03-A-5 | Warranty.
| 06605(ADD3) | FIBERGLASS REINFORCED PLASTIC PANELS |  | Struc | 1.03-B | Product Data: Manufacturer's data sheets on each product to be used.
|  |  |  | Struc | 1.03-C | Selection Samples: For each finish specified, two complete sets of color chips representing manufacturer's full range of available colors and patterns.
|  |  |  | Struc | 1.03-D | Maintenance Instructions. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 06607(ADD8) | CLARIFIER LAUNDER COVERS |  | Struc | 1.04-B-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
|  |  |  | Struc | 1.04-C-1-a | Manufacturer’s representative qualifications.
|  |  |  | Struc | 1.04-C-1-b | Certificates.
|  |  |  | QC/Struc | 1.04-C-1-c | Test Reports.
|  |  |  | Struc | 1.04-C-1-d | Manufacturer’s representatives field notes and data.
|  |  |  | Struc | 1.04-D-1 | Shop Drawings
| 06608 | FIBERGLASS REINFORCED PLASTIC |  |  | 1.04-A-1 | Submit general arrangement and fabrication drawings, calculations, and elements of the design.
[5 empty] | 1.04-B | Operation and Maintenance Data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-C | Warranty.
| 06611 | FIBERGLASS REINFORCED PLASTIC FABRICATIONS |  |  | 1.03-A | Shop Drawings.
[5 empty] | 1.03-B | Submit general arrangement and fabrication drawings, calculations, and elements of the design for grating and stairs.
[5 empty] | 1.03-C | Product Data and Material Certifications.
[5 empty] | 1.03-D | Manufacturer's Installation Instructions.
[5 empty] | 1.03-E-1 | For tank covers: Submit structural design calculations prepared and signed by a professional structural engineer licensed in the state of Hawaii.
| 06616 | FIBERGLASS REINFORCED PLASTIC HANDRAIL AND GUARDRAIL |  |  | 1.03-A | Product data: Include available colors.
[5 empty] | 1.03-B | Shop drawings: Plans and elevations showing heights, sizes, shapes, and locations of installations, and details of connections and anchorage. Shop drawings shall be stamped and signed by Professional Engineer registered with the state of Hawaii.
| 06622(ADD3) | SOLID SURFACE COUNTERTOPS |  |  | 1.04-A | Shop Drawings.
[5 empty] | 1.04-B | Product Data: Submit manufacturer's product data and installation instruction for each type of countertop material.
[5 empty] | 1.04-C | Color Samples: Submit physical samples and/or color cards of available finishes for countertop materials for selection by Engineer.
| 07110 | DAMPPROOFING |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Shop drawings.
[5 empty] | 1.03-C | Manufacturer's Installation Instructions.
[5 empty] | 1.03-D | Warranty.
| 07164 | CEMENTITIOUS CRYSTALLINE CONCRETE WATERPROOFING |  |  | 1.03-A | Product data: Include mixing and application procedures.
[5 empty] | 1.03-B-1 | Certificates of conformance or compliance: Attest that waterproofing materials meets specified requirements, signed by manufacturer.
[5 empty] | 1.03-B-2 | Certificates of conformance or compliance: Attest that chemical and physical properties of cementitious crystalline waterproofing materials have been determined by specified methods, and have been found to conform with Specification.
|  |  |  | QC/Struc | 1.03-C | Laboratory test reports.
| 07190 | WATER REPELLENTS |  |  | 1.04-A | Product Data.
[5 empty] | 1.04-B | Samples: Water repellent applied on 8-inch by 8-inch substrates to receive water repellent, marked with application date and application rate.
[5 empty] | 1.04-C | Manufacturer's Application Instructions.
07210-001.0 | 07210(ADD3) | BUILDING INSULATION | Building Insulation | QC/Struc | 1.03-B | Manufacturer's Data: Submit manufacturer's specifications and installation instructions for types of insulation required. Include data substantiating that materials comply with specified requirements. | 2025-07-31 | 2025-09-05 |  | AN
[5 empty] | 1.03-C | Material Safety Data Sheets (MSDS): Submit MSDS for each material.
| 07212(ADD5) | WALL INSULATION SYSTEM |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Manufacturer's installation instructions.
| 07220 | ROOF AND DECK INSULATION |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Samples. Include 6-inch square samples of each type and thickness of insulation required.
[5 empty] | 1.03-C | State thickness and R-value of insulation to be provided at each building.
[5 empty] | 1.03-D | Manufacturer's Installation Instructions.
[5 empty] | 1.03-E-1 | Certificates: Certify that products meet or exceed specified requirements.
[5 empty] | 1.03-E-2 | Certificates: Certify that insulation is approved by manufacturer for use with specified roofing materials.
[5 empty] | 1.03-F | Manufacturer's field reports.
[5 empty] | 1.03-G | Warranty.
07410-001.0 | 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING | Preformed Metal roofing and Siding | QC/Struc | 1.03-B | Manufacturer's Data: Submit manufacturer's product specifications, standard details, installation instructions and general recommendations, as applicable to materials and finishes for each component and for total system of preformed panels. | 2025-07-31 | 2025-09-03 |  | AC
| 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING |  |  | 1.03-C | Shop Drawings.
| 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING |  |  | 1.03-D | Roof Color and Samples.
| 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING |  | QC/Struc | 1.03-E | Test Reports: Provide test data demonstrating structural capacity, wind uplift and resistance to water infiltration performance as specified.
| 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING |  |  | 1.03-F | Manufacturer's Technical Representative's Reports: Submit copies of all reports to the Contracting Officer.
| 07410(ADD3) | PREFORMED METAL ROOFING AND SIDING |  |  | 1.03-G | Warranty: Submit warranty as noted under Article 1.04.
| 07540 | THERMOPLASTIC POLYOLEFIN (TPO) MEMBRANE ROOFING |  |  | 1.03-A | Product data: Include specifications and flashing details.
[5 empty] | 1.03-B | Detail drawings.
[5 empty] | 1.03-C | Samples.
[5 empty] | 1.03-D | Manufacturer's Installation Instructions.
[5 empty] | 1.03-E-1 | Certificates: UL listings.
[5 empty] | 1.03-E-2 | Certificates: Letter of certification from the manufacturer certifying the roofing contractor is authorized to install the manufacturer's roofing system, include certified foreman and training dates.
[5 empty] | 1.03-E-3 | Certificates: Indicating membrane thickness from the membrane manufacturer.
[5 empty] | 1.03-F | Installer Authorization: Letter or certificate signed by roofing system manufacturer certifying that installer is approved, authorized, or licensed by manufacturer to install roofing system.
[5 empty] | 1.03-G | Maintenance manual: Include repair instructions.
[5 empty] | 1.03-H-1 | Prior to beginning the Work of this Section: Submit sample warranties.
[5 empty] | 1.03-H-2 | Prior to beginning the Work of this Section: Submit the final System Assembly Letter issued by manufacturer.
[5 empty] | 1.03-H-3 | Prior to beginning the Work of this Section: Submit the Guarantee Application Confirmation document issued by manufacturer.
[5 empty] | 1.03-I-1 | Upon substantial completion: Submit final warranties.
| 07700 | ROOF SPECIALTIES |  |  | 1.03-A | Product data: Include finish and color options.
[5 empty] | 1.03-B | Shop drawings. Include equipment curbs and supports details.
[5 empty] | 1.03-C | Certifications: Certify that curbs are capable of supporting the specified equipment including loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.03-D | Samples: Include finish and color samples.
[5 empty] | 1.03-E | Manufacturer's Installation Instructions.
[5 empty] | 1.03-F | Warranties.
| 07722 | ROOF HATCHES |  |  | 1.03-A | Product data: Indicate general construction, configurations, and jointing methods.
[5 empty] | 1.03-B | Shop drawings: Show locations, sizes, fastening methods, and installation details.
[5 empty] | 1.03-C | Manufacturer's Installation Instructions.
| 07840 | FIRESTOPPING |  | R&L Ohana | 1.03-A | Product data: Submit manufacturer's data and installation instructions.
| 07900 | JOINT SEALANTS |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Samples, include color selections.
[5 empty] | 1.03-C | Manufacturer's Installation Instructions.
[5 empty] | 1.03-D | Warranty.
| 07914 | J-SEALS |  |  | N/A
| 07920(ADD3) | SEALANT |  |  | N/A
| 08254 | PRE-ASSEMBLED PLASTIC DOOR ASSEMBLIES |  |  |  | Product data of other equipment provided with the heat exchanger package
[5 empty] | 1.02-B | Shop drawings.
[5 empty] | 1.02-C | Samples: Typical corners, minimum 6-inch long horizontal and vertical members, showing construction texture and finish color.
[5 empty] | 1.02-D | Manufacturer's instructions: Submit manufacturer's installation instructions.
| 08320 | FLOOR ACCESS DOORS |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Shop drawings.
| 08332 | OVERHEAD COILING DOORS |  |  | 1.03-A | Product data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.03-B | Shop drawings.
[5 empty] | 1.03-C | Samples: Submit samples of finishes for finish selection.
[5 empty] | 1.03-D | Manufacturer’s Certificates: Certify products meet or exceed specified requirements.
[5 empty] | 1.03-E-1 | Manufacturer's instructions.
[5 empty] | 1.03-F-1-a | Project record documents: Operation and maintenance data.
[5 empty] | 1.03-F-1-b | Project record documents: Warranty.
| 08393 | WATERTIGHT DOORS |  |  | 1.06-B-1 | Product Data.
[5 empty] | 1.06-B-2 | Schedules.
[5 empty] | 1.06-B-3 | Manufacturer’s Instructions.
[5 empty] | 1.06-B-4 | Shop drawings.
[5 empty] | 1.06-B-5-a | Manufacturer's certification that the doors furnished, or doors of similar design (including dimensions and detailing), have been tested and will withstand the specified hydrostatic pressure without leakage.
[5 empty] | 1.06-C | Vendor operation and maintenance manual as specified in Section 01782 - Operation and Maintenance Manuals.
[5 empty] | 1.06-D-a | Qualifications: Manufacturer.
|  |  |  | QC | 1.06-D-2 | Protocols for source testing and for field testing.
|  |  |  | QC | 1.06-D-3 | Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
|  |  |  | QC | 1.06-D-4 | Manufacturer’s Certificate of Installation Verification as specified in Section 01756 - Commissioning.
|  |  |  | QC | 1.06-D-5 | Manufacturer’s Certificate of Functional Compliance as specified in Section 01756 - Commissioning.
[5 empty] | 1.06-E-1 | Calculations demonstrating that frame anchoring geometry and anchors will resist pressures against the door without damage to the surrounding concrete.
| 08530(ADD3) | VINYL WINDOWS |  |  | 1.02-B | Manufacturer's Data: Submit manufacturer's descriptive literature and data along with shop drawings for approval.
[5 empty] | 1.02-C | Shop Drawings.
[5 empty] | 1.02-D | Samples: Submit three samples of required finish. Submit samples of finishes, including hardware to the Contracting Officer for acceptance.
|  |  |  | QC | 1.02-E | Test Reports: Where manufacturer's data does not clearly indicate conformance with performance requirements submit test reports from an independent laboratory certifying performance requirements of all exterior systems.
[5 empty] | 1.02-F | Certification: Supply certification by the manufacturer that the windows, including finish, conform to specifications.
[5 empty] | 1.02-G | Warranty: Submit warranty as stipulated in Article 1.04 "WARRANTY".
[5 empty] | 1.02-H | Maintenance Manual: Submit three maintenance manuals for each type of window and finish.
| 08710 | DOOR HARDWARE |  |  | 1.03-A-1 | Product data: Manufacturer's product data sheets.
[5 empty] | 1.03-A-2 | Product data: Product Test Reports.
[5 empty] | 1.03-B | Hardware schedule.
[5 empty] | 1.03-C | Samples: Include for each different type and manufacturer for review of finish.
[5 empty] | 1.03-D | Construction key distribution list: Submit upon Owner's request.
[5 empty] | 1.03-E | Templates.
[5 empty] | 1.03-F | Project record documents: Include corrected hardware schedule.
[5 empty] | 1.03-G | Operating and Maintenance Manuals.
| 08800 | GLAZING |  |  | 1.04-A | Product data.
[5 empty] | 1.04-B | Shop drawings: Locations of glass types and typical glazing details.
[5 empty] | 1.04-C-1 | Samples: Glazing sealants.
[5 empty] | 1.04-C-2 | Samples: Glass.
[5 empty] | 1.04-D | Certificates of compliance: Certification that tempered glass in accordance with ANSI Z97.1 and CPSC 16 CFR 1201.
[5 empty] | 1.04-E | Manufacturer's Installation Instructions.
| 08952 | TRANSLUCENT SKYLIGHT SYSTEM |  |  | 1.03-A | Shop drawings.
[5 empty] | 1.03-B | Product data: Manufacturer's standard technical specifications and product literature describing materials, special handling instructions, and installation instruction.
[5 empty] | 1.03-C | Samples: Include metal finishes, colors of metal framed skylights, and face sheet types and colors.
[5 empty] | 1.03-D | Manufacturer's installation instructions.
[5 empty] | 1.03-E | Warranty.
[5 empty] | 1.03-F | Manufacturer's certificates: Certifications that materials meet specified requirements.
[5 empty] | 1.03-G | Structural calculations.
[5 empty] | 1.03-H | Proof of regular, independent quality control monitoring under a building code review and listing program shall be submitted.
| 09110 | NON-LOAD BEARING WALL FRAMING |  |  | 1.03-A | Product data: Product data for all proposed material for framing system.
| 09131 | ACOUSTICAL CEILING SUSPENSION ASSEMBLIES |  |  | 1.03-A | Product Data: Include installation instructions.
[5 empty] | 1.03-B | Shop Drawings: Include reflected ceiling plan, details.
[5 empty] | 1.03-C | Samples: Include minimum 3-inch long main and cross members showing intersections, profile, and finish.
| 09250 | GYPSUM BOARD |  |  | 1.03-A | Product Data: Include manufacturer's instructions for sealing openings, penetrations, and cut edges of water-resistant gypsum board.
[5 empty] | 1.03-B | Samples: Include texture samples on minimum 6 inch square specified materials.
09310-001.0 | 09310 | CERAMIC TILING | Product Data | Maka Construction | 1.03-A | Product data: Include manufacturer's standard colors. | 2025-07-29 | 2025-09-03 |  | AC
| 09310 | CERAMIC TILING | Samples |  | 1.03-B | Samples: Tile and grout on minimum 24-inch square waterproof boards showing range of Engineer's selected colors.
| 09510(ADD3) | ACOUSTICAL CEILING |  |  | N/A
| 09511 | ACOUSTICAL PANEL CEILINGS |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Samples: Include nominal 12-inch square acoustical panels.
[5 empty] | 1.03-C | Manufacturer's installation instructions.
| 09523 | ACOUSTICAL PANELS |  |  | 1.03-A | Product data: Include sound absorption data, cutting and fabrication, and installation details for panel systems.
[5 empty] | 1.03-B | Shop drawings.
|  |  |  | QC | 1.03-C | Test reports: Results of sound absorption coefficient testing by independent acoustical laboratory.
[5 empty] | 1.03-D | Manufacturer's installation instructions: Including installation instructions for suspended grid system and adhesives.
[5 empty] | 1.03-E | Samples.
09650-001.0 | 09650(ADD3) | RESILIENT FLOORING | Resilient Flooring |  | 1.02-B | Manufacturer's Data: Submit manufacturer's technical data and installation instructions for resilient flooring, wax, and accessories. | 2025-07-16 | 2025-09-22 | 2025-10-22 | NCR
09650-001.0 |  |  |  |  | 1.02-C | Samples: Submit samples of all flooring, bases, and accessories to the Contracting Officer for color and/or pattern selection. | 2025-07-16 | 2025-09-22 | 2025-10-22 | NCR
09650-001.0 |  |  | Resilient Flooring |  | 1.02-D | Maintenance Instructions: Submit manufacturer's recommended cleaning and maintenance practices for resilient flooring and accessories. | 2025-07-16 | 2025-09-22 | 2025-10-22 | NCR
09650-001.0 |  |  | Resilient Flooring | QC | 1.02-E | Test Reports: Submit copies of all concrete floor moisture and alkalinity tests to the Contracting Officer. | 2025-07-16 | 2025-09-22 | 2025-10-22 | NCR
09650-001.0 |  |  | Resilient Flooring |  | 1.02-F | Material Safety Data Sheets (MSDS): Submit MSDS for adhesives, patching and leveling compounds, and sealers. | 2025-07-16 | 2025-09-22 | 2025-10-22 | NCR
09652-001.0 | 09652 | RESILIENT BASE AND ACCESSORIES | RESILIENT BASE AND ADHESIVES |  | 1.02-A | Product data. | 2025-07-16 | 2025-09-22 |  | AC
| 09652 | RESILIENT BASE AND ACCESSORIES |  |  | 1.02-A | Product data.
| 09652 | RESILIENT BASE AND ACCESSORIES |  |  | 1.02-B | Samples: Include 6 inch by full height or width sections for each type or color base and accessory. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 09654 | RESILIENT TILE FLOORING |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Shop drawings.
[5 empty] | 1.03-C | Samples: Include 8-inch by 10-inch sized samples of each flooring material, color, and pattern selected.
[5 empty] | 1.03-D | Manufacturer's installation instructions.
09672-001.0 | 09672(ADD3) | RESINOUS FLOORING | Zelensky | Krishna | 1.03-A | Product Data: For each type of product include manufacturer's technical data, safety data sheets, application instructions, and recommendations for each resinous flooring component required. | 2025-09-12 |  |  | Submitted
| 09672(ADD3) | RESINOUS FLOORING |  |  | 1.03-B | Samples for Verification: For each resinous flooring system required, 6-inches square, applied to a rigid backing by Installer for this Project. Samples must comply with specified system materials, application thickness, color and finish texture.
| 09672(ADD3) | RESINOUS FLOORING |  |  | 1.03-C | Installer Certificates: Installer certification by material manufacturer for the system(s) specified.
09672-001.0 | 09672(ADD3) | RESINOUS FLOORING | Zelensky | Krishna | 1.03-D | Material Data Sheets, Safety Data Sheets (SDS) and Installation Instructions: For each resinous flooring component and system from manufacturer. | 2025-09-12 |  |  | Submitted | This is space is intentionnaly left blank for scrolling
09672-001.0 | 09672(ADD3) | RESINOUS FLOORING | Zelensky | Krishna | 1.03-E | Maintenance Data: For each resinous flooring system maintenance instructions and period system evaluation from material manufacturer. | 2025-09-12 |  |  | Submitted
09672-001.0 | 09672(ADD3) | RESINOUS FLOORING | Zelensky | Krishna | 1.03-F | Warranty: Installation and material warranty from installer and material manufacturer. | 2025-09-12 |  |  | Submitted
09910-001.0 | 09910 | PAINTING | PAINTING | Krishna/QC | 1.03-B | Shop drawings. | 2025-09-08 |  |  | AC
09910-001.0 | 09910 | PAINTING | PAINTING | Krishna/QC | 1.03-C | Product data: Include description of physical properties of coatings including solids content and ingredient analysis, VOC content, temperature resistance, typical exposures and limitations, and manufacturer's standard color chips. | 2025-09-08 |  |  | AC
| 09910 | PAINTING |  | QC | 1.03-D | Samples: Include 8-inch square draw-downs or brush-outs of topcoat finish when requested. Identify each sample as to finish, formula, color name and number and sheen name and gloss units.
09910-001.0 | 09910 | PAINTING | PAINTING | Krishna/QC | 1.03-E | Manufacturer's instructions: Submit in accordance with requirements for Product Data. | 2025-09-08 |  |  | AC
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-1 | Schedule of proposed coating materials.
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-2 | Schedule of surfaces to be coated with each coating material.
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-3 | Dehumidification and heating plan.
09960-001.0 | 09960 | HIGH-PERFORMANCE COATINGS | Product Data: Zelensky |  | 1.05-A-4 | Product data. | 2025-09-09 |  |  | Submitted
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-5-a | Quality assurance plan.
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-5-b | Qualifications of CSA.
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-5-c | CSA Reports.
| 09960 | HIGH-PERFORMANCE COATINGS |  |  | 1.05-A-5-d | CTR Reports.
| 09968 | CONCRETE REPAIR AND COATING |  |  | 1.06-A | Shop drawings.
[5 empty] | 1.06-B | Product data (general): Submit prior to start of work.
[5 empty] | 1.06-C-1 | Product data for 100 percent solids elastomeric polyurethane coating: Manufacturer’s literature including installation procedure and warranty for coating system.
[5 empty] | 1.06-C-2 | Product data for 100 percent solids elastomeric polyurethane coating: Manufacturer’s letter of declaration to maintain local permanent inventory and field technical services during coating application and Warranty period.
[5 empty] | 1.06-C-3 | Product data for 100 percent solids elastomeric polyurethane coating: Test results of product from approved material testing laboratory certifying that product meets or exceeds required physical properties.
[5 empty] | 1.06-C-4 | Product data for 100 percent solids elastomeric polyurethane coating: Certification of manufacturer’s technical services representative.
[5 empty] | 1.06-D | Testing procedure in accordance with ASTM D4263.
[5 empty] | 1.06-E | Coating repair procedures.
[5 empty] | 1.06-F-1 | Coating applicator licensing: Approval and licensing by manufacturer of 100 percent solids elastomeric polyurethane coating for coating applicator to apply this system.
[5 empty] | 1.06-G | Manufacturer's instructions: Submit in accordance with requirements for product data.
[5 empty] | 1.06-H | Manufacturer's technical representative’s field reports.
| 10100 | VISUAL DISPLAY SURFACES |  |  | 1.02-A | Product data.
[5 empty] | 1.02-B | Samples: Include minimum 6-inch square samples of selected finishes.
[5 empty] | 1.02-C | Manufacturer's installation instructions.
[5 empty] | 1.02-D | Operation and maintenance data: Include cleaning instructions.
| 10400 | SIGNAGE |  |  | 1.03-A | Product data.
[5 empty] | 1.03-B | Shop drawings.
[5 empty] | 1.03-C | Samples: Include actual materials.
[5 empty] | 1.03-D | Manufacturer's installation instructions.
| 10810 | TOILET ACCESSORIES |  |  | 1.03-A | Shop drawings.
|  | TOILET ACCESSORIES |  |  | 1.03-B | Product data: Include dimensions gauge, profiles, materials, fabrication details, manufacturer's installation instructions including setting drawings where cutouts are required, templates, substrate preparation instructions and directions for preparing cutouts for installation of accessories.
|  | TOILET ACCESSORIES |  |  | 1.03-C-1 | Special samples: Include 1 of each accessory type.
13120-001.0 | 13120(ADD3) | Pre-Engineered Structures | Pre-Engineered Structures | QC/STRUC | 1.05-A | Product Data: For all metal building system components. | 2025-07-31 | 2025-09-03 | 2025-10-03 | NCR
[5 empty] | 1.05-B | Shop Drawings.
[5 empty] | 1.05-C | Letter of Design Certification: Signed and sealed by a qualified professional engineer licensed in the State of Hawaii.
[5 empty] | 1.05-D | Welding certificates.
[5 empty] | 1.05-E | Erector Certificate: Signed by manufacturer certifying that erector complies with requirements.
[5 empty] | 1.05-F | Manufacturer certificate.
[5 empty] | 1.05-G | Fabrication shall proceed based only on approved anchor bolt plan and building shop drawings.
Formulas:
NLT Date (14 days) = [Return Date]+14
NLT Date (14 days) = 15+[Return Date]
Return Date = [Date Submitted]+14

## Elec
note: submittal status code: AN - Approved no comments, AC - Approved no comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Submitted Date | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 01783 | WARRANTIES AND BONDS |  |  | 1.02-A-1 | Submit manufacturer's warranty prior to fabrication and shipment of the item from the manufacturer's facility. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.02-A-2 | Submit manufacturer's special warranty when specified.
[5 empty] | 1.02-B | Provide consolidated warranties and bonds within 15 calendar days of Substantial Completion.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-A | Product data: Manufacturer's catalog data, details, and warranties.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-B | Shop drawings.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-C-1-a | Structural calculations.
02581-001.0 | 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES | Precast Electrical Structure Mix Design |  | 1.04-C-1-b | Manufacturer's statement of materials used for fabrication and construction, in accordance with ASTM C858, for record. | 2025-06-12 | 2025-08-20 |  | AN
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-D-1-a | Fabricator's tests for compressive strength of concrete used in structures, made in accordance with recommendations of ASTM C858.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-E-1-a | Manufacturer's current plant certification under NPCA for the structures to be supplied. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-E-1-b | Manufacturer's certification that handholes and manholes are in accordance with the requirements of ASTM C858.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-F-1 | Instructions for handling and setting structures in place.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-F-2-a | Instructions for operation and maintenance of hatches.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-G-1-a | Manufacturer's inspection reports in accordance with ASTM C1037.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-H-1 | Project record documents.
| 02581 | PRECAST ELECTRICAL HANDHOLES AND ELECTRICAL MANHOLES |  |  | 1.04-H-2 | Warranties.
16060-001.0 | 16060 | GROUNDING AND BONDING | Grounding and Bonding | Mass | 1.03-B | Product data. | 2025-09-11 |  |  | Submitted
| 16070 | HANGERS AND SUPPORTS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Delegated design submittals: Hangers and supports – General.
[5 empty] | 1.04-D-2 | Delegated design submittals: Hangers and supports – Exterior and seismic conditions.
[5 empty] | 1.04-D-3 | Delegated design submittals: Hangers and supports anchored to concrete and masonry.
| 16075 | IDENTIFICATION FOR ELECTRICAL SYSTEMS |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C-1 | Record documents: Update the conduit schedule to reflect the exact quantity of wire numbers including spares and destination points for all wires.
| 16123 | 600-VOLT OR LESS WIRES AND CABLES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Test reports.
[5 empty] | 1.03-E | Calculations.
[5 empty] | 1.03-F-1 | Cable lengths: Submit installed cable lengths using a conduit measuring tape for all 3-phase circuits.
[5 empty] | 1.03-F-2 | Cable lengths: Submit installed lengths of cable for the following single-phase circuits.
| 16124 Deleted(ADD6) | MEDIUM VOLTAGE CABLES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop Drawings.
[5 empty] | 1.03-D | Calculations.
[5 empty] | 1.03-E | Qualifications.
[5 empty] | 1.03-F | Test reports.
[5 empty] | 1.03-G-1 | Cable lengths: Submit installed cable lengths using a conduit measuring tape for medium voltage circuits
[5 empty] | 1.03-H | Record documents.
| 16125 | FIBER OPTIC CABLE AND APPURTENANCES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Installation instructions.
[5 empty] | 1.03-E-1 | Manufacturer’s representative qualifications.
[5 empty] | 1.03-F | Operation and maintenance manuals.
[5 empty] | 1.03-G | Test reports.
[5 empty] | 1.03-H | Record documents.
[5 empty] | 1.03-I | Calculations
16130-001.0 | 16130 | CONDUITS | Explosion Prof and Liquidtight Flex Conduit |  | 1.04-B | Product data. | 2025-09-10 | 2025-09-11 |  | REV
16130-001.1 | 16130 | CONDUITS | Explosion Prof and Liquidtight Flex Conduit |  | 1.04-B | Product data. | 2025-09-11 |  |  | Submitted
16130-002.0 | 16130 | CONDUITS | Rigid PVC Conduit |  | 1.04-B | Product data. | 2025-09-10 | 2025-09-22 |  | AC
16130-003.0 | 16130 | CONDUITS | PCS RIGID COATED |  | 1.04-B | Product data. | 2025-09-10 | 2025-09-22 | 2025-10-06 | NCR
16130-004.0 | 16130 | CONDUITS | Galavanized Rigid Steel |  | 1.04-B | Product data. | 2025-09-10 | 2025-09-22 | 2025-10-06 | NCR
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D | Delegated design submittals.
[5 empty] | 1.04-E | Certifications.
[5 empty] | 1.04-F | Record Documents.
[5 empty] | 1.04-G | Installation drawings.
16133-001.0 | 16133 | DUCT BANKS | Underground Marking Tape |  | 1.02-B | Markings |  | 2025-06-02 | n/a | AN
16133-002.0 | 16133 | DUCT BANKS | Shop Drawings |  | 1.02 C (1) & (2) | Product data & Shop drawings. | 2025-08-15 | 2025-09-03 | 2025-10-03 | REV
16133-002.1 | 16133 | DUCT BANKS | Shop Drawings |  | 1.02 C (1) & (2) | Product data & Shop drawings. | 2025-09-19 |  |  | Submitted
16133-003.0 | 16133 | DUCT BANKS | Conduit Spaces and Duct Seal |  | 1.02-B | Markings | 2025-09-10 |  |  | Submitted
| 16134 | BOXES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Calculations.
| 16140 | WIRING DEVICES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
| 16150 | LOW VOLTAGE WIRE CONNECTIONS |  |  | 1.03-B | Product data.
| 16210 | UTILITY COORDINATION |  |  | 1.03-B | Certification.
| 16222 | LOW VOLTAGE MOTORS UP TO 500 HORSEPOWER |  |  | 1.03-B | Submit completed motor data sheets for each motor supplied.
[5 empty] | 1.03-C | Product data.
[5 empty] | 1.03-D | Shop drawings.
[5 empty] | 1.03-E | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning.
[5 empty] | 1.03-F | Test reports.
[5 empty] | 1.03-G | Certification.
[5 empty] | 1.03-H | Calculations.
| 16232 | SINGLE DIESEL FUELED ENGINE GENERATOR ABOVE 200 KW |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D | Delegated design submittals: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850- Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F | Maintenance Service Agreement (MSA): Provide MSA including maintenance service requirements as specified in this section..
[5 empty] | 1.04-G-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-G-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-G-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-G-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-G-e | Commissioning submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-G-f | Commissioning submittals: Owner training.
[5 empty] | 1.04-H | Operation and maintenance manuals.
[5 empty] | 1.04-I | Test reports. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-J | Certificates.
[5 empty] | 1.04-K | Calculations.
| 16239 | GENERATOR CONNECTION CABINET |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop Drawings.
[5 empty] | 1.04-D-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F | Quality Control Submittals: Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
| 16251 | GENERATOR CONTROL SYSTEM FOR PARALLEL OPERATION |  |  | 1.04-B | Product data. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D | Control system narrative.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-F-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-F-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-F-e | Commissioning submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-F-f | Commissioning submittals: Owner training.
[5 empty] | 1.04-G | Start-up testing procedure.
[5 empty] | 1.04-H | Operation and maintenance manuals.
| 16262 | VARIABLE FREQUENCY DRIVES 0.50 - 50 HORSEPOWER |  |  | 1.04-A-1 | Custom prepared by the VFD manufacturer and specific for the equipment furnished.
[5 empty] | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1-a | Delegated design submittals: For wall mounted equipment weighing 125 pounds or more and floor mounted equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-D-2-a | Delegated design submittals: For outdoor installations: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.04-G | Operation and maintenance manuals.
[5 empty] | 1.04-H | Test forms and reports.
[5 empty] | 1.04-I | Manufacturer’s field reports.
[5 empty] | 1.04-J | Record Documents.
| 16265 | REDUCED HARMONIC VARIABLE FREQUENCY DRIVES |  |  | 1.05-A-1 | Custom prepared by the VFD manufacturer and specific for the equipment furnished.
[5 empty] | 1.05-B | Product data.
[5 empty] | 1.05-C | Shop Drawings.
[5 empty] | 1.05-D | Calculations.
[5 empty] | 1.05-E-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.05-F | Installation instructions.
[5 empty] | 1.05-G-1 | Quality Control Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.05-G-2 | Quality Control Submittals: Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-G-3 | Quality Control Submittals: Manufacturer’s Certificate of Installation as specified in Section 01756 - Commissioning.
[5 empty] | 1.05-G-4 | Quality Control Submittals: Test reports.
[5 empty] | 1.05-G-5 | Quality Control Submittals: Report listing the setting of VFD adjustable parameters and their values after start-up.
[5 empty] | 1.05-H-1 | Owner Training Submittals: As specified in Section 01756 - Commissioning.
[5 empty] | 1.05-I | Certifications.
[5 empty] | 1.05-J | Operation and maintenance manuals.
| 16272 | DRY-TYPE TRANSFORMERS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C-1-a | Delegated design submittals: For equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-C-2-a | Delegated design submittals: For outdoor installations: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-D | Installation instructions.
[5 empty] | 1.04-E | Furnish commissioning submittals specified in this Section as specified in Section 01756 - Commissioning.
| 16281 | HARMONIC FILTER |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Delegated design submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-F-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-F-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-F-e | Commissioning submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-F-f | Commissioning submittals: Owner training.
[5 empty] | 1.04-G | Calculations.
[5 empty] | 1.04-H | Test forms and reports.
[5 empty] | 1.04-I | Record documents.
[5 empty] | 1.04-J | Operation and maintenance manuals.
| 16285 | SURGE PROTECTIVE DEVICES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-D-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.03-E | Operation and maintenance manuals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 16290 | ELECTRICAL POWER MONITORING |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.03-D | Operation and maintenance manuals.
[5 empty] | 1.03-E | Configuration files and reports.
| 16305 | ELECTRICAL SYSTEM STUDIES |  |  | 1.03-B | Initial studies and reports.
| 16305 | ELECTRICAL SYSTEM STUDIES |  |  | 1.03-C | Delegated Design final studies and reports.
16305-001.0 | 16305 | ELECTRICAL SYSTEM STUDIES | Quality Assurance |  | 1.05 | Submit the credentials of the individual(s) performing the study and the individual in responsible charge of the study. | 2025-08-25 | 2025-09-11 | n/a | AN | This is space is intentionnaly left blank for scrolling
| 16305 | ELECTRICAL SYSTEM STUDIES |  |  | 1.03-E | Submit course outline for Owner’s training.
| 16411 | DISCONNECT SWITCHES |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Installation instructions.
| 16412 | LOW VOLTAGE MOLDED CASE CIRCUIT BREAKERS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.04-D-1-a | Delegated design submittals: For wall mounted equipment weighing 125 pounds or more and floor mounted equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-D-2-a | Delegated design submittals: For outdoor installations: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
| 16413 | LOW VOLTAGE INSULATED CASE CIRCUIT BREAKERS |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C-1 | Owner Training Submittals: As specified in Section 01756 - Commissioning.
| 16422 | MOTOR STARTERS |  |  | 1.04-A-1 | Submit motor starter data with equipment submittal.
[5 empty] | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1-a | Delegated design submittals: For wall mounted equipment weighing 125 pounds or more and floor mounted equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-D-2-a | Delegated design submittals: For outdoor installations: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Operation and maintenance manuals.
| 16433 | SERVICE ENTRANCE AUTOMATIC TRANSFER EQUIPMENT |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop Drawings.
[5 empty] | 1.04-D-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-a | Commissioning Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-b | Commissioning Submittals: Certificates.
[5 empty] | 1.04-F-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-F-d | Commissioning Submittals: Test Reports.
[5 empty] | 1.04-F-e | Commissioning Submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-F-f | Commissioning Submittals: Owner Training.
[5 empty] | 1.04-G-1 | Utility Coordination: Submit certifications as specified in Section 16210 - Utility Coordination.
[5 empty] | 1.04-G-2 | Utility Coordination: Submit table of utility required parameters and settings for control functions.
[5 empty] | 1.04-H | Operation and maintenance manuals.
| 16441 | GROUP-MOUNTED CIRCUIT BREAKER SWITCHBOARDS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Delegated design submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-F-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-F-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-F-e | Commissioning submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-F-f | Commissioning submittals: Owner training.
[5 empty] | 1.04-G | Operating and maintenance manuals.
[5 empty] | 1.04-H | Calculations.
| 16442 | INDIVIDUALLY-MOUNTED CIRCUIT BREAKER SWITCHBOARDS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop Drawings.
[5 empty] | 1.04-D-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-F-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-F-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-F-e | Commissioning submittals: Manufacturer’s representatives field notes and data.
[5 empty] | 1.04-F-f | Commissioning submittals: Owner training.
[5 empty] | 1.04-G | Operation and maintenance manuals.
| 16444 | LOW VOLTAGE MOTOR CONTROL CENTERS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1-a | Delegated design submittals: For equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.04-G | Operation and maintenance manuals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-H | Test forms and reports.
[5 empty] | 1.04-I | Record Documents.
[5 empty] | 1.04-J | Calculations.
| 16445 | PANELBOARDS |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1-a | Delegated design submittals: For equipment installed in structures designated as seismic design category C, D, E, or F: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-G | Operations and maintenance manual.
[5 empty] | 1.04-H | Calculations.
| 16472 | PACKAGED POWER SUPPLY CENTER |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop Drawings.
[5 empty] | 1.04-D | Calculations.
[5 empty] | 1.04-E-1 | Delegated Design Submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-F | Installation instructions.
[5 empty] | 1.04-G-1 | Quality Control Submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-G-2 | Quality Control Submittals: Manufacturer’s Certificate of Source Testing as specified in Section 01756 - Commissioning.
[5 empty] | 1.04-G-3 | Quality Control Submittals: Test reports.
[5 empty] | 1.04-H | Operations and maintenance manual.
| 16491 | TRANSFER SWITCHES |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Delegated design submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Installation instructions.
[5 empty] | 1.04-F-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.04-F-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.04-G | Operation and maintenance manuals.
[5 empty] | 1.04-H | Calculations.
[5 empty] | 1.04-I-a | Commissioning submittals: Manufacturer’s representative qualifications.
[5 empty] | 1.04-I-b | Commissioning submittals: Certificates.
[5 empty] | 1.04-I-c | Commissioning Submittals: Test Plans.
[5 empty] | 1.04-I-d | Commissioning submittals: Test Reports.
[5 empty] | 1.04-I-e | Commissioning submittals: Owner training.
| 16510 | LIGHTING: LED LUMINAIRES |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C-1 | Delegated design submittals: Project-specific calculations with anchoring and bracing details based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-D | Record documents.
| 16670 | LIGHTNING PROTECTION |  |  | 1.03-B | Product data.
[5 empty] | 1.03-C | Shop drawings.
[5 empty] | 1.03-D | Certificates.
[5 empty] | 1.03-E | Record Documents.
| 16710 | FIRE ALARM AND SMOKE DETECTION SYSTEM |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C-1 | Delegated Design Submittals: Fire detection system block diagram.
[5 empty] | 1.04-C-2 | Delegated Design Submittals: System power and battery charts with performance graphs and voltage drop calculations to ensure that system will operate per the specified backup time periods and under all voltage conditions per UL and NFPA standards.
[5 empty] | 1.04-C-3 | Delegated Design Submittals: System layout on floor plan drawings, drawn to scale using AutoCAD software.
[5 empty] | 1.04-C-4 | Delegated Design Submittals: Location diagrams for all ventilation duct mounted smoke detectors and corresponding ventilation system shutdown interlock.
[5 empty] | 1.04-C-5 | Delegated Design Submittals: Fire alarm system input-output point list.
[5 empty] | 1.04-C-6 | Delegated Design Submittals: Sequence of Operation in either an input/output matrix or narrative form.
[5 empty] | 1.04-D | Operating and Maintenance data as specified in Section 01782 - Operation and Maintenance Manuals. Manufacturer's installation instructions.
[5 empty] | 1.04-E | Designer, manufacturer, and installer qualifications.
[5 empty] | 1.04-F | Test reports indicating satisfactory completion of required tests and inspections.
| 16950 | FIELD ELECTRICAL ACCEPTANCE TESTS |  |  | 1.03-B | Copper Ethernet test form.
[5 empty] | 1.03-C | Manufacturers’ testing procedures.
[5 empty] | 1.03-D | Test report.
[5 empty] | 1.03-E | Test data records.
[5 empty] | 1.03-F | Testing laboratory qualifications.
[5 empty] | 1.03-G-1 | Division of responsibilities: Submit a list identifying who is responsible for performing each portion of the testing.
| 16990 | CONDUIT SCHEDULE |  |  | N/A
| 16990.01.02 | CONDUIT SCHEDULE AREA 01 & 02 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.03 | CONDUIT SCHEDULE AREA 03 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.05.06 | CONDUIT SCHEDULE AREA 05 & 06 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.07 | CONDUIT SCHEDULE AREA 07 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.08.09 | CONDUIT SCHEDULE AREA 08 & 09 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.10 | CONDUIT SCHEDULE AREA 10 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.11 | CONDUIT SCHEDULE AREA 11 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.11AA | CONDUIT SCHEDULE AREA 11AA |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.12 | CONDUIT SCHEDULE AREA 12 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.13 | CONDUIT SCHEDULE AREA 13 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.14 | CONDUIT SCHEDULE AREA 14 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.19 | CONDUIT SCHEDULE AREA 19 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 16990.21 | CONDUIT SCHEDULE AREA 21 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.22 | CONDUIT SCHEDULE AREA 22 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
| 16990.25 | CONDUIT SCHEDULE AREA25 |  |  | 1.01-A | Conduit requirements: As defined in Section 16050 and Section 16130.
[5 empty] | 1.01-B | Cable requirements: As defined in Section 16050 and Section 16123.
This is space is intentionnaly left blank for scrolling
Formulas:
NLT Date (14 days) = [Return Date]+14
NLT Date (14 days) = 30+[Return Date]

## I&C
note: submittal status code: AN - Approved no comments, AC - Approved no comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 17050 | COMMON WORK RESULTS FOR PROCESS CONTROL AND INSTRUMENTATION SYSTEMS |  |  | 1.05-B-1 | Control Panel Drawings. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.05-B-2 | Schematics and Wiring Diagrams.
[5 empty] | 1.05-B-3 | Loop drawings.
[5 empty] | 1.05-B-4 | PLC I/O List.
[5 empty] | 1.05-B-5 | Control Descriptions.
[5 empty] | 1.05-B-6 | Instrument Datasheets.
[5 empty] | 1.05-B-7 | Instrument Installation Drawings.
[5 empty] | 1.05-B-8 | Product data.
[5 empty] | 1.05-B-9-a | Commissioning Submittals: As specified in Section 01756 - Commissioning. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.05-B-9-b | Commissioning Submittals: Manufacturer representative qualifications.
[5 empty] | 1.05-B-9-c | Commissioning Submittals: Manufacturer certificates.
[5 empty] | 1.05-B-9-d | Commissioning Submittals: Test plans.
[5 empty] | 1.05-B-9-e | Commissioning Submittals: Test reports.
[5 empty] | 1.05-B-9-f | Commissioning Submittals: Owner Training Submittals.
[5 empty] | 1.05-B-9-g | Commissioning Submittals: Operation and maintenance manuals.
| 17100 | CONTROL STRATEGIES |  |  | 1.04-A | As specified in Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
| 17101A | SPECIFIC CONTROL STRATEGIES - SEPTAGE RECEIVING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101B | SPECIFIC CONTROL STRATEGIES - SCREENING AND SCREENINGS HANDLING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101C | SPECIFIC CONTROL STRATEGIES - GRIT REMOVAL AND HANDLING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101D | SPECIFIC CONTROL STRATEGIES - INFLUENT SAMPLING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101E | SPECIFIC CONTROL STRATEGIES - HEADWORKS ODOR CONTROL |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Section 01330 - Submittal Procedures, Section 17050 - Common Work Results for Process Control and Instrumentation Systems, Section 11395D - Headworks Odor Control System, and Section 15832 - Odor Control Fans.
[5 empty] | 1.04-B | Loop number and title.
| 17101F | SPECIFIC CONTROL STRATEGIES - HEADWORKS DRAINAGE |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101G | SPECIFIC CONTROL STRATEGIES - PRIMARY SEDIMENTATION TANKS |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101H | SPECIFIC CONTROL STRATEGIES - VENTILATION SYSTEM |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101I | SPECIFIC CONTROL STRATEGIES - SECONDARY CLARIFIERS |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101J | SPECIFIC CONTROL STRATEGIES - BLEND TANKS |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101K | SPECIFIC CONTROL STRATEGIES - BLEND TANKS ODOR CONTROL |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101L | SPECIFIC CONTROL STRATEGIES - SOLIDS ODOR CONTROL |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101M | SPECIFIC CONTROL STRATEGIES - DIGESTION |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101N | SPECIFIC CONTROL STRATEGIES - DIGESTER GAS HANDLING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101O | SPECIFIC CONTROL STRATEGIES - DIGESTED SLUDGE TRANSFER |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101P(ADD3) | SPECIFIC CONTROL STRATEGIES - THICKENING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101Q(ADD3) | SPECIFIC CONTROL STRATEGIES - DEWATERING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents.
[5 empty] | 1.04-B | Loop number and title.
| 17101R(ADD3) | SPECIFIC CONTROL STRATEGIES - CAKE LOADING |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101S | SPECIFIC CONTROL STRATEGIES - DISINFECTION |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101T(ADD4) | SPECIFIC CONTROL STRATEGIES - UTILITY WATER |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101U | SPECIFIC CONTROL STRATEGIES - RETURN FLOW PUMP STATION |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101V | SPECIFIC CONTROL STRATEGIES - WASTE SECONDARY SLUDGE (WSS) PUMP |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Loop number and title.
| 17101W | SPECIFIC CONTROL STRATEGIES - GENERATOR |  |  | 1.04-A | Develop detailed loop descriptions based on the information in the Contract Documents and submit as specified in Section 01330 - Submittal Procedures, Section 17050 - Common Work Results for Process Control and Instrumentation Systems, Section 16232 – Single Diesel Fueled Engine Generator Above 200 kW, and Section 16251 – Generator Control System for Parallel Operation.
[5 empty] | 1.04-B | Loop number and title.
| 17201 | LEVEL MEASUREMENT: SWITCHES |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17206 | LEVEL MEASUREMENT: ULTRASONIC |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
[5 empty] | 1.03-C-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17208 | LEVEL MEASUREMENT: RADAR PULSE TIME OF FLIGHT (PTOF) |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-B-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17301 | FLOW MEASUREMENT: SWITCHES |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
| 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS
17302-001.0 | 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS | Product Data(Dynatek) | Mark | 1.03-B-1 | Chart of the measurement error from zero to maximum measured volumetric flow range indicated in data sheets. | 2025-09-18
17302-001.0 | 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS | Product Data(Dynatek) | Mark | 1.03-B-2 | Indication of all input parameters and their values used in the calculations. | 2025-09-18
| 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS |  |  | 1.03-C1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
17302.001.0 | 17302 | FLOW MEASUREMENT: MAGNETIC FLOWMETERS |  |  | 1.03-C-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17305 | FLOW MEASUREMENT: THERMAL MASS |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Design calculations.
[5 empty] | 1.03-C | Provide complete documentation covering the traceability of all calibration instruments. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.03-D-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-D-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17307 | FLOW MEASUREMENT: ULTRASONIC TRANSIT TIME - NON-INTRUSIVE |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17316 | FLOW MEASUREMENT: ROTAMETERS (VARIABLE AREA FLOWMETERS) |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 and 17050 - Common Work Results for Process Control and Instrumentation Systems.
| 17401 | PRESSURE/VACUUM MEASUREMENT: DIAPHRAGM AND ANNULAR SEALS |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Product data.
| 17402 | PRESSURE/VACUUM MEASUREMENT: INSTRUMENT VALVES |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-B-1 | Product data.
[5 empty] | 1.04-B-2 | Shop drawings.
| 17403 | PRESSURE/VACUUM MEASUREMENT: SWITCHES |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Product data.
| 17404 | PRESSURE/VACUUM MEASUREMENT: GAUGES |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Product data.
| 17405 | PRESSURE/VACUUM MEASUREMENT: DIRECT |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17407 | PRESSURE MEASUREMENT: SUBMERSIBLE |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures, and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17409 | PRESSURE/VACUUM MEASUREMENT: MANOMETERS |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17504 | ANALYZERS: GAS MONITORS |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17505 | ANALYZERS: RESIDUAL CHLORINE |  |  | 1.03-A | Furnish Submittals as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of calibration instruments.
[5 empty] | 1.03-C-1 | Furnish commissioning Submittals listed below, as specified in this Section, and Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning Submittals listed below, as specified in this Section, and Section 01756 - Commissioning: Owner training.
| 17522 | ANALYZERS: TOTAL SUSPENDED SOLIDS (TSS) |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
[5 empty] | 1.03-C-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17524 | ANALYZERS: SLUDGE BLANKET |  |  | 1.03-A | Furnish Submittals as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of calibration instruments.
[5 empty] | 1.03-C-1 | Furnish commissioning Submittals listed below, as specified in this Section, and Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning Submittals listed below, as specified in this Section, and Section 01756 - Commissioning: Owner training.
| 17604 | TEMPERATURE MEASUREMENT: RTD |  |  | 1.03-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
| 17622 | WEIGHT MEASUREMENT: PLATFORM SCALE AND LOAD CELLS |  |  | 1.03-A | Furnish Submittals as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-B | Provide complete documentation covering the traceability of all calibration instruments.
[5 empty] | 1.03-C-1 | Furnish commissioning Submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-C-2 | Furnish commissioning Submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
| 17710 | CONTROL SYSTEMS: PANELS, ENCLOSURES, AND PANEL COMPONENTS |  |  | 1.04-A | Provide submittals as specified in Section 01330 - Submittal Procedures and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B-1 | Provide a control panel hardware submittal for each control panel/enclosure being provided on this project: Product data.
[5 empty] | 1.04-B-2 | Provide a control panel hardware submittal for each control panel/enclosure being provided on this project: Shop drawings.
[5 empty] | 1.04-B-3 | Provide a control panel hardware submittal for each control panel/enclosure being provided on this project: Calculations.
[5 empty] | 1.04-C-1-a | Seismic design: Seismic panel construction: Provide seismic design calculations and installation details for anchorage of all panels, enclosures, consoles, etc. to meet seismic requirements in Section 01850 - Design Criteria.
[5 empty] | 1.04-C-1-b | Seismic design: Seismic panel construction: For floor-mounted freestanding panels weighing 200 pounds or more (assembled, including contents), submit calculations, data sheets, and other information to substantiate that panel, base, and framing meet minimum design strength requirements and seismic requirements as specified in Section 01850 - Design Criteria.
| 17712 | CONTROL SYSTEMS: UNINTERRUPTIBLE POWER SUPPLIES 10 KVA AND BELOW |  |  | 1.05-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.05-B | Product data.
[5 empty] | 1.05-C | Shop drawings.
[5 empty] | 1.05-D | Calculations.
[5 empty] | 1.05-E-1 | Record documents: Provide Record Drawings of installed unit(s) including layout and wiring.
[5 empty] | 1.05-F | Manufacturer’s field reports.
[5 empty] | 1.05-G | Operation and maintenance manuals.
| 17713 | CONTROL SYSTEMS: COMPUTER CONSOLES |  |  | 1.04-A | Furnish submittals as specified in Section 01330 - Submittal Procedures. and Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Shop drawings.
[5 empty] | 1.04-C | Bill of materials with a detailed description of components and equipment data sheets.
[5 empty] | 1.04-D | Calculations.
[5 empty] | 1.04-E | Drawing plan.
[5 empty] | 1.04-F | Console installation plan.
[5 empty] | 1.04-G-1 | Delegated design submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-H | Installation instructions.
| 17720 | CONTROL SYSTEMS: PROGRAMMABLE LOGIC CONTROLLERS |  |  | 1.05-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
? |  |  |  |  | 1.05-B | Product data.
[5 empty] | 1.05-C | Calculations.
[5 empty] | 1.05-D | Product data.
[5 empty] | 1.05-E | Control logic.
[5 empty] | 1.05-F | Provide application software for the specific Project process requirements.
| 17721 | CONTROL SYSTEMS: LOCAL OPERATOR INTERFACE (LOI) |  |  | 1.05-A | Furnish submittals in accordance with Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.05-B | Product data.
[5 empty] | 1.05-C | Shop drawings.
[5 empty] | 1.05-D | Operation and maintenance manuals.
[5 empty] | 1.05-E | Record documents.
| 17730 | CONTROL SYSTEMS: PCS COMPUTER EQUIPMENT |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Shop drawings.
| 17733 | CONTROL SYSTEMS: NETWORK MATERIALS AND EQUIPMENT |  |  | 1.04-B | Product data.
[5 empty] | 1.04-C | Shop drawings.
[5 empty] | 1.04-D-1 | Delegated design submittals: Provide project-specific calculations based on support conditions and requirements to resist loads specified in Section 01850 - Design Criteria.
[5 empty] | 1.04-E | Calculations.
[5 empty] | 1.04-F | Test reports.
[5 empty] | 1.04-G | Operating manuals. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-H | Record drawings.
| 17762 | CONTROL SYSTEMS: PCS SOFTWARE |  |  | 1.04-A | Furnish submittals as specified in Sections 01330 - Submittal Procedures and 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.04-B | Remote alarm database.
[5 empty] | 1.04-D-1-b-1 | Graphic displays.
[5 empty] | 1.04-D-1-b-2 | Overview screens.
[5 empty] | 1.04-D-1-b-3 | Process screens.
[5 empty] | 1.04-D-1-b-4 | Setpoint screens. |  |  |  |  | This is space is intentionnaly left blank for scrolling
[5 empty] | 1.04-D-1-b-5 | Faceplates/popups.
[5 empty] | 1.04-D-1-b-6 | Trend displays.
[5 empty] | 1.04-D-1-b-7 | Alpha numeric displays.
[5 empty] | 1.04-D-1-b-8 | Alarm displays.
[5 empty] | 1.04-D-1-b-9 | Summary screens.
[5 empty] | 1.04-D-1-b-10 | Diagnostic screens.
[5 empty] | 1.04-D-1-b-11 | Network status screens.
[5 empty] | 1.04-E | Pre-acceptance test documentation as specified in the Sequencing article of this Section.
[5 empty] | 1.04-F | Operator's reference manual.
[5 empty] | 1.04-G-1 | Review meeting minutes submittals: Graphics review meeting.
[5 empty] | 1.04-G-2 | Review meeting minutes submittals: Report review meeting.
[5 empty] | 1.04-G-3 | Review meeting minutes submittals: Alarm review meeting.
| 17765 | CONTROL SYSTEMS: PROGRAMMING REQUIREMENTS |  |  | 1.02-B-1-a-2-a | Graphic displays.
[5 empty] | 1.02-B-1-a-2-b | Trend displays.
[5 empty] | 1.02-B-1-a-2-c | Alpha numeric displays.
[5 empty] | 1.02-B-1-a-2-d | Alarm displays
[5 empty] | 1.02-B-2 | Operator's reference manual.
[5 empty] | 1.02-B-3-a | Review meeting minutes submittals: Graphics review meeting.
| 17903 | SCHEDULES: I/O LIST |  |  | N/A
| 17950 | COMMISSIONING FOR INSTRUMENTATION AND CONTROLS |  |  | 1.03-B-1 | Reference additional detailed test submittal scheduling and prerequisite requirements as specified in the Sequencing article of Section 17050 - Common Work Results for Process Control and Instrumentation Systems.
[5 empty] | 1.03-C | Overall test plan.
[5 empty] | 1.03-D | Test procedures.
[5 empty] | 1.03-E | Test forms.
[5 empty] | 1.03-F-1 | FAT procedure additional minimal requirements: Prepare and submit a FAT procedure .
[5 empty] | 1.03-G | Details on the simulator construction, components, and operation.
[5 empty] | 1.03-H-1 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Manufacturer’s representative qualifications.
[5 empty] | 1.03-H-2 | Furnish commissioning submittals listed below and specified in this Section as specified in Section 01756 - Commissioning: Owner training.
[5 empty] | 1.03-I | Test reports.
[5 empty] | 1.03-J-1-a | Application software: Finalized fully annotated copy of programmed PLC logic in its native format.
[5 empty] | 1.03-J-1-b | Application software: Cross-referenced index of all PLC registers or points.
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling

## QC
note: submittal status code: S - submited AN - Approved no comments, AC - Approved with comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Assignee | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
01450-001.0 | 1450 | Quality Control | Trueform Independent Lab Qualifications | MC | 1.09 | Independent Lab Concrete Testing Trueform LLC | 2025-07-09 | 2025-07-31 | 2025-08-30 | REV | This is space is intentionnaly left blank for scrolling
01450-001.1 | 1450 | Quality Control | note: Mark Grant to speak with Carollo for allowance | MC | 1.09 | Resubmittal for Trueform LLC Qualifcations | 2025-08-29 | 2025-09-17 | 2025-10-17 | REV
01450-001.2 | 1450 | Quality Control | HMA Independent Lab Qualification | MC | 1.09 | Resubmittal for ASTM Qualifcations | 2025-09-24 | 2025-09-25 |  | REV
01450-001.2 | 1450 | Quality Control | HMA Independent Lab Qualification | MC | 1.09 | Resubmittal for ASTM Qualifcations | 2025-09-25 |  |  | In Progress
| 01452(ADD3) | MOISTURE VAPOR AND ALKALINITY TEST |  |  | 1.04-A | Testing Agency qualifications.
| 01452(ADD3) | MOISTURE VAPOR AND ALKALINITY TEST |  |  | 1.04-B | Report all test results in chart form listing test dates, start/stop time, start/stop weight, weight gain in grams, moisture vapor emission value and alkalinity levels.
| 01452(ADD3) | MOISTURE VAPOR AND ALKALINITY TEST |  |  | 1.04-C | List test locations on chart and show same on 8-1/2 inch x 11-inch site map (when such map is made available to testing agency).
| 01452(ADD3) | MOISTURE VAPOR AND ALKALINITY TEST |  |  | 1.04-D | Deliver results for distribution to Contracting Officer and General Contractor.
| 01455 | REGULATORY QUALITY ASSURANCE |  |  | 1.05-A | Contractor shall submit special certifications for designated seismic systems and wind load. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 01455 |  |  |  | 1.05-B | Contractor shall schedule and coordinate the submittal of Special Inspection reports and test results prepared by others.
01460-002.0 | 1460 | CONTRACTOR QUALITY CONTROL - Manager Qualification |  | MM |  | Mark McCarthy Added to QC team as QCM | 2025-05-19 | 2025-09-03 | 2025-10-03 | NCR
01460-001.0 | 01460 | CONTRACTOR QUALITY CONTROL PLAN |  | CQC Team | 1.02-A | Qualifications of the Contractor’s Quality Control (CQC) Plan Manager. | 2025-04-07 | 2025-04-22 |  | L
| 01460 |  |  |  | 1.02-B | Contractor’s Quality Control Plan | 2025-04-07 | 2025-04-22
| 01460 |  |  |  | 1.02-C | Contractor’s Daily Quality Control Report | 2025-04-07 | 2025-04-22
| 01460 |  |  |  | 1.02-D | Daily Inspection Report | 2025-04-07 | 2025-04-22
01460-001.1 | 01460 | CONTRACTOR QUALITY CONTROL PLAN |  | CQC Team | 1.02-A | Qualifications of the Contractor’s Quality Control (CQC) Plan Manager. | 2025-04-24 | 2025-05-09 |  | L
| 01460 |  |  |  | 1.02-B | Contractor’s Quality Control Plan | 2025-04-24 | 2025-05-09
| 01460 |  |  |  | 1.02-C | Contractor’s Daily Quality Control Report | 2025-04-24 | 2025-05-09
| 01460 |  |  |  | 1.02-D | Daily Inspection Report | 2025-04-24 | 2025-05-09
01460-001.2 | 01460 | CONTRACTOR QUALITY CONTROL PLAN |  | CQC Team | 1.02-A | Qualifications of the Contractor’s Quality Control (CQC) Plan Manager. | 2025-05-09 | FIO |  | L
| 01460 |  |  |  | 1.02-B | Contractor’s Quality Control Plan | 2025-05-09 | FIO
| 01460 |  |  |  | 1.02-C | Contractor’s Daily Quality Control Report | 2025-05-09 | FIO
| 01460 |  |  |  | 1.02-D | Daily Inspection Report | 2025-05-09 | FIO
| 01759 | WATER LEAKAGE TEST FOR CONCRETE STRUCTURES |  | QC/Struc | 1.03-B | Tests and evaluation reports.
| 01759 | WATER LEAKAGE TEST FOR CONCRETE STRUCTURES |  | QC/ Struc | 1.03-C-1 | Testing plan for each structure, or portion thereof, required to be tested.
| 01770 | CLOSEOUT PROCEDURES |  | QC | 1.08-A-1 | Punch list of items to be completed or corrected with the request for issuance of Substantial Completion.
| 01770 |  |  | QC | 1.08-A-2 | Evidence of Compliance with Requirements of Governing Authorities.
| 01770 |  |  | QC | 1.08-A-3 | Project Record Documents.
| 01770 |  |  | QC | 1.08-A-4 | Approved Operation and Maintenance Manuals.
| 01770 |  |  | QC | 1.08-A-5 | Approved Warranties and Bonds.
| 01770 |  |  | QC | 1.08-A-6 | Keys and Keying Schedule.
| 01770 |  |  | QC | 1.08-A-7 | Completed contract requirements for commissioning and process start-up.
| 01770 |  |  | QC | 1.08-B-1 | Punch list of items have been completed and Engineer and Owner are satisfied that all deficiencies are corrected.
| 01770 |  |  | QC | 1.08-B-2 | Evidence of Payment and Release of Liens or Stop Payment Notices as outlined in Conditions of the Contract.
| 01770 |  |  | QC | 1.08-B-3 | Release of claims as outlined in Conditions of the Contract.
| 01770 |  |  | QC | 1.08-B-4 | Submit certification of insurance for products and completed operations, as specified in the General Conditions.
| 01770 |  |  | QC | 1.08-B-5 | Final statement of accounting.
| 01770 |  |  | QC | 1.08-B-6 | Submit Final (As-Built) Schedule as specified in Section 01321 - Schedules and Reports.
| 01770 |  |  | QC | 1.08-B-7 | Submit final Project Record (As-Built) documents.
| 01784 | ASSET MANAGEMENT DATA SPREADSHEET |  | QC | 1.02-C | The Contractor shall submit 2 CDs with the completed electronic spreadsheet in Excel format and 10 hard copies.
| 01784 |  |  | QC | 1.02-D | Contractor shall use one equipment as an example to demonstrate how the information is obtained and entered into the spreadsheet.
| 01784 |  |  | QC | 1.02-E | The Asset Management Data Spreadsheet shall be completed in its entirety except the warranty start date and submitted prior to the Reliability Acceptance Testing (RAT).
| 01784 |  |  | QC | 1.02-F | The Final Asset Management Data Spreadsheet submittal with the warranty start date shall be submitted to the County prior to acceptance of the project. The Contractor shall submit 1 CD in Excel format and 2 hard copies for this final submittal.
| 03055 | ADHESIVE-BONDED REINFORCING BARS AND ALL THREAD RODS IN CONCRETE |  | QC/Struc | 1.04-C | Inspection and testing reports.
| 03150 | CONCRETE ACCESSORIES |  | Struc | 1.03-B-1 | Sample: Polyvinyl chloride waterstop.
| 03150 | CONCRETE ACCESSORIES |  | QC | 1.04 A | Mock-up
| 03154 | HYDROPHILIC RUBBER WATERSTOP |  | QC/Struc | 1.02-A-3-a | Minimum 6-inch long samples of each type of waterstop to be used if requested by the Engineer.
| 03200 | CONCRETE REINFORCING |  | QC/Struc | 1.04-D-1 | Bar supports/wire reinforcement supports: Samples of each type of chair and bolster proposed for use. Submit with letter stating where each type will be used.
| 03200 | CONCRETE REINFORCING |  | QC/Struc | 1.04-D-2 | Precast concrete bar supports: Samples of each type of precast support proposed for use. Submit with letter stating where each will be used.
| 03200 | CONCRETE REINFORCING |  | QC | 1.04-I-1 | Field quality control and inspection reports.
| 03200 | CONCRETE REINFORCING |  | QC | 1.04-I-2 | Field quality assurance special inspection and testing reports.
| 03300 | CAST-IN-PLACE-CONCRETE |  | STRUC | 1.05-F-1 | Current NRMCA certification for all plants and trucks that will be used to supply concrete.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-G-1 | Truck batch tickets for each load of concrete delivered to the site, whether accepted or rejected.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-G-2 | Concrete supplier's quality control plan.
| 03300 | CAST-IN-PLACE-CONCRETE |  | QC | 1.05-H-2 | Contractor's reports of field quality control testing.
| 03600 | GROUTING |  | QC/STRUC | 1.03-C-2 | Material submittals. Non-shrink epoxy grout: Quality control tests results.
| 03600 | GROUTING |  | Qc/Struc | 1.03-D-2 | Non-shrink grout: Quality control tests results.
| 03703 | THERMAL CONTROL OF CONCRETE |  | STRUC | 1.03-A | Product data.
|  |  |  | STRUC | 1.03-B | Thermal Control Plan.
|  |  |  | STRUC | 1.03-C | Temperature Monitoring Program.
|  |  |  | STRUC | 1.03-D | Temperature monitoring data.
|  |  |  | STRUC | 1.03-E | Layout of cooling pipe system, if used, showing pipe sizes and material type, connections, location, spacing, method of support, and system for monitoring temperature of water in cooling pipes.
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | QC | 1.03-C-1 | Quality control submittals: Certificates of Compliance.
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | QC | 1.03-C-2 | Quality control submittals: Manufacturer's Instructions.
03931-001.0 | 03931 | EPOXY INJECTION SYSTEM |  | Struc | 1.03-D-1 | Special procedure submittals: Protection plan for surrounding areas and non-cementitious surfaces.
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC | 1.03-C-1 | Quality control submittals: Certificates of Compliance.
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC | 1.03-C-2 | Quality control submittals: Manufacturer's Instructions.
| 03933 | HYDROPHILIC AND HYDROPHOBIC FOAM POLYURETHANE RESIN INJECTION SYSTEM |  | QC/STRUC | 1.03-C-3 | Quality control submittals: Protection plan for surrounding areas and non-cementitious surfaces. |  |  |  |  | This is space is intentionnaly left blank for scrolling
|  |  |  | QC/Struc | 1.04-B-1 | Quality control submittals: Detailed instructions for special inspection to comply with the building code specified in Section 01410 - Regulatory Requirements.
|  |  |  | STRUC | 1.04-B-2 | Evaluation Report confirming that the product complies with the requirements of ICC-ES AC58.
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
Formulas:
NLT Date (14 days) = 30+[Return Date]

## Commissioning
note: submittal status code: AN - Approved no comments, AC - Approved no comments, AS - Approved Correct and Resubmit, NCR - Not Approved Correct Resubmit, NR - Not Approved Rejected, RA - Reciept Acknowledge, RC - Reciept with Comments, L - Living Document or continously submitted
Submittal No. | Spec Section Number | Specification Title | Submittal Title | Paragraph No. | Description | Date Submitted | Return Date | NLT Date (14 days) | Status | Key | Accepted | Resubmit | Submited
| 01756 | COMMISSIONING |  | 1.05-A-1 | Organization chart for conducting start-up and testing. |  |  |  |  | This is space is intentionnaly left blank for scrolling
01756-001.0 | 01756 | COMMISSIONING |  | 1.05-A-2 | Description of previous experience on similar projects for the designated TSC. Include list of references complete with phone numbers. | 2025-05-27 | 2025-08-14 | 2025-08-29 | NCR
01756-002.0 | 01756 | COMMISSIONING |  | 3.13-B | Contractor Designated Training Coordinator | 2025-05-28 | 2025-08-14 |  | AC
| 01756 | COMMISSIONING |  | 1.05-A-3 | Detailed start-up and testing plan with schedule signed by the TSC, for each equipment item and system.
| 01756 | COMMISSIONING |  | 1.05-A-4 | An overall schedule and subsequent updates, presenting the Contractor’s plan for testing the equipment and systems installed under this contract.
| 01756 | COMMISSIONING |  | 1.05-A-5 | A detailed schedule establishing the expected time period.
| 01756 | COMMISSIONING |  | 1.05-A-6 | A summary of the Quality Assurance Manager’s qualifications.
| 01756 | COMMISSIONING |  | 1.05-A-7 | The original and 3 copies of all records produced during the testing program.
| 01756 | COMMISSIONING |  | 1.05-A-8 | Acceptance criteria required to release equipment and systems for start-up. |  |  |  |  | This is space is intentionnaly left blank for scrolling
| 01756 | COMMISSIONING |  | 1.05-A-9 | Manufacturer’s certification of proper installation of equipment before testing begins.
| 01756 | COMMISSIONING |  | 1.05-A-10 | Operation and maintenance instruction manual for each equipment item and system to be tested as specified in Section 01782.
| 01756 | COMMISSIONING |  | 1.05-B-1-a | All testing procedures.
| 01756 | COMMISSIONING |  | 1.05-B-1-b | All testing forms.
| 01756 | COMMISSIONING |  | 1.05-B-1-c | Required information on all testing equipment.
| 01756 | COMMISSIONING |  | 1.05-C | Test Reports.
| 01756 | COMMISSIONING |  | 1.05-D | Operation and Maintenance (O&M) Manuals.
| 01756 | COMMISSIONING |  | 1.06-D-1-a | Qualifications and experience records of each proposed Manufacturer’s Representative who will provide field services.
| 01756 | COMMISSIONING |  | 1.06-D-1-b | After installation inspection, a written report (using the form prepared by the TSC) certifying that the equipment is installed properly, in accordance with the manufacturer’s installation instructions.
| 01756 | COMMISSIONING |  | 1.06-D-1-c | After start-up/testing, a written report (using the form prepared by the TSC) verifying that the equipment has been properly installed and lubricated and that it operated satisfactorily.
| 01756 | COMMISSIONING |  | 1.06-D-1-d | After final checkout, a written report (using the form prepared by the TSC) verifying that the equipment is in proper condition for regular continuous operation.
| 01756 | COMMISSIONING |  | 1.06-D-1-e | After post-start-up, a written report (using the form prepared by the TSC) verifying that this service has been performed and that the equipment Manufacturer’s Representative and the Contractor have inspected all equipment under this contract as installed, the appropriate adjustments have been made, and the complete system is operating in conformance with the design, specifications, and manufacturer’s requirements.
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
This is space is intentionnaly left blank for scrolling
Formulas:
NLT Date (14 days) = [Return Date]+15